## Nov 2018 tasks
Due by 01/2019 mtg |  |  | Presented at AdHoc
Section | Description | Volunteer | 2018-12-05 | 2018-12-19 | 2019-01-02
44.3 149.10 | Delay constraints - Maximum bit time, Maximum pause quanta | Use text from 126 with TBDs
125.3 149.10 | Delay constraints - Maximum bit time, Maximum pause quanta, Maximum (ns) | Use text from 126 with TBDs
149.1.3.1 | Data mode scrambler seed | Mike Tu
149.3.x | Figure 136-x Need to know if an exisiting Figure should be referenced or need the correct figure. | Paul Langner
149.3.2.3 | Need text for Normal PCS Receive function operation. | George Z. Based on first 5 paragraphs of 126.3.2.3? Needs updated as we only have one pair.
149.3.2.3.2 | PCS descrambler | Mike Tu - Text okay as is.
149.3.2.3.3 | List of Invalid blocks conditions | Brett McClellan
149.3.2.2.19 | Need to decide what to replace highlighted note with.
149.3.3 | Test-pattern generators - Need transmit and receive diagrams. | Figure numbers were added to D1.0.
149.3.4.6 | PMA training mode descrambler polynomials - all yellow | Same as 149.3.2.3.2 - Mike Tu - Text okay as is.
149.1.3.3, 149.3.2.2.1, 149.3.2.2.21, 149.3.5.3, 149.4.2.7 | Refresh period signaling - was not finalized in Bangkok. <Alert/Wake>
149.3.6 | Need complete State Diagrams section | Mike Tu provided as comment #69
149.4.2.3 | RFER - Reed-Solomon Block error rate
149.4.2.4 | Can be comment for draft to use tu_3ch_04_1018.pdf slides 4 to 7 with or without changes. | Mike Tu will provide updated presentations
149.5.1 | Test clock frquency & need final details on all test modes, much of this is still yellow | George Zimmerman, except clock frequency
149.5.2 | Output droop - need timing
149.5.2.5 | Need maximum peak output voltage. This was not provided with the PSD text.
149.7.1.5 | Need additional text for Shielding attenuation and details on test method.

## D1.0 review points
Section
45.2.3 OAM Registers | The text describing the OAM registers was added under editorial license and needs to be carefully reviewed and aligned with the text in clause 149. The editor and content provider noticed that there were technical choices to be made in aligning the text. Commenters are encouraged to review and comment on the register arrangement of the extra 4 bytes.
149.4.5, Figure 149-21 | Link Monitor - This was slide 10 of souvigner_3ch_03a_1118.pdf. There was not a motion to adopt this, but thse changes were required to match the states in the PHY Control state diagram which were adopted.
149.3.8 | New name for OAM?
149.3.8.2.1 | "dummy" OAM sent when transitioning from LPI to normal operation. Please see presentation http://www.ieee802.org/3/ch/public/adhoc/Lo_3ch_02_1218.pdf for details.

## D1.0 text neede
Motion # | Description | Mover | Seconder | Provider
4 | Scrambler for all modes | Tom Souvignier | Brett McClellan | NA
5 | LPI - need text or example Clause & State diagrams | Tom Souvignier | Saied Benyamin | Mike Tu, Jim Grabba, Tom Souvignier
6 | PSD masks - need info on what is transmitted for Test mode 5 for the measurement | Tom Souvignier | Gerrit den Besten | Assume idles are transmitted. George will try to provide a reference.
7 | PoDL | Olaf Grau | Christoph Wechsler | NA
8 | PoDL | Olaf Grau | Christoph Wechsler | NA
9 | OAM - need text including RS(16,14) | William Lo | Saied Benyamin | William Lo
10 | OAM Sttus bytes | Christoph Wechsler | Sujan Pandey | Natalie Wienckowski
11 | FEC Interleaving | Sujan Pandey | William Lo | William Lo
12 | PCS diagrams | Tom Souvignier | William Lo | NA
13 | Link Segment Frequency ranges | Gerrit den Besten | Josef Ohni | NA
14 | Link delay frequency ranges | Gerrit den Besten | Ricky Vernickel | NA
15 | MDI Return loss frequency ranges | Gerrit den Besten | Thomas Müller | NA
16 | Sheilding Attenution - provide text or clause with example text | Gerrit den Besten | Thomas Müller | George Zimmerman
17 | IL limit line | Gerrit den Besten | Ricky Vernickel | NA
18 | 2.5G RL | Gerrit den Besten | Josef Ohni | NA
19 | 5G RL | Gerrit den Besten | Thomas Müller | NA
20 | 10G RL | Gerrit den Besten | Ricky Vernickel | NA
21 | Clause 45 - Need new OAM registers | Brett McClellan | Olaf Grau | George Zimmerman
22 | Test Mode 3 - Don't need graphs in text | Conrad Zerna | Olaf Grau | George Zimmerman

## Sept 2018 tasks
Due by 11/2018 mtg |  |  | Presented at AdHoc
Section | Description | Volunteer | 2018-09-19 | 2018-10-03 | 2018-10-17 | 2018-10-31
| Interleaver Depth at each speed | Tu |  |  | planned
| IL limit for 2.5GBASE-T1 | Gerrit |  |  |  | planned
| Shielding Attenuation for each speed | Gerrit |  |  |  | planned
149.5.3.5 | Transmit Differential signal voltage, PSD
149.7 | Align maximum frequency of all link segment parameters to be the same. Current IL is 3000 MHz and RL is 5500 MHz. | Gerrit |  |  |  | planned
149.10 | Delay Constraints also in 44.3 and 125.3
45 | Registers for all speeds | George Zimmerman |  |  | planned
78.2, 149.3.5 | EEE Parameters, LPI signaling | Langner, Saied, Graba |  | planned | planned
104 | PoDL text | Heath, Gitesh
149.3.2.2.12 | PCS Scrambler | Tu, Sujan |  | planned |  | planned
149.4.3.2 | RFER (Receive Frame Error Rate)
149.4.2.4 | PHY Control function | Tu
149.4.4 | PMA State variables
149.4.5 | Startup sequence | Tu |  | planned
149.5.2 | Test Modes - don't forget additional modes for selectable fixed precoder | Langner
149.5.4.2 | Alien crosstalk noise rejection test parameters.
149.6.1 | Additional Auto-Negotiation functions
149.3.8 | OAM Frame definition | Langner, Lo, Wienckowski |  | planned | planned
Training - Where superframe starts with interleaving

## July 2018 tasks
Motion | Desc | Owner ( due 8am EDT 7/23/18)
4 | PAM 4 @ all speeds | George Z
5 | IL eq change | Natalie
6 | Impedance | Natalie
7 | Link Synchronization | Mike Tu
8 | Baud rate | George Z
9 | OAM | Natalie
10 | 10-bit RS symbol | for next step
SP
7 | Burst length - more info | Olaf K will provide info on what pulses are in a vehicle - 8/8/18 error propagation statistics - everyone to determine themselves based on their assumptions and Olaf's data
11 | IL change to 26 gauge @ 11 m | Gerrit 8/8/18
12 | Looser IL for 2.5 Gbps | Eric - 8/22/18
13, 14 | Optional Asymmetric data | Tom S & Gerrit - 8/22/18
| OAM usage definition | Jim & Natalie

## Action Items
On Track
Started, risk of being late | 2018 | [20 empty] | 2019
late | Mar |  | Apr |  | May |  |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  |  | Nov |  | Dec | Jan |  | Feb |  | Mar |  | Apr |  | May |  |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  |  | Nov |  | Dec
due date | 7,8 | 21 | 4 | 18 | 2 | 16 | 24,25 | 13 | 27 | PL | 25 | 8 | 22 | 5 | IN | 3 | 17 | 31 | PL | 28 | 12 | 9 | IN | 6 | 20 | 6 | PL | 3 | 17 | 1 | 15 | IN | 12 | 26 | 10 | PL | 7 | 21 | 4 | IN | 2 | 16 | 30 | PL | 27 | 11
OEM Topology
Consolidated Topology
OEM Power Consumption Expectations
PoDL and Power Budget
Cabling System Model - IL & RL
Thomas Mueller
Eric DiBiaso
Signaling type and modulation (2.5 Gb/s & 10 Gb/s)
Sujan Pandey
Tom Souvignier
Peter Wu
Ramin Farjad
Tazhi Madgar
Conrad Zerna
EMC testing
PHY Vendor Needs
Test Data
Line Coding and FEC
Register Maps
EEE support
PICs

## D 1.0 tasks
What's still missing. Major items only. Minor stuff and corrections not covered here.
Based on | 0.4.1
Date updated | 2019-01-08 14:12
Clause | Who to contribute text | Comments
44 |  | Introduction to 10 Gb/s baseband network Need to complete additions to add 10GBASE-T1.
45 | George | Management Data Input/Output (MDIO) Interface Collected from information in Clauses 149 & 150. Should OAM be added?
78 |  | Energy-Efficient Ethernet (EEE) Someone needs to provide the timing information for the rows to be added.
104 |  | PoDL
125 |  | Introduction to 2.5 Gb/s and 5 Gb/s networks Need to modify to add references to 2.5GBASE-T1 and 5GBASE-T1
149, 149.1.1, 149.1.2 | Natalie | Fill in open spots based on remainder of content in Clause 149.
149.1.3.1 |  | Overview - Physical Coding Sublayer (PCS)
149.1.3.3 |  | EEE capability
149.1.3.4 |  | Link Synchronization
149.1.4 |  | Signaling
149.2 |  | 2.5GBASE-T1 service primitives and interfaces
149.3 |  | 2.5GBASE-T1 Physical Coding Sublayer (PCS) functions Add OAM
149.4 |  | Physical Medium Attachment (PMA) Sublayer
149.5 |  | PMA electrical specifications - Test modes
149.6 |  | Management interface
149.7 |  | Link Segment
149.7.x |  | Differential to common mode conversion/ common mode to differential mode conversion
149.7.x |  | Coupling parameters between link segments - alien xtalk
149.7.x |  | Coupling attenuation
149.7.x |  | Transfer Impedance
149.10 |  | Delay constraints
149.11 | Curtis | PICS