## Action Items
On Track
Started, risk of being late | 2018 | [20 empty] | 2019
late | Mar |  | Apr |  | May |  |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  |  | Nov |  | Dec | Jan |  | Feb |  | Mar |  | Apr |  | May |  |  | Jun |  | Jul |  | Aug |  | Sep |  | Oct |  |  | Nov |  | Dec
due date | 7,8 | 21 | 4 | 18 | 2 | 16 | 24,25 | 13 | 27 | PL | 25 | 8 | 22 | 5 | IN | 3 | 17 | 31 | PL | 28 | 12 | 9 | IN | 6 | 20 | 6 | PL | 3 | 17 | 1 | 15 | IN | 12 | 26 | 10 | PL | 7 | 21 | 4 | IN | 2 | 16 | 30 | PL | 27 | 11
OEM Topology
Consolidated Topology
OEM Power Consumption Expectations
PoDL and Power Budget
Cabling System Model - IL & RL
Thomas Mueller
Eric DiBiaso
Signaling type and modulation (2.5 Gb/s & 10 Gb/s)
Sujan Pandey
Tom Souvignier
Peter Wu
Ramin Farjad
Tazhi Madgar
Conrad Zerna
EMC testing
PHY Vendor Needs
Test Data
Line Coding and FEC
Register Maps
EEE support
PICs

## D 1.0 tasks
What's still missing. Major items only. Minor stuff and corrections not covered here.
Based on | D2.2.2
Date updated | 2018-03-20 15:10
Clause | Who to contribute text | Comments
30 | Natalie | Management Most of this can be completed as information is provided in Clauses 149 & 150.
45 | Natalie | Management Data Input/Output (MDIO) Interface Collected from information in Clauses 149 & 150. Does Adam assign the register numbers or do we just pick?
78 |  | Energy-Efficient Ethernet (EEE) Someone needs to provide the timing information for the rows to be added.
98B.3 |  | Need to add bit definitions for 2.5GBASE-T1, 5GBASE-T1 and 10GBASE-T1. Need to coordinate with cg. - email sent
98.B.4 | Natalie | Add 2.5GBASE-T1, 5GBASE-T1 and 10GBASE-T1 to Priority Resolution list from fastest to slowest.
104 |  | PoDL Is anything needed?
149, 149.1, 149.2 | Natalie | Fill in open spots based on remainder of content in Clause 149.
149.1.2.1 |  | Overview - Physical Coding Sublayer (PCS)
149.1.2.2 |  | Overview - Physical Medium Attachment (PMA) sublayer
149.1.2.3 |  | EEE capability
149.1.2.4 |  | Link Synchronization
149.1.3 |  | Signaling
149.1.4 | Natalie | Interfaces
149.1.5 | Natalie | Conventions - similar in all PHY Clauses
149.2 |  | 2.5GBASE-T1 service primitives and interfaces
149.3 |  | 2.5GBASE-T1 Physical Coding Sublayer (PCS) functions
149.4 |  | Physical Medium Attachment (PMA) Sublayer
149.5 |  | PMA electrical specifications
149.6 |  | Management interface
149.7.x | Natalie | Differential characteritic impedance Need to decide if we want to put a tolerance on 100 ohms, e.g. 3%.
149.7.x |  | Do we need Differential to common mode conversion?
149.7.x |  | Maximum link delay
149.8 |  | MDI specification
149.9 | Natalie | Environmental specifications Text approved at March 2018 Interim
149.10 |  | Delay constraints
149.11 | Curtis | PICS
150, 150.1, 150.2 | Natalie | Fill in open spots based on remainder of content in Clause 150.
150.1.3.1 |  | Overview - Physical Coding Sublayer (PCS)
150.1.3.2 |  | Overview - Physical Medium Attachment (PMA) sublayer
150.1.3.3 |  | EEE capability
150.1.3.4 |  | Link Synchronization
150.1.4 |  | Signaling
150.1.5 | Natalie | Interfaces to be inserted prior to current 149.1.4 Conventions in this clause and after Signaling.
150.1.6 | Natalie | Conventions - similar in all PHY Clauses
150.2 |  | 5GBASE-T1 and 10GBASE-T1 service primitives and interfaces
150.3 |  | 5GBASE-T1 and 10GBASE-T1 Physical Coding Sublayer (PCS) functions
150.4 |  | Physical Medium Attachment (PMA) Sublayer
150.5 |  | PMA electrical specifications
150.6 |  | Management interface
150.7.x | Natalie | Differential characteritic impedance Need to decide if we want to put a tolerance on 100 ohms, e.g. 3%.
150.7.x |  | Do we need Differential to common mode conversion?
150.7.x |  | Maximum link delay
150.8 |  | MDI specification
150.9 | Natalie | Environmental specifications Text approved at March 2018 Interim
150.10 |  | Delay constraints
150.11 | Curtis | PICS