## Action Items
Planned to vote
On Track
Started, risk of being late
late
Task | Subtask | Owner | 2020 | [9 empty] | 2021
|  |  | Aug | Sept |  |  | Oct |  | Nov |  | Dec |  | Jan |  | Feb |  | Mar |  |  | Apr |  | May |  | Jun |  |  | Jul |  | Aug |  | Sept |  |  | Oct |  | Nov |  |  | Dec
|  |  | 18 | 1 | 15 | IN | 6 | 20 | 3 | PL | 1 | 15 | 5 | IN | 2 | 16 | 2 | PL | 30 | 13 | 27 | 11 | IN | 1 | 15 | 29 | PL | 27 | 10 | 24 | 7 | IN | 28 | 12 | 26 | 9 | PL | 30 | 14 | 28
Draft to-do list |  | Luisma Torres
Timeline approval |  | Bob Grow
In-vehicle link requirements that will shape the optical channel specifications | Mechanical requirements
Environmental requirements
Relative cost analysis |  | Rick Pimpinella
Link budget analysis (≤ 25 Gb/s) | PCS encoding, frame structure, modulation scheme, FEC | Rubén Pérez de Aranda
Optical channel, and O/E receiver model
Reliability assessment — “reliability constrained link budget” | Reliability assesment reports
Link budget impact
Optical connector requirements |  | Steven Swanson
Transceiver specification (PMD)
Link budget analysis (> 25 Gb/s) | VCSEL characterization
PCS encoding, frame structure, modulation scheme, FEC
Optical channel, and O/E receiver model