## Slide 1: 802.11F Meeting Report Nov 2000
The group that got no respect this week….
Notes: Page <number>
        <footer>
<header>
<date/time>

## Slide 2: The between Sept & Nov mtg plan
Ad-Hoc discussions by interested parties will continue up to Nov mtg.
  Goal was to derive common proposal text for further consideration in Nov.
  Two calls scheduled
    One happened, 2nd called but no one attended.

## Slide 3: Nov mtg progress prevented by over scheduling of meetings
When 11E & F were first set up, the agreement was that they would not be run in parallel (at the request of the .11 membership)
  This was changed this week due to the establishment of multiple E sub groups, resulting in an experiment with parallel E&F sessions.
  11F chair expressed concern over this prior to mtg week, experiment went ahead over objection.
  This has impacted 11Fs ability to get work done
    Monday – 9 people, 3 voters + chair; Tuesday – 12 people, 4 voters + chair; Thurs: 4 people, 1 voter + chair
  The Level of industry interest in IAPP is not implied by attendance, what is implied is that WLAN brains are a scarce physical resource that can’t be in multiple physical locations simultaneously…

## Slide 4: Nov 2000 802.11 F Agenda
Administration Stuff
Goals for Mtg
Papers & discussion
Adjournment

## Slide 5: Admin Stuff
Secretary: Mahesh Venkatraman
  (for this mtg only).
Approval of minutes from Sept
  This is where it started, we couldn’t get minutes approved from Sept…
    Moved: Bob Ohara
    Second: none… (Other voter had not read them yet)
    Vote: n/a
Notes: Page <number>
        <footer>
<header>
<date/time>

## Slide 6: Nov Goals
1st draft text
  and maybe
First internal .11 ballot after Nov mtg
  It all depends on the amount of effort volunteered between now and Nov…

## Slide 7: Approved Target 11F Schedule
1st TG mtg, IAPP history review, task framing – May 2000
Functional determination, proposals – July 2000
1st Draft written, review starts – Nov 2000
  Cut off for additional DS environment inclusion.
First internal .11 ballot – Nov 2000
  But need a draft to ballot….!
  Schedule now slipping.
Schedule fork issue decision – Jan 2001
  Hold for 11E progress or start external ballots…?
Notes: Page <number>
        <footer>
<header>
<date/time>

## Slide 8: Papers
None new, discussed 345R1 on Tuesday.

## Slide 9: 11F Motion: Recess & Regroup
Moved: That 802.11F recess until the scheduled Thurs morn session. In the meantime the Chair (with the input of any interested parties) is to figure out a proposal for continuing work in light of the 802.11 scheduling issues; this will be discussed with 11F on Thurs morn with the intent that 11F decide and recommend to the Plenary on Thurs afternoon a revised work plan.
  Moved: Bob O’Hara
  2nd: Gary Spiess
  Vote: unanimous (2,0,0…..)

## Slide 10: Target 11F Schedule (plan of record prior to today – now obsolete)
1st TG mtg, IAPP history review, task framing – May 2000
Functional determination, proposals – July 2000
1st Draft written, review starts – Nov 2000
  Cut off for additional DS environment inclusion.
First internal .11 ballot – Nov 2000
  But need a draft to ballot….!
  Schedule now slipping.
Schedule fork issue decision – Jan 2001
  Hold for 11E progress or start external ballots…?
Notes: Page <number>
        <footer>
<header>
<date/time>

## Slide 11: “Plan B” schedule

## Slide 12: 802.11F work recovery plan
Step 1: Attempt recovery by offering interested parties a venue for an Ad Hoc (non-binding) session to work out a base proposal/draft. Resulting draft to be brought to Jan mtg for consideration as candidate for first (internal) LB.
  Tentative Mtg target week 12/3 (2 days?); location TBD; will be announced on reflector; mtg facilities will be provided; on your own for hotel
If step 1 successful, proceed to LB in Jan/Mar with Ad-Hoc mtg draft (if approved in Jan)
If step 1 not successful, recognize that re have people resource conflicts and re-sched work to be dependent on 11e settling down and freeing people up (schedule impact unknown at this date).

## Slide 13: Revised 802.11F Schedule (assuming ad-hoc mtg progress)
1st TG mtg, IAPP history review, task framing – May 2000
Functional determination, proposals – July 2000
Cut off for additional DS environment inclusion. – Nov 2000
Ad-Hoc drafting recovery mtg Dec 2000
1st Draft available, review starts – Jan 2000
First internal .11 ballot – Mar 2000
Schedule fork issue decision – May 2001
  Hold for 11E progress or start external ballots…?
Notes: Page <number>
        <footer>
<header>
<date/time>

## Slide 14: Non-parallel meeting motion
Whereas:
  1) 802.11 has multiple Open active PARs, all of which need to make progress, and
  2) The set of members needed to make progress on both have significant people in common between 11E & 11F topics, and
  3) When 802.11E and 802.11F were setup, 802.11 committed that E&F mtgs would not be in parallel, and
  4) an experiment in scheduling was tried this week where E&F mtgs were overlapping, and this resulted in a significant negative impact to 802.11F progress;
Moved: 802.11F moves that future 802.11 meetings not repeat the experiment of scheduling overlapping 802.11E and 802.11F meetings sessions.

## Slide 15: End of report
Questions?