## Slide 1: IEEE 802.15 Working Group for Wireless Personal Area Networks
Thoughts on Project Management

## Slide 2: Agenda
WPAN Project Management
  Project Tasks
  Milestones
Duration vs. Effort

## Slide 3: Milestone - Project Tasks
Project Authorization Request Approved
Press Release
Liaisons
Call For Proposals (CFP)
First Unapproved WPAN Draft Specification
Draft Specification approved by 802.15 WG
Draft Specification approved by IEEE SAB

## Slide 4: Milestone - Gantt Chart #1
Assumptions:
  Effort Driven
  60 day cycles from receipt of draft to WG LB and Sponsor LB

## Slide 5: Milestone - Gantt Chart #2
Assumptions:
  Effort & Event Driven
  60 day cycles from receipt of draft to WG LB and Sponsor LB

## Slide 6: Milestone - Gantt Chart #3
Assumptions:
  Event Driven
  60 day cycles from receipt of draft to WG LB and Sponsor LB

## Slide 7: Milestone - ~50 Meeting Days
VENUE DAYS START STOP
Chiba Japan 2d Wed 5/5/99 Thu 5/6/99
London, England 1d Mon 6/7/99 Mon 6/7/99
Montreal, Canada 5d Mon 7/5/99 Fri 7/9/99
Denver, Colorado 2d Thu 8/5/99 Fri 8/6/99
Santa Rosa, California 5d Mon 9/13/99 Fri 9/17/99
Kauai, Hawaii 5d Mon 11/8/99 Fri 11/12/99
Israel 5d Mon 1/10/00 Fri 1/14/00
Albuquerque, NM 5d Mon 3/6/00 Fri 3/10/00
? 5d Mon 5/15/00 Fri 5/19/00
LaJolla, California 5d Mon 7/10/00 Fri 7/14/00
? 5d Mon 9/18/00 Fri 9/22/00
Tampa, Florida 5d Mon 11/6/00 Fri 11/10/00
IEEE 802 Plenary

## Slide 8: Milestone - Gantt Chart #4

## Slide 9: Duration vs. Effort Driven Tasks
Duration is the length of time (calendar time) the task is scheduled to occur.
  November 2000 is ~17 months away
Effort is the amount of work (resource assignments) to be done on the task.
  Consortia do not have time to work both in Industry and SDOs
  The WG has limited technical resources