## Project
TASK NAME | DESCRIPTION | DURATION | START | FINISH
Handoff of Bluetooth Specification | Handoff officially occured when the Bluetooth SIG approved the submission of D0.6 to the IEEE P802.15 Working Group | 0 days | 1999-11-10 08:00 | 1999-11-10 08:00
Comment Resolution Database Creation | Microsoft Access will be used to process and archive all comments received during the balloting process. This database will be custom defined for this application. | 20 days | 1999-11-10 08:00 | 1999-12-07 17:00
Ballot Procedure Formalization Discussion | Starting with the letter from Jim Kardach, Dr. Chatschik Bisdikian, Mr. Ian Gifford, Mr. Tom Siep have drafted a letter and agreed to this PERT. | 0.5 days | 1999-11-10 08:00 | 1999-11-10 12:00
Letter Ballot #1 | Distribution of Draft 0.6, ballot form, comments form, and instructions to the voting members of IEEE P802.15. There is a 30 voting period during which the members decide if the Draft is acceptable to be sent to the Sponsor Ballot voters. At a minimu... | 30 edays | 1999-11-10 08:00 | 1999-12-10 08:00
Formalization Proposal | Creation and transmittal of this PERT with a cover letter to Jim Kardach | 1 day | 1999-11-10 13:00 | 1999-11-11 12:00
Review of Formalization Proposal | Bluetooth SIG reads, understands, and agrees to processes specified in the letter and PERT. | 14 days | 1999-11-11 13:00 | 1999-12-01 12:00
Ready for Comment Resolution | All prequisite tasks have been satisfied to enable the processing of comments | 0 days | 1999-12-07 17:00 | 1999-12-07 17:00
Comments Loaded into Database | All voters' comments are loaded into the database. Any Bluetooth comments are also loaded. | 3 days | 1999-12-10 08:00 | 1999-12-14 17:00
Comments Published to 802.15 and BTWG | A summary report sorted by clause number is generated from the Comment Resolution Database. | 0 days | 1999-12-14 17:00 | 1999-12-14 17:00
BTWG Response to Comments | Bluetooth internal review and generation of responses to comments registered by P802.15 voting members. | 21 edays | 1999-12-14 17:00 | 2000-01-04 17:00
Produce BTWG Summary Report | Production of a single report that represents the Bluetooth SIG's official position and response to the Comments against D0.6 | 3 days | 2000-01-05 08:00 | 2000-01-07 17:00
IEEE 802.15 Interim Meeting | Meeting in Tel Aviv to resolve comments against D0.6. The anticipated output of the meeting is:... | 5 days | 2000-01-10 08:00 | 2000-01-14 17:00
Prepare Summary of Technical Issues | Collection of all proposed changes to D0.6 and a description of the Action Items to be completed by specified indivuals by a specified time. | 5 days | 2000-01-17 08:00 | 2000-01-21 17:00
802.15 Action Item Completion |  | 12 edays | 2000-01-21 17:00 | 2000-02-02 17:00
BTWG Approval/Updates | Bluetooth internal review and generation of responses to proposed changes to the Draft. | 14 edays | 2000-01-21 17:00 | 2000-02-04 17:00
Draft 1.0 Creation | Application of the changes specified by the Technical Issues document. | 5 days | 2000-02-07 08:00 | 2000-02-11 17:00
BTWG Approval of Draft 1.0 | Bluetooth internal review and generation of application of changes to the Draft. | 5 days | 2000-02-14 08:00 | 2000-02-18 17:00
Recirculation or Confirmation Ballot | Ballot by the P802.15 membership on the changes to the Draft. Only those clauses that have changed from D0.6 to D1.0 are eligible for comment in this round of voting.... | 15 edays | 2000-02-18 17:00 | 2000-03-04 17:00
Comments Loaded into Database | All voters' comments are loaded into the database. Any Bluetooth comments are also loaded. | 3 days | 2000-03-06 08:00 | 2000-03-08 17:00
BTWG Response to Comments | Bluetooth internal review and generation of responses to comments registered by P802.15 voting members. | 10 edays | 2000-03-08 17:00 | 2000-03-18 17:00
IEEE 802 Plenary Meeting | Determination will be made if Draft is ready for Sponsor Ballot or needs further work and recirculation. | 5 days | 2000-03-13 08:00 | 2000-03-17 17:00