## Slide 1: IEEE P802.15 Working Group for Wireless Personal Area Networks
Timeline/Milestone

## Slide 2: Contents
Introduction
  The Ballot Process
  The Ballot Process w/ Bluetooth
Timeline/Milestone
  Roadmap #1
  Roadmap #2
  Timeline/Milestone
Next Steps
  1, 2, 3, and 4 (Issues)
Backup
  Overview of the IEEE P802 Standards Process

## Slide 3: You are here in the Ballot Process
You are here 14Sep99

## Slide 4: The Ballot Process w/ Bluetooth
?
BT-IEEE
Editorial
Working Group
Yes
Resolvable
Negatives?
Bluetooth SIG
Peer Review
“Ballots”
Make
Changes to
Obtain BT
PM Approval
No
Yes/No
BT PM
Decision to
Submit

## Slide 5: TG1 Ballot Roadmap #1
WG
LB
#1
1999
2000
9/99
Today
11/99
8/99
12/99
WG Balloting
2/00
3/00
4/00
5/00
6/00
7/00
8/00
9/00
10/00
11/00
12/00...
10/99
Sponsor
Balloting
WG Letter
Ballot
#1
WG Letter
Ballot
#2
WG
LB
#2
TG 1 wants
Sponsor Says
HI
CA
IL
NM
WA
CA
?
FL
Meetings/
Events
IEEE
ETSI?
Sponsor
Ballot
#1
Sponsor
Ballot
#2
WG
LB #3
Option

## Slide 6: TG1 Ballot Roadmap #2
1999
2000
9/99
Today
11/99
8/99
12/99
WG Balloting
2/00
3/00
4/00
5/00
6/00
7/00
8/00
9/00
10/00
11/00
12/00...
10/99
Sponsor
Balloting
WG Letter
Ballot
#1
WG Letter
Ballot
#2
Sponsor Says
the TG1 Agrees
HI
CA
IL
NM
WA
CA
?
FL
Meetings/
Events
IEEE
ETSI?
Sponsor
Ballot
#1
Sponsor
Ballot
#2

## Slide 7: Overview of the Tasks
Bluetooth SIG Letter of Intent (JK)
Meeting #1 July 5-9, 1999 Montreal, PQ, Canada
P802.15 Finalize the Copyright License Agreement (IG)
Meeting #2 September 13-17, 1999 Santa Rosa, CA USA Hilton 802.15 Interim Meeting.
BT-IEEE WG Finalize Draft Standard (TS)
BT-IEEE WG Submit Draft Standard to BSIG Program Management (CB)
BSIG Review Derivative Draft Standard Submission (BSIG)
BSIG Disposition Draft Standard/Submit to IEEE P802.15, if ok (JK)
Meeting #3 November 8-12, 1999 Kauai, Hawaii Hyatt Regency, 802 Plenary Meeting.
P802.15 Authorize P802.15 WG LB #1 between the Sep99 - Nov99 (BH)
P802.15 Compose P802.15 WG Electronic Letter #1 Ballot (BH)
P802.15 Upload Draft Standard to the private Web Site (IG)
P802.15 WG Letter Ballot #1 Package Distribution (BH)
P802.15 Letter Balloting (WG)
P802.15 Process and Consolidation Comments (?)
P802.15 WG LB #1 Comment Resolution (WG)
Meeting #4 January 10-14, 2000 Tel-Aviv, IL InterContinental, 802.15 Interim Meeting.
Meeting #5 March 6-10, 2000 Albuquerque, NM Hyatt Regency, 802 Plenary Meeting.

## Slide 8: Timeline/Milestone
= Critical Path Dates

## Slide 9: Timeline/Milestone
Next Steps

## Slide 10: Step 1: Finish P802.15.1 Draft on or before 1Nov99
Our plan is to be here 1Nov99 and to
post to the P802.15 Private Web Site

## Slide 11: Step 2: Our plan is to start the Letter Ballot #1 Process on or before 8Nov99
Our plan is to be here 8Nov99 and to
Vote LB#1 and release the same day

## Slide 12: Step 3: Our plan is to stop the Letter Ballot #1 Process on 13Dec99
Our plan is to be here 13Dec99 and to
release LB Comments the same day

## Slide 13: Step 4: Issues to consider
WG Recirculation Letter Ballot? If yes, Pre Tel-Aviv or Post Tel-Aviv?
Tel-Aviv Interim Meeting Quorum?
WG Tel-Aviv Interim Meeting Balloting vs. Letter Ballot?
Sponsor Ballot submission is 18Feb99
The Task Group 1 suggest that we identify the Post LB #1 next
steps after the Comments are received.

## Slide 14: Timeline/Milestone
Backup

## Slide 15: The 802 LMSC Standards Process
Each standard (or recommended practice, or guide) starts as a group of people with an interest in developing the standard. A Project Authorization Request (PAR) is normally submitted for approval within 6 months of the start of work. In LMSC, new projects require supporting material in the form of '5 criteria' to show that they meet the charter of LMSC. The draft PAR is voted on by the SEC, and then goes to the IEEE Standards Board New Standards Committee (NesCom) which recommends it for approval as an official IEEE Standards project.
Part of the PAR identifies which outside standards groups there will be liaisons with, for instance ITU for some international standards. The liaisons help avoid conflicts or duplication of effort in one area.

## Slide 16: The 802 LMSC Standards Process (cont.)
Proposals are evaluated by the WG, and a draft standard is written and voted on the by the WG. The work progresses from technical to editorial / procedural as the draft matures. When the WG reaches enough consensus on the draft standard, a WG Letter Ballot is done to release it from the WG. It is next approved by the SEC and then goes for Sponsor Letter Ballot. In the past, the sponsor group was the Technical Committee on Computer Communication, so the sponsor ballot is still referred to sometimes as a TCCC ballot, even though LMSC now is a sponsor and conducts its own Sponsor Letter Ballots.

## Slide 17: The 802 LMSC Standards Process (cont.)
After the Sponsor Letter Ballot has passed and 'No' votes are answered, the draft Standard is sent to the IEEE Standards Board Standards Review Committee (RevCom).
Once recommended by RevCom and approved by the Standards Board, it can be published as an IEEE standard.
Most draft standards in LMSC are also sent to ISO at or before the time they go to Sponsor Letter Ballot. A parallel approval path is followed in ISO JTC1/SC6 (Joint Technical Committee 1, Subcommittee 6 - responsible for LANs) that leads to publication as an ISO standard.
The process from start to finish can take several years for new standards, and less for revisions or addenda.