## Slide 1: IEEE 802.15 Working Group for Wireless Personal Area Networks
WG Ballot Planning

## Slide 2: Contents
Introduction
TG1 Timeline Overview or Where, What When
Next Steps prior to Balloting
Working Group Planning
Sponsor Ballot Planning

## Slide 3: Where - TG1 is here
~Jun97 - Idea for standard
Mar98 - Find Sponsor
Feb99 - Submit PAR
Mar99 - Approve PAR
Jul99 - Organize working group
Sep99 - Develop draft standard
? - Ballot draft standard
? - Approve draft standard
? - Publish approved standard
You are here

## Slide 4: What - TG1 is here
Write scope and purpose
Examine related standards and publications
Draft outline
Fill in outline
Revise, revise, revise
Finalize document
You are here

## Slide 5: When - TG1 done by Dec00
~Jun97 - Idea for standard
Mar98 - Find Sponsor
Feb99 - Submit PAR
Mar99 - Approve PAR
Jul99 - Organize working group
Sep99 - Develop draft standard
Nov99 - Ballot draft standard
Mar00 - Approve draft standard
Dec00 - Publish approved standard
You could be here

## Slide 6: Importance of IEEE-SA and Sponsor Balloting
Ballot work actually begins while you're finalizing your draft, with the formation of your balloting group. Many sponsors have particular rules of how the balloting group is to be formed, so we should examine those carefully before taking any action. It is the responsibility of the sponsor to form the balloting group.

## Slide 7: IEEE-SA has identified three (3) Membership Balloting processes
Individual Member Balloting
Entity Member Balloting
Mixed Membership Balloting, combination the above two (Still being determined by the SASB)
Our P802.15 sponsor indicated on the Project Authorization Request (PAR)
that Individual Member Balloting will be used, and that the process
will be followed throughout the P802.15 standard’s development.
Note: IEEE-SA membership, both individual and corporate: 3364 individual members and 8 corporate members, Jul99

## Slide 8: Sponsor Ballot Pool
3364 Individual
8 Corporate
1 Organizational
Representative
Current
3364 Individual
8 Corporate
New
1 Organizational Representative
40

## Slide 9: IEEE-SA Standards Management and Committee Services program
The IEEE-SA Standards Management and Committee Services program offers a flexible set of dedicated standards development services to IEEE working groups and sponsors. These services are intended to accelerate the development, approval, and publication of IEEE Standards.
The services are cost-based, through fees for services provided to traditional IEEE working groups and sponsors. Each group can set its program and its budget based upon the group's priorities, requirements, and funding.

## Slide 10: Available services include traditional association management offerings such as:
Project management
Contract management
PAR and RevCom submittal support
Balloting and peer review services
Process support meeting/workshop support
Editorial and publishing services
Electronic services
Contact Jerry Walker, Business Development Manager
for IEEE Standards Activities, to find out more information.

## Slide 12
IEEE Standards sponsor-level ballots
  http://standards.ieee.org/db/balloting/
IEEE Standards Balloting Reports On-line
  http://standards.ieee.org/db/balloting/

## Slide 13: Timeline - Scenario 1
1997
1998
1999
2000
IEEE P802.11 Study Group
for WPANs
IEEE P802.15 Working
Group for WPANs
6/97
3/98
3/99
IEEE Ad Hoc “Wearables”
Standards Committee
1
CFP
5/98
9/98
1
CFA
6/99
2
CFP
2001
Draft
STD

## Slide 14: Conclusion
The IEEE Working Group cannot make obligations as no one can project the future.
If the Bluetooth SIG promoters do not agree with what is put into the 802.15 standard, then they can tell their members not to support it and not to provide any IPR and the standard is stopped.
The standard would be stopped on IPR grounds or become a shell of a piece of paper that is not worth much.
The IEEE is very interested and is willing to continue the
process and we understand the BT requirements.

## Slide 15: The Specification and resultant IEEE 802.15 standard are required to be:
a) 100% compatible with the Bluetooth 1.0 Foundation Specification (as measured by a certified Bluetooth test house)
b) Maintains and requires inclusion of Bluetooth testing interfaces as described in the current Bluetooth specification (to allow interoperability testing between Bluetooth and 802.15 compliant solutions)
c) Any 802.15 extensions (beyond Bluetooth 1.0 specification) must not break interoperability with existing Bluetooth 1.0 certified radios and be approved by the Bluetooth SIG Promoters
Source:BSIG Letter to IEEE, http://grouper.ieee.org/groups/802/15/pub/Proposals.htm