## Slide 1: IEEE P802.15 Working Group for Wireless Personal Area Networks
Bluetooth Program Management
&
IEEE P802.15 Working Group
Joint Meeting

## Slide 2: Joint Topics
P802.15.1 WPAN Timeline
  Overview
  Draft Status
IEEE Sub Working Group Status?
  Coexistence SG
  WPAN-HR SG
  WPAN-LR SG
Bluetooth SIG2 and IEEE P802.15?
OUI Issues & Status?
Testing Status?
BQRB Inquiry?
Notes: These Joint Topics were identified on 8Dec99 by Chatschik Bisdikian, Bluetooth IEEE Working Group Chair. The italicized topics are from the Bluetooth PM.

## Slide 3: IEEE WPAN Timeline - Overview
1997
1998
1999
2000
IEEE P802.11 Study Group
for WPANs
IEEE P802.15 Working
Group for WPANs
6/97
3/98
3/99
IEEE Ad Hoc “Wearables”
Standards Committee
CFP #1 5/6/98 to 3/12/99
5/98
7/98
CFA #1 7/24/98 to 3/12/99
3/18/99
Approved
PAR
6/99
CFP #2
6/14/99
- 7/1/99
7/99
CFI #1
9/13/99
- 9/17/99
Today
Notes: IEEE Ad Hoc “Wearables” Standards Committee
This activity was kicked off in IEEE PASC on 16Jul97 after a Jun97 Meeting with the IEEE Standards Board
This group was hibernated after the WPAN Air Link was determined as the first step and that a Study Group could be formed in IEEE P802.11
IEEE P802.11 Study Group
The SG drafted a PAR and after a year long review (3 lifecycles of SG’s) the PAR was forwarded to our Sponsor and approved.
The P802.15 WG was voted on and approved for forwarding to IEEE 802 LMSC SEC on 9Mar99, The SEC approved the PAR to be forwarded to NesCom
IEEE P802.15 Working Group for WPANs
The WG PAR was approved by NesCom on 18Mar99
The WG had their first meeting during the Jul99 IEEE 802 Plenary in Montreal

## Slide 4: TG1 Ballot Roadmap
WG
LB
#1
1999
2000
9/99
Today
11/99
8/99
12/99
WG Balloting
2/00
3/00
4/00
5/00
6/00
7/00
8/00
9/00
10/00
11/00
12/00...
10/99
Sponsor
Balloting
WG Letter
Ballot
#1
WG Letter
Ballot
#2
TG 1 Budget
Sponsor Says
HI
CA
IL
NM
WA
CA
TN
FL
Meetings/
Events
IEEE
ETSI?
Sponsor
Ballot
#1
Sponsor
Ballot
#2
TG 1 Actual
WG
LB
#2
WG
LB #3
Option
WG
LB
#1
WG
LB
#2
Sponsor
LB
#1
Notes: This slide provides an overview of the TG1 Ballot Roadmap. The WG vs.. Sponsor rectangles at the top indicate the two (2) phases of the Balloting Process. Sponsor means Jim Carlo IEEE 802 Chair. The TG1 Budget vs.. Actual is way to show our pre and post Letter Ballot #1 planning. The Meeting/Events are key tasks in the IEEE Balloting Process or Roadmap.

## Slide 5: Attendance, 8Dec99
Bluetooth
Warren Allen Toshiba warren.allen@tais.toshiba.com
Tom Baker Lucent twbaker@lucent.com
Chatschik Bisdikian IBM bisdik@us.ibm.com
Mike Foley Microsoft mfoley@microsoft.com
Jon Inouye Intel jon.w.inouye@intel.com
James Kardach Intel jim.kardach@intel.com
Peter Lee IBM leep@us.ibm.com
Dave Leeper Motorola dave.leeper@mot.com
Thomas Müller Nokia thomas.t.muller@nokia.com
Jan Ritmeester Ericsson jan.willem.ritmeester@erh.ericsson.se
Tod Sizer Lucent ts2@lucent.com
Nick Thomas 3Com nick_thomas@mtn.3com.com
Mike Wehrs Microsoft mwehrs@microsoft.com
IEEE
Ian Gifford M/A-COM giffordi@ieee.org
Bob Heile GTE bheile@bbn.com
Tom Siep Texas Instruments siep@ti.com