## Slide 1: IEEE P802.15 Working Group for Wireless Personal Area Networks
TG1 Report #2
David Intercontinental Hotel 12, Kaufman St. Tel Aviv Israel

## Slide 2: Contents
TG1 Summary
Overview of Tel-Aviv
  Objectives
  Submissions
  Motion Scheduling
  Session
Next Steps

## Slide 3: Summary
LB1 yielded 1013 comments to be resolved against P802.15.1/D0.6
  193 Technical Comments and
  818 Editorial Comments
LB1 Comment Resolution 10Jan00 - 11Feb00
LB(2) 21Feb00 to 2Mar00
LB(3) 19May00 to 22Jun00
Draft ready for Sponsor Ballot Jul00

## Slide 4: Tel-Aviv Objectives
1. LETTER BALLOT 1 COMMENT RESOLUTION/DISPOSITION
2. PROVIDE AN UPDATE ON TG1
3. PROVIDE AN OVERVIEW OF THE BLUETOOTH VERSION 1.0 B SPECIFICATION(S), IN SESSION & TUTORIAL
4. PLAN FOR DRAFT STANDARD
5. VOTE TO FORWARD/RECIRCULATE THE DRAFT TO SPONSOR/WG RECIRC LB
6. VOTE TO REVIEW THE RECIRC COMMENTS FROM WG LB #X BEFORE PLENARY

## Slide 5: Tel-Aviv - Submissions

## Slide 6: TG1/WG Motion Scheduling
Motions
  Motion #1 - Empower the WG Technical Editor for resolution
  Motion #2 - Empower the WG to recirculate a Draft LB

## Slide 7: MOTION #1
MOTION: I move that we empower the WG Technical Editor to be able to continue with TG1 Comment Resolution between 14Jan00 & 5Mar00.
Non Technical 50% (Procedural)
Mover: Ian
Second: Tom
Y/N/A: 8/0/0
Pass/Fail?: Pass

## Slide 8: MOTION #2
MOTION: I move that we empower the WG chair to be able to conduct a 10 Day Electronic Letter Ballot for approval of the application of -99/173r5 to the current P802.15.1 Draft Standard between 14Jan00 & 5Mar00.
Non Technical 50% (Procedural)
Mover: Ian
Second: Tom
Y/N/A: 8/0/0
Pass/Fail?: Pass

## Slide 9: New TG1 -99/160r1 Graphic
Note: This graphic describes the weekly session of the IEEE P802.15, w/ TG1 highlighted. TG1 are r1 new adds.

## Slide 10: Next Steps/TG1 Roadmap
14Jan00 post Tel-Aviv, IL
  Complete Comment Resolution(s) -99/173r5
  Change IEEE P802.15.1/D0.6 to reflect Bluetooth Specification(s) v1.0 B; will become P802.15.1/D0.7
  Electronic Letter Ballot of the -99/173r5
6-10Mar00 Albuquerque, NM USA
  Based on results of Ballot apply -99/173r5 to P802.15.1/D0.7 this becomes P802.15.1/D0.8
8-12May00 Seattle, WA USA
  Electronic Letter Ballot of P802.15.1/D0.8
10-14Jul00 LaJolla, CA USA
  LB Comment Resolution of P802.15.1/D0.8

## Slide 11: Comment Codes
[1] Planned
  TG1 Concurs
[2] Research
  TG1 needs to do more research
[3] Discussion
  TG1 needs to discuss in more detail
[4] Clarification
  TG1 will request more detail from the Author
[5] BSIG Discussion
  TG1 needs to discuss the comment w/ BSIG
[6] Decline
  TG1 declines the comment from the Author
[7] Verify
  TG1 we need to review Bluetooth Specification(s) v1.0 B
[8] Defer
  TG1 requires and Bluetooth has not determined need
[9] Editor Discretion
  Anything coded as E/e/N

## Slide 12: LB1 Results - Overview
42 Total Voting Members
35 Total Votes (18/15/2)
7 Total Failed to vote (2 of 7 were incomplete No's)

## Slide 13: LB1 Results - Detail
a = Abstain
n = Do Not Approve (Negative)
y = Approve (Affirmative)
/c = with Comments
w/o = with out Comments
y = failed to respond

## Slide 14: Type of comments (e/E/t/T) - LB1 #
TG1 appreciates the work the eighteen (18) Members did
in providing these 1013 Comments! 2 not coded.
Notes: Notes:
NadaG used a non-standard Type of Comment e.g., 32 "E/t" and 4 "e/t". I am unclear how to deal with these comments. The Editor-in-Chief interpreted them as "t’s”; which nets 59 total of which 36 are hybrid.
PatK forgot to code pwk19 e.g., Type of Comment e.g., "E/t/e/t”.
HoumanA used a non-standard numbering for comments e.g., 8a, 8b, etc. indicating he did not read the instructions. He supplied 62 not 48 comments.
MikeP used "e" 100% in the Type of comments (E/e/T/t) and added the N, t, T in the Part of NO vote (Y/N); indicating he did not read the instructions. Therefore he has 139 "e's" and he added 4 "t’s" and 3 "T’s" to the wrong column hence -7 "e’s" and a some T/t entries.
Dropped Dr. Yunxin Li as I could not find his comments. Source: BobH results *.xls file. FOUND 10JAN00…All 250 of them! He forgot to code yxl007.
Dropped Mr. Daniel R. McGlynn & Mr. Ivan Reede as they did not supply Comments w/ their “Nea” vote. Therefore these balloters failed to vote. Note: Ivan indicated 7Jan00 that he would change his “Nea” to a “Yea” w/o Comments if it stalled the WG Balloting process. He will not supply comments on his nea vote - lost HD & NadaG covered his comments.

## Slide 15: Type of comments (e/E/t/T) - LB1 #/%
1011 Comments
Minor Editorial "e”
  454 (45%)
Major Editorial "E”
  364 (36%)
Minor Technical "t”
  99 (10%)
Major Technical "T”
  94 (9%)