IEEE P802.15

Wireless Personal Area Networks

| Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs) |  |
| --- | --- | --- |
| Title | Project Plan for completion of 802.15.1 |  |
| Date Submitted | [The date the document is contributed, in the format “21 May, 1999”] |  |
| Source | [Robert F. Heile] [<company>] [40 Sylvan Road] | Voice: [ 781-466-2057 ] Fax: [ 781-466-2575] E-mail: [ bheile@bbn.com ] |
| Re: | [If this is a proposed revision, cite the original document.] [If this is a response to a Call for Contributions, cite the name and date of the Call for Contributions to which this document responds, as well as the relevant item number in the Call for Contributions.] [Note: Contributions that are not responsive to this section of the template, and contributions which do not address the topic under which they are submitted, may be refused or consigned to the “General Contributions” area.] |  |
| Abstract | [Description of document contents.] |  |
| Purpose | [Description of what the author wants P802.15 to do with the information in the document.] |  |
| Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. |  |
| Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15. |  |

Output:  Standard based on Bluetooth specification ver 1.1 including IEEE input.

Plan to deal with versions 1.x as supplements to the base standard.

Assumption is that ver1.1 will be fairly stable for L2CAP and below.

- WG Ballot-completed July 3, 2000

- Comment Resolution- July Meeting

- Submit comments to Bluetooth SIG for incorporation into ver 1.1-July 21.

- SIG establishes Task Force to review and validate SDLs-July 24

- Discuss/resolve comments back from SIG on LB3 at Sept Meeting, Sept 18-22

- SIG/IEEE complete SDL review/validation/debug by Sept 22, 2000

- Clean room preparation of recirculation draft incorporating results of comment resolution and draft of 1.1.  Begin Sept 22, 2000, complete October 10, 2000.

- WG recirculation -15 days-  Start on October 12,complete on October 27, 2000

- Comment Resolution on recirculation at November Meeting, Nov 6-10

- WG recirculation - Start December 1 complete December 15

- Complete Draft at January 2001 Meeting, Jan 15-19 -- submit to ExCom for Letter Ballot to Release to Sponsor Ballot

- Sponsor Ballot complete by March 9

- SB Comment Resolutions at March 2001 Meeting, Mar 12-16

- Seek Conditional Approval from Excom at the March Meeting to Release Draft to NesCom on May 4, 2001.

- Sponsor Ballot recirculation:  Start on March 26, conclude on April 10, 2001.

- Comment Resolution complete on April 20, 2001

- SB recirculation if needed: start on April 23, complete on May 7.

- Will result in SAB action at June 25 meeting

Key Dates and Dependencies:

- Need to have comments incorporated into ver1.1 prior to release by Bluetooth SIG

- Need to have SDL issues resolved by Sept 22, 2000.

- Need to have contract agreement between SIG and IEEE dealing with rights to ver 1.x complete by October 1, 2000.

- Need Clean room copy of ver 1.1 by Sept 22, 2000

- Need to be able to publicly release draft by October 12, 2000

- Need to join sponsor ballot pool by Nov 1, 2000

- Will need Letter Ballot approval from the SEC to release draft to Sponsor Ballot by January 22

- Need to complete Sponsor Ballot prior to March Meeting in order to secure conditional approval to release to Nescom on May 4, 2001

Missing these dates, especially those between now and start of the recirculation ballot on October 12, 2000, will result in a slip for the release of a standard from June 25, 2001 to Sept 12, 2001.

Glossary

| SAB | Standards Activities Board |
| --- | --- |
| Recirculation | Confirmation of changes made as a result of balloting |
| Letter Ballot | Vote of the membership on a Draft Standard |
| Nescom | New Standards Executive Committee of the IEEE Standards Association (IEEE-SA) |
| ExCom | IEEE 802 Executive Committee |
| Sponsor Ballot | Public ballot sponsored by the IEEE Standards Association. A Draft approved by this process becomes an official IEEE Standard. |