## Slide 1
Slide <number>
<footer>
<date/time>
Project: IEEE 802.15 Working Group for Wireless Personal Area Networks (WPANs)
Submission Title: [Task Group 1 Report]
Date Submitted: [8May00]
Source: [Ian Gifford] Company [M/A-COM, Inc.]
Address [1011 Pawtucket Boulevard Lowell, MA USA 01853-3295]
Voice:[+1 978 442 4650], FAX: [+1 978 442 5442], E-Mail:[giffordi@ieee.org]
Re: [-00/095r0, etc.]
Abstract: [TG1 chair report to WG.]
Purpose: [TG1 chair report to WG to update them from the last session (#5) to the current session (#6) on all the work items.]
Notice: This document has been prepared to assist the IEEE 802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release: The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by 802.15.

## Slide 2: IEEE 802.15 Working Group for Wireless Personal Area Networks
TG1 Report #1
May 2000 Seattle, WA USA

## Slide 3: Contents
TG1 Summary
Overview of Seattle
  Objectives
  Submissions
  Session Graphic
Tentative TG1 Needs for Jul00 Plenary
TG1 Draft Sources – Baseline
TG1 Draft Sources - Revision
Next Steps/TG1 Roadmap
TG1 Drafting History
Next Steps

## Slide 4: TG1 Summary
Letter Ballot #2 passed! 34/1/2; out of 43 voting members, there were 37 responses (22 required for a valid vote). Detail: 4 yes with comment , 30 yes w/o comment, 1 no, and 2 abstains.
LB2 yielded 20 Reply Comments to be resolved against –99/173r5a
LB2 Reply Comment Resolution 6Mar00
Apply edits –99/173r5a, et. al. to Draft
LB(3) 19May00 to 22Jun00
Draft ready for Sponsor Ballot post Jul00

## Slide 5: Seattle - Objectives
1. Provide An Update on TG1
2. Planning for Draft Standard, BSIG Approval
3. Planning for Letter Ballot (#3), Empowerment Motions
4. Planning For Sponsor Ballot
5. Initiate/release "INVITATION-TO-BALLOT" to the LAN/MAN 802.15 Pool
6. Identify JUL00 Objectives & Graphic/Timeslots

## Slide 6: Seattle - Submissions
Note: Contributions in red are in process and will be released during session #6 or just after. They will be posted to Jul00 Web Directory

## Slide 7: TG1 May00 Session #6 Graphic
Notes: Legend:
WG = Working Group
AC = Advisory Core (of the WG)
TG1 = Task Group 1 WPAN or Bluetooth Derivation
TG2 = Task Group 2 WPAN to WLAN Coexistence
TG3 = Task Group WPAN-HR (High Rate) SG
MC = Marketing Committee
Joint = Joint Meeting of the 802.11 & 802.15 WGs

## Slide 8: Tentative TG1 Needs for Jul00 Plenary
10-13Jul00 (4 Days)
  25 People
  Power Strips, w/ 1 outlet per chair
  BR = Boardroom
  LCD = PC Screen Projector & Screen (SVGA, 450 lumens)
  FC = Flipchart with markers
TG1 will provide a Jul00 graphic for TG1 on Thursday, 11May00 to the WG

## Slide 9: TG1 Draft Sources – Baseline
D0.6
(v1.0A)
+
IEEE Clauses
D0.7 = D0.6
+(BSIG v1.0B)
+-99/173r5a C1-5
+HCI
+Annex – Timers
+MSCs
+SDLs
D0.8=D0.7
+(BSIG v1.1)
+Informal
comments
+PICS
SDLs
4Nov99
8May00
Letter Ballot #1
Letter Ballot #2
Letter Ballot #3
?
v1.1
10Jul00
23May00

## Slide 10: TG1 Draft Sources - Revision
D0.7.0
(v1.0B)
+HCI
+Annex
+Timers
+MSCs
+etc.
D0.8
(v1.1)
C1-11
Annex
+etc.
*8May00
Letter Ballot #3
40 Day LB
?
v1.1
~12Jul00
*17Apr00
D0.7.1
(v1.0B)
+-99/173r6
C1-11
Annex
+SDLs
+PICS
*12May00
*Note: Date released by Editor-in-Chief
D0.7.2
(v1.0B)
+-99/173r6
C1-11
Annex
+Informal
comments
*~5Jul00
Available one (1) week before ballot starts.
~20Aug00

## Slide 11: Timeline - Summary
8-12May00 Seattle, WA USA
  Make P802.15.1/D0.7.1 available to WG for informal comments
  Apply edits to create P802.15.1/D0.7.2, available later in May00
  Before Jul00 Plenary we will receive a revised Bluetooth Foundation Specification v1.0C or v1.1; this will then be the basis for P802.15.1/D0.8
  One week before Jul00 Plenary we will post P802.15.1/D0.8
10-14Jul00 LaJolla, CA USA
  Start Electronic Letter Ballot of P802.15.1/D0.8 (40 Day LB could start on 12Jul00 and end on 20Aug00)
  Before Sep00 Interim conduct LB Comment Resolution of P802.15.1/D0.8 if resolved
  Before Sep00 Interim start 10 day recirculation LB of P802.15.1/D0.8
18-22Sep00 Scottsdale, AZ USA
  Finalize P802.15.1/D1.0 for Sponsor Ballot
27Oct00 Deadline For RevCom Draft Submission
6-10Nov00 Tampa, FL USA
Jan01 ?
9Feb01 Deadline For RevCom Draft Submission
12-16Mar01 Hilton Head, SC USA

## Slide 12: Timeline - Detail
Note: Backward scheduling from RevCom Deadlines
indicates we will miss 27Oct00 and slip to 9Feb01
…IEEE 802.15.1-2001 Std.
Note: Critical date for receipt of BSIG
Specification v1.1 revision
Source: IEEE802_15_1-editorial-plan-r5.mpp

## Slide 13: TG1 Drafting History
Draft 0.0 - Tom Siep 100%
Draft 0.1 - Tom Siep 100%
Draft 0.2 - Tom Siep 100%
Draft 0.3 - Tom Siep 100%
  283 Pages
Draft 0.4 - Tom Siep 100%
Draft 0.5 - BT-IEEE Editorial Working Group
  331 Pages
  1 Chief Editor/6 Technical Editors
  6 Bluetooth Promoter Company Reviewers w/ internal help
  ~300 Comments
Draft 0.6 - BT-IEEE Editorial Working Group
  308 Pages
  1013 Comments
Draft 0.7 – Tom Siep 100%
  617 Pages
Draft 0.7.1 - IEEE 802.15 Task Group 1 Technical Editors
  Xxx Pages
  1 Chief Editor/11 Technical Editors