## Cover
February 2001 |  | IEEE P802.15.3-01/122r5
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG3 PHY Issues List
Date Submitted | [May 16, 2001]
Source | [James P. K. Gilb] | Voice: [(858)-217-2201]
| [Mobilian] | Fax: [ (858)-217-2301 ]
| [11031 Via Frontera, Suite C] | E-mail: [jgilb@mobilian.com ]
[ San Diego, CA 92129 ]
Re:
Abstract | [List of issues and their resolution for the PHY layer of the 802.15.3 draft standard ]
Purpose | [Track issues and resolution]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Issues List
This is a summary of the issues in the PHY layer and the status of their resolution. Reference document is 01011r0P802-15_TG3-minutes-from-Monterey.doc
Legend
Issue is resolved
Assigned to someone, resolution in progress
Not assigned
Number | Description | Commenter | Assigned to | Status | Disposition | Resolved | Assigned | Other
1 | Should destination and source addresses be in the PLCP header? | P. Kinney | J. Gilb | Resolved | SA and DA are in the MAC header, reference document00000D02P802-15-3 | 1 | 0 | 0
2 | CCA definition? | J. Gilb | J. Gilb | Assigned | This is required for the CAP, PHY needs to define | 0 | 1 | 0
3 | Is RSSI needed, what is the definition? | J. Gilb | J. Gilb and J. Karaoguz | Assigned | Rename Link Quality Indicator (LQI), include RSSI (802.11 DS definition) and mean square error (to be defined) | 0 | 1 | 0
4 | Jamming margin? | J. Gilb | S. Ling | Assigned | New suggested values, reference document IEEE802.15-01/216r0 | 0 | 1 | 0
5 | Intermodulation requirements | J. Gilb | J. Gilb | Resolved | Not specified in the standard, reference document IEEE802.15-01/072r2 | 1 | 0 | 0
6 | Rx sensitivity (number and definition)? | J. Gilb | J. Karaoguz | Resolved | Numbers found in draft v02, reference documents IEEE802.15-01/072r2, IEEE802.15-01/027r1, IEEE802.15-01/011r0 | 1 | 0 | 0
7 | TX Power | J. Gilb | J. Gilb | Resolved | No lower limit, upper limit is determined by appropriate regulatory body ala 802.11b, 18.4.7.1 | 1 | 0 | 0
8 | TX PSD | J. Gilb | S. Ling | Resolved | Reference document IEEE802.15-01/069r3 | 1 | 0 | 0
9 | Modulation accuracy? | J. Gilb | W. Music | Resolved | Measurement method and numbers adopted, reference document IEEE802.15-01/090r2 | 1 | 0 | 0
10 | Error rate criterion? | J. Gilb | J. Gilb | Resolved | Reference documents IEEE802.15-01/027r1, IEEE802.15-01/011r0 | 1 | 0 | 0
11 | Header coding? | J. Karaoguz | J. Karaoguz | Assigned | 2 options left, BPSK and repeating the entire header twice. | 0 | 1 | 0
12 | PHY PIB? | R. Roberts | R. Roberts | Resolved | First proposals accepted, reference document 00000d03P802-15-3, other problems tracked separately | 1 | 0 | 0
13 | What is the need for protection on signal and service fields? | R. Roberts | J. Gilb | Resolved | Signal and service fields are part of the header and FEC'ed | 1 | 0 | 0
14 | Should the symbol clock be synchronized with carrier clock? | S. Ling | S. Ling | Assigned | Initial description of idea is in IEEE802.15-01/147r0. Need proposed definition. | 0 | 1 | 0
15 | Are the PLCP and MAC headers separate? | M. Nafie | J. Gilb, R. Gubbi | Resolved | The PLCP and MAC headers are generated separately but FEC encoded and error checked together | 1 | 0 | 0
16 | How to resolve rate negotiation changes? | J. Karaoguz | J. Gilb | Resolved | Transferred to MAC issues list on March 6, 2001 | 1 | 0 | 0
17 | Link quality assessment technique? | J. Karaoguz | J. Karaoguz | Resolved | Now issue 3 above. | 1 | 0 | 0
18 | Channelization? | J. Gilb | S. Ling | Resolved | Documents IEEE802.15-01/069r2 and IEEE802.15-01/072r2 | 1 | 0 | 0
19 | Out of band performance? | J. Gilb | J. Gilb | Resolved | Not specified in the standard, reference document IEEE802.15-01/072r2 | 1 | 0 | 0
20 | Service field (do we need it)? | R. Roberts | R. Roberts | Assigned | It might be used, need to get a potential definition | 0 | 1 | 0
21 | TxRx and RxTx turnaround time. | P. Kinney | J. Gilb | Resolved | Set at 10 us, reference document 00000D02P802-15-3 | 1 | 0 | 0
22 | Maximum packet length? | J. Gilb | J. Gilb | Resolved | Set at 1514 bytes maximum, pass to MAC committee for comment, MAC committee wants 2048 byte packet, 2048 OK, but note that the MAC should reduce packet size if PER goes to high. | 1 | 0 | 0
23 | Slot for sending: what are problems with allowing peer to peer selecting data rate? | J. Barr | A. Heberling, R. Gubbi, P. Kinney | Resolved | Transferred to MAC issues list on March 6, 2001 | 1 | 0 | 0
24 | Adaptive channel assignments? | M. Nafie | M. Nafie | Resolved | The current draft, 00000d04P802-15-3, provides this capability, closed per email from Mohammed. | 1 | 0 | 0
25 | Channel hop time? | J. Gilb | J. Gilb | Resolved | Change to channel switch time 224 us, reference document 00000D03P802-15-3 | 1 | 0 | 0
26 | Need minimum packet size? | B. Shvodian | B. Shvodian | Resolved | None required, minimum is FCS | 1 | 0 | 0
27 | Padding required in coding? | B. Shvodian | J. Karaoguz | Resolved | 2 symbol tail only, can have any number of bits but must pad to symbol boundry, use all zeros, (5,4,3,2), reference document 00000D02P802-15-3 | 1 | 0 | 0
28 | Whitener? | P. Kinney | J. Karaoguz | Assigned | Polynomial is proposed, awaiting text | 0 | 1 | 0
29 | Coexistence with other wireless devices in support of PAR? | J. Barr | J. Gilb | Assigned | Ongoing issue with draft development. | 0 | 1 | 0
30 | Temperature range for compliance | J. Gilb | J. Allen | Resolved | Adopted 0-40 C, need to add to draft standard | 1 | 0 | 0
31 | PLME-RESET.request: What are the defaults | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
32 | PLME-TESTMODE.request: Missing DATA_TYPE parameter. | R. Roberts | R. Roberts | Resolved | Add it to parameter list, should go out in either v0.3 or v0.4 | 1 | 0 | 0
33 | PLME-TESTMODE.request: What is the depth of loopback, similar to 15.1? | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
34 | PLME Power Management: What is the PHY management policy, no PLME primitives defined | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
35 | PhyPib_RegDomainsSupported: How do we enumerate these? | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
36 | PhyPib_MaxDataRate: Delete? Appears unnecessary | R. Roberts | J. Gilb | Resolved | Unnecessary, deleted since there is only one base rate | 1 | 0 | 0
37 | PhyPib_MinDataRate: Delete? Appears unnecessary | R. Roberts | J. Gilb | Resolved | Unnecessary, deleted since there is only one base rate | 1 | 0 | 0
38 | PhyPib_DataRateStepSize: Not appropriate for data rates that are not equally spaced. | R. Roberts | J. Gilb | Resolved | Replace with PhyPib_DataRateVector … index into vector that returns a list of data rates. | 1 | 0 | 0
39 | PhyPib_CurrentDataRate: Should this be reported instead in MAC PIB? Can this be reported on a per packet basis? Is this the only point where the SME can set/read the data rate? | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
40 | PhyPib_CurrentPowerLevel: Can this be done on a per packet basis by the SME? | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
41 | PhyPib RX RSSI Group: Revisit policy on using the RSSI in the CAP. | A. Heberling | A. Heberling | Assigned |  | 0 | 1 | 0
42 | PhyPib_CCAModesSupported: How many modes will 15.3 have? | R. Roberts | J. Gilb | Resolved | Currently there will only be one defined, will be put in document 00000d05P802-15-3 | 1 | 0 | 0
43 | Ranging Support Group: Ranging is in the evaluation document but there is nothing in the PHY PIB that reflects this … is this an issue? | R. Roberts | R. Roberts | Resolved | Ranging group has been added, reference document 00000d04P802-15-3 | 1 | 0 | 0
44 | PHY-TXSTART.request … TXVECTOR: Should the TXVECTOR pass the DA (destination address) and the SA (source address). | B. Shvodian | B. Shvodian | Resolved | It turns out there is no need to pass the MAC header via the TXVECTOR, hardware design team feels confident that the CRC can be calculated and inserted real-time. | 1 | 0 | 0
45 | PHY-RXSTART.request … RXVECTOR: Should the RXVECTOR pass the DA (destination address) and the SA (source address). | B. Shvodian | B. Shvodian | Resolved | It turns out there is no need to pass the MAC header via the RXVECTOR, hardware design team feels confident that the CRC can be calculated and inserted real-time. | 1 | 0 | 0
46 | PHY-CCARESET.xxxxxx: Is this needed? | R. Roberts | J. Gilb | Assigned |  | 0 | 1 | 0
47 | PHY-CCA.indication: Need to work out policy for this usage. | A. Heberling | A. Heberling | Assigned |  | 0 | 1 | 0
48 | PHY "nap" commond (PHY-RXNAP.xxxxx): How does the RX go to sleep if the incoming packet is not for this station? | B. Shvodian | J. Gilb | Assigned |  | 0 | 1 | 0
49 | Should we support a lower speed mode (e.g. BPSK at 11 Mb/s) for 3 dB SNR improvement? | J. Allen, J Karaoguz | J. Gilb | Assigned |  | 0 | 1 | 0
50 | PHY "nap" commond (PHY-RXNAP.xxxxx): How does the RX go to sleep if the incoming packet is not for this station? | B. Shvodian | J. Gilb | Assigned |  | 0 | 1 | 0
51 | PHY "nap" commond (PHY-RXNAP.xxxxx): How does the RX go to sleep if the incoming packet is not for this station? | B. Shvodian | J. Gilb | Assigned |  | 0 | 1 | 0
[5 empty] | Totals | 30 | 21 | 0