## Cover
February 2001 |  | IEEE P802.15.3-01/122r0
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG3 PHY Issues List
Date Submitted | [November 2, 2000]
Source | [James P. K. Gilb] | Voice: [(858)-217-2201]
| [Mobilian] | Fax: [ (858)-217-2301 ]
| [11031 Via Frontera, Suite C] | E-mail: [jgilb@mobilian.com ]
[ San Diego, CA 92129 ]
Re:
Abstract | [List of issues and their resolution for the PHY layer of the 802.15.3 draft standard ]
Purpose | [Track issues and resolution]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Issues List
This is a summary of the issues in the PHY layer and the status of their resolution. Reference document is 01011r0P802-15_TG3-minutes-from-Monterey.doc
Legend
Issue is resolved
Assigned to someone, resolution in progress
Not assigned
Number | Description | Commenter | Assigned to | Status | Disposition
1 | Should destination and source addresses be in the PLCP header? | P. Kinney | J. Gilb | Assigned | SA and DA are in the MAC header, reference document00000D02P802-15-3
2 | CCA definition? | J. Gilb |  |  | This is required for the CAP, PHY needs to define
3 | Is RSSI needed, what is the definition? | J. Gilb |  |  | MAC committee needs to clarify the requirements for the RSSI so the PHY committee can define this, if necessary.
4 | Jamming margin? | J. Gilb | J. Gilb
5 | Intermodulation requirements | J. Gilb | J. Gilb | Resolved | Not specified in the standard, reference document IEEE802.15-01/072r2
6 | Rx sensitivity (number and definition)? | J. Gilb | J. Karaoguz | Resolved | Numbers found in draft v02, reference documents IEEE802.15-01/072r2, IEEE802.15-01/027r1, IEEE802.15-01/011r0
7 | TX Power | J. Gilb | J. Gilb | Resolved | No lower limit, upper limit is determined by appropriate regulatory body ala 802.11b, 18.4.7.1
8 | TX PSD | J. Gilb | S. Ling | Resolved | Reference document IEEE802.15-01/069r3
9 | Modulation accuracy? | J. Gilb | W. Music | Proposal pending | Measurement method proposed, numbers to be presented, reference document IEEE802.15-01/090r0
10 | Error rate criterion? | J. Gilb | J. Gilb | Resolved | Reference documents IEEE802.15-01/027r1, IEEE802.15-01/011r0
11 | Header coding? | J. Karaoguz | J. Karaoguz | Assigned
12 | MIB? | R. Roberts | R. Roberts | Assigned
13 | What is the need for protection on signal and service fields? | R. Roberts | J. Gilb | Resolved | Signal and service fields are part of the header and FEC'ed
14 | Should the symbol clock be synchronized with carrier clock? | S. Ling | S. Ling | Assigned
15 | Are the PLCP and MAC headers separate? | M. Nafie | J. Gilb, R. Gubbi | Resolved | The PLCP and MAC headers are generated separately but FEC encoded and error checked together
16 | How to resolve rate negotiation changes? | J. Karaoguz | J. Gilb | Pending | Transferred to MAC issues list on March 6, 2001
17 | Link quality assessment technique? | J. Karaoguz | J. Karaoguz | Assigned
18 | Channelization? | J. Gilb | S. Ling | Resolved | Documents IEEE802.15-01/069r2 and IEEE802.15-01/072r2
19 | Out of band performance? | J. Gilb | J. Gilb | Assigned | Not specified in the standard, reference document IEEE802.15-01/072r2
20 | Service field (do we need it)? | R. Roberts | R. Roberts | Assigned
21 | TxRx and RxTx turnaround time. | P. Kinney | J. Gilb | Resolved | Set at 10 us, reference document 00000D02P802-15-3
22 | Maximum packet length? | J. Gilb | J. Gilb | Proposal pending | Set at 1514 bytes maximum, pass to MAC committee for comment
23 | Slot for sending: what are problems with allowing peer to peer selecting data rate? | J. Barr | A. Heberling, R. Gubbi, P. Kinney | Assigned | Transferred to MAC issues list on March 6, 2001
24 | Adaptive channel assignments? | M. Nafie
25 | Channel hop time? | J. Gilb | J. Gilb | Proposal pending | 224 us
26 | Need minimum packet size? | B. Schvodian | J. Karaoguz | Assigned | 10 symbols for all modulations, 8 bytes
27 | Padding required in coding? | B. Schvodian | J. Karaoguz | Proposal pending | 2 symbol tail only, can have any number of bits but must pad to symbol boundry, use all zeros, (5,4,3,2), reference document 00000D02P802-15-3
28 | Whitener? | P. Kinney | T. Schmidl | Assigned
29 | Coexistence with other wireless devices in support of PAR? | J. Barr | J. Gilb | Assigned
30 | Temperature range for compliance | J. Gilb | J. Allen | Assigned | Will benchmark against consumer devices.