## IEEE-Cover
September 2001 |  | IEEE P802.15.4-01/479r0
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | P802-15 TG4 Open Issues List
Date Submitted | [September 7th, 2001]
Source | [José A. Gutierrez] | Voice: [(414)-449-6525]
| Eaton Corp. | Fax: [ ]
| [4201 North 27th Street] | E-mail: [josegutierrez@eaton.com ]
[ Milwaukee, WI 53216 ]
Re: | 00000d10xP802-15-4_Draft-Standard.pdf
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG4 clauses specified in 00000d10xP802-15-4_Draft-Standard.pdf. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## OpenIssuesList
Legend
Rows Color Code |  |  | Issue Status |  | Resolution Status |  | Type of Comment | Comments
Issue Closed |  |  | X - received |  | O -Open |  | E - Editorial | Do not make changes in this file. Send your comments/Issues to JoseGutierrez@eaton.com
Issue Open |  |  | D - Dispatched |  | W - Written |  | T - Technical
|  |  | A - Accepted |  | C - Closed
|  |  | R - Rejected |  | A - unsatisfied
Z - Withdrawn
Issue Nr. | Commenter | Draft Version Nr. | Clause number (e.g., 8.10.2) | Page number | Line number | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Issue Status (X,D,A,R) | Resolution Status O,W,C,U,Z | Date Entered | Date Completed | Asignee
1 | Jose | 6 | 7.1.1.1.1 | 54 | 47 & 51 | T | MAC | In Table 29, no explanation of "MACAddress" has been made |  | X | O | 2001-09-07 |  | Phil
2 | Jose | 6 | 7.1 1 1 1 | 55 | 5 | T | MAC | In Table 29 (and others like table 32), theparameter type is integer less or equal to 127. Why? If the field is going to occupy 8 bits anyway why don't we use less than 255? |  | R | C | 2001-09-07 | 2001-10-09 | Phil
3 | Jose | 6 | 7.1.1.2.1 | 55 | 43 | E | MAC | We need to define somewhere a table with all of the valid ranges for the MAC enumeration types. Note: Almost done. LLC table needs to be added |  | A | C | 2001-09-07 | 2001-10-19 | Phil
4 | Jose | 6 | 7.1.1.4.1 | 57 | 5 & 6 | T | MAC | It is not clear to me why a Handshake needs to send data. I understand that we are planning to send to signaling bits, but the semantics expressed here suggest data bytes. | See issue 40. Changes on actual handshake definition. | D | C | 2001-09-07 | 2001-10-09 | Phil
5 | Jose | 6 | 7.1.1.6.1 | 58 | 28 | T | MAC | Same than issue #4 but in this clause | See comment on issue 4 | D | C | 2001-09-07 | 2001-10-09 | Phil
6 | Jose | 6 | 7.1.2.2.1 | 60 | 25 | E | MAC | Need to create table with valid ranges for the enumeration type "Status" (set of error codes) | See issue 39. | D | C | 2001-09-07 | 2001-10-09 | Phil
7 | Jose | 6 | 7.1.2.3 | 60 | 44 | T | MAC | This paragraph is talking about "star" networks, should be generalized | According to Monique we do not need this message indication for the cluster tree | A | C | 2001-09-07 | 2001-10-09 | Monique
8 | Jose | 6 | 7.1.2.5.1 | 61 | 17 | T | MAC | I think this primitive should have a parameter "state" of type enumeration and a valid range: {ON, OFF} This way this primitive enables and disables the receiver Pat will check if this functionallity should be in the standard Ian will check the need to it |  | A | C | 2001-09-07 | 2001-10-09 | Pat/Ian
9 | Jose | 6 | 7.1.2.6.3 | 61 | 49 | T | MAC | I think we need to add a sequence diagram somewhere with an overview of the network creation (both start & mesh) | We will add an inforative section on chapter 5. See issue 42 | A | C | 2001-09-07 | 9_oct | Marco Monique Phil
10 | Jose | 6 | 7.1.2.10 | 63 | 40 | T | MAC | Same than issue #7 but in this clause |  | C | O | 2001-09-07 | 2001-10-11 | Monique
11 | Jose | 6 | 7.1.2.10.3 | 64 | 3 | T | MAC | Same than issue #7 but in this clause |  | C | O | 2001-09-07 | 2001-10-11 | Monique
12 | Jose | 6 | 7.2.1 | 65 | Tables 42 & 43 | T | MAC | Instead of saying "variable length", can we say "8*n where 0<n<xx"? This implies that we are using integer multiples of bytes! |  | A | C | 2001-09-07 | 2001-10-09 | Team
13 | Jose | 6 | 7.2.1.2 | 66 | 41 | T | MAC | This paragraph states "16 to 176 bits", but in Table 43 says "24 to 176" bits. Please check |  | A | C | 2001-09-07 | 2001-10-09 | Phil
14 | Jose | 6 | 7.2.2.2 | 70 | 40 | T | MAC | Zone needs to be defined somewhere before this point |  | A | C | 2001-09-07 | 2001-11-06 | Phil
15 | Jose | 6 | 7.2.2.3.1 | 71 | Table 55 | E | MAC | I have a doubt here: Addres type is only 4 bits long and we are representing it with a 8 bit hex representation. I am not really sure if we should make a change, or write in the last row: 0X16 |  | A | C | 2001-09-07 | 2001-10-05 | Monique
16 | Jose | 6 | 8 | 81 | 3 | E | LLC | This section needs a little introduction |  | A | C | 2001-09-07 | 2001-10-11 | Monique
17 | Jose | 6 | 8.2.1 | 88 | Table 68 | T | LLC | Where is the length of the LPDU? | This is already included in the MPDU | A | C | 2001-09-07 | 2001-10-09 | Phil
18 | Jose | 6 | 7.2.1.2 | 66 | Table 46 | T | MAC | Please check this table throughly, I found several inconsistencies |  | A | C | 2001-09-07 |  | Monique
18.1 | Monique | 6 | 7.2.1.2 | 66 | Table 46 | T | MAC | The terms "uplink" and "downlink" shoul not be used to refer to a cluster tree network. Need names for the description |  | A | C | 2001-09-07 |  | Monique
18.2 | Monique | 6 | 7.2.1.2 | 66 | Table 46 | T | MAC | The following cluster tree frame control fields should me marked as "illegal": 0101, 1101, 0011,1011 (all cluster tree messages will have both source and destination addresses) |  | A | C | 2001-09-07 |  | Monique
19 | Monique | 6 | 7.2.1.2 | 67 | 23-34 | T | MAC | Does the 16 bit network identifier include 4 bits for the macSuperFrameOrder (a.k.a. collapse value)? | Collapse value is not included in 16bit identifyer and needs to be defined in more detail. | A | C | 2001-09-07 |  | Phil/Ed/Monique
19.1 | Monique | 6 | 7.2.1.2 | 67 | 23-34 | T | MAC | Assuming the answer to the comment above is yes, this seems redundant. I suggest rewriting this section as follows: a) A network identifier. This address shall be 16 bits in length and specifies the identity of the network. The network identifier is the only address specified in the beacon frame of a star network. b) A source/destination address… c) A cluster identifier. This address shall be 8 bits in length and specifies the cluster identifier of a cluster tree network. | Paragraph deleted and a improve definition of cluster tree address was added to 7.2.1.2.3 | A | C | 2001-09-07 | 2001-11-06 | Phil/Ed/Monique
20 | Phil | 6 | N/A | ix | all | E | TOC | Should we have more depth in the contents list? | IEEE style requires at least 2 levels. Deeper levels can be used as editing team thinks is appropriate, but our sibbling standars are using 3. We will use 3 | A | C | 2001-09-04 | 2001-10-09 | Jose
21 | Phil | 6 | N/A | N/A | N/A | E | Misc. | We do not have any concept of a "conventions" section - is this implied by the IEEE drafting conventions? | We can have a "conventions" subsection within a given chapter is we think is appropriate. We should not have a separate chapter for general conventions. | X | O | 2001-09-04 | 2001-09-12 | Marco
22 | Phil | 6 | 7.5.2.x | 78 | 34 | T | MAC | This section needs updating as it has to include stimulation from the NWK layer. The Beacon_Req packet is an out-of-date concept | Closed since issue 42 addresses this issue | A | C | 2001-09-04 | 2001-10-22 | Phil
23 | Said/Phil | 6 | 6 | N/A | N/A | T | PHY | Rx-Tx and Tx-Rx turnaround time issue Robert is taking care of this |  | A | C | 2001-09-07 | 0ct-29 | Robert Poor
24 | Farron | 6 | N/A | N/A | N/A | E/T | PHY | Issues on regulatory text in the standard [jose] Farron after our discussion in the teleconference (9/10/01), we'll discretize the issue in its multiple parts |  | A | C | 2001-08-29 | 2001-11-06 | Farron/Said
25 | Jose | 5 | 6.5.3.6 | N/A | N/A | T | PHY | "Receiver RSSI sounds complex, this can be integrated with previous section 6.5.3.5. If an implementer wants to add this capability is OK. Basically we just need CCA capability (yes or not) |  | A | C | 2001-08-26 | 2001-09-18 | Paul
26 | Jose/Paul | 6 | 6.4 | N/A | N/A | T | PHY | We are planning to make the following addition to the draft: "...a compliant device may support either (1) Base Rate and Low Rate or (2) only Low Rate. In other words, a base rate device must also support low rate, but a low rate device doesn't need to support base rate. This would result in two types of devices." This has implications in the MAC/LLC that needs to be addressed. | Simulations from Paul and Said has shown no much value in E/N due to low rate (only 0.5 dB). See issue 46 (waiting for resolution on the soingle/dual modes) | A | C | 2001-09-17 | 2001-10-29 | Said
27 | Paul | 6 | N/A | N/A | N/A | T | PHY | Compliance definition for each band (2.4 GHz, 868 MHz, 910 MHz). Need information from STS. | The statement we are looking is that a compliant device needs to support … | A | C | 2001-09-17 | 2001-10-10
28 | Robert Poor | 7 | 6.1.2.7 | ---- | ---- | T | PHY | Section 6.1.2.7 PLME-SET.confirm Suggest we make the interface for PMLE-SET.confirm identical to those of PMLE-GET.confirm (include the PIBAttribute along with status and PIBAttributeValue) so return values can be interpreted asynchronously. | Leave it as is. Added issue #50 | A | C | 2001-09-20 | 2001-10-10
29 | Robert Poor | 7 | 6.2.1 6.2.1.3 6.2.1.4 | ---- | ---- | T | PHY | Section 6.2.1: Frame Format. (And sections 6.2.1.3, 6.2.1.4) Propose that the PHY payload of handshake header conform to the [Frame Length / PSDU] format of a beacon or data frame PPDU in orderto simplify decoding in the MAC layer: ¦[ synch header ]¦[phy header ]¦[phy payload]¦ ¦[preamble]¦[sof delim]¦[frame length]¦[psdu ]¦ ¦ ?bits ¦ 8 bits ¦ 0000010 ¦ <2 bytes> ¦ In other words, a handshake frame has a frame length of two and a constant two-byte payload. | Phil changed that already. | A | C | 2001-09-20 | 2001-10-10
30 | Robert Poor | 7 | 6.3 | ---- | ---- | T | PHY | Section 6.3: PHY Managed Objects Need clarification for each PIB entry if it 'must' be implemented or 'may' be implemented, and a reminder of what happens for a request of a PIB entry that doesn't exist. | Question answered/superseded with other modifications on the draft | A | C | 2001-09-20 | 2001-10-09 | Team
31 | Pat Kinney | 7 | 6.5.1.5 | ---- | ---- | T | PHY | Pat is requesting to remove this section | See minutes from meetings on the week of Sept 17th Team Agree | A | C | 2001-08-21 | 2001-09-21 | Said
32 | Pat Kinney | 10 | 6.6.2.6 | ---- | ---- | T | PHY | Pat is suggesting to kill this section. Paul would like to discuss the issue | kill section 6.6.2.6 | A | C | 2001-09-21 | 2001-10-10 | Jose
33 | Pat Kinney | 10 | 6.6.2.7 | ---- | ---- | T | PHY | Pat - Pat asked why the transmit power-up and power-down ramp is so tightly controlled ()? / Paul stated that this was just the initialdraft and that this needs fine-tuning. / Said stated that the intent was to reduce transients in other bands. Said would like to discuss this with his team and bring it up again at next week call. | Delete section unless Said objects. | A | C | 2001-09-21 | 2001-11-06 | Said
34 | Said | 10 | 6.6.2.9 | ---- | ---- | T | PHY | 2nd paragraph. Is there any command at the MAC level able to handle this functionality? - Said asked if there is any MAC level functionality to handle the step-wise power reduction as specified in the 2nd paragraph of section 6.5.2.9? |  | R | C | 2001-09-21 |  | Jose/Monique
35 | Monique | 8 | 7.5.2.3 | ---- | ---- | T | MAC | Steps 4-5 of the network beacon detection procedure mention the MLME_SYNC.confirm primitive that was previously removed from the draft. This section must be rewritten to reflect the current procedure. | Addressed by Phil in his e-mail from Oct-9th | A | C | 2001-10-03 | 2001-10-09 | Phil
36 | Monique | 8 | 7.5.2.4 | ---- | ---- | T | MAC | The last line of the section reads "If allocation is impossible due to the slot capacity, the MAC sublayer should return the slot identifier zero and the maximum slot length currently available." What is meant by "the slot identifier zero"? | Slot identifier will part of some primitives that have to be identified. New issue 51. | A | C | 2001-10-03 | 2001-10-10 | Phil
37 | Monique | 8 | --- | ---- | ---- | T | MAC | Should a PIB "Identifier" column be added to the MAC PIB table 55? | Add column to all PIB tables for the identifyer | A | C | 2001-10-05 | 2001-10-10 | Jose
38 | Monique | 8 | 7.5.1.1 | ---- | ---- | E | MAC | 7.5.1.1 states "One time unit is defined in MAC PIB." Reference to table not clear. Ask Phil is He is refering to: macBaseChunkDuration If so is one chunk too coarse for CSMA backoff? | Yes, the one time unit is refering to the macBaseChunkDuration. Change text saying: "One time is defined as macBaseChunkDuration" also added item 52. | A | O | 2001-10-05 | 2001-10-10 | Jose
39 | Team | 10 | --- | ---- | ---- | T | MAC | Create a table explaining details on the enumeration data at the end of PHY, MAC, LLC sections |  | A | C | 2001-10-09 | 2001-10-11 | Phil
40 | Phil | 10 | --- | ---- | ---- | T | MAC | Handshake mechanism is taking too long. Phil would like to optimize it pushing it right down to the MAC (no LLC involvement on the recipient or higher layers processing) |  | A | C | 2001-10-09 | 2001-10-22 | Phil
41 | Robert Poor | 10 | --- | ---- | ---- | T | MAC | Comments about "star" word usage and beacons. Robert will check the MAC section. Robert will talk to Phil about this topic to clarify other scenarios |  | X | O | 2001-10-09 |  | Robert Poor
42 | Phil | 10 | --- | ---- | ---- | T | GENERAL | We need to put together an informative section explaining network formation | Add as informative section in Annes or put is as clause in MAC | A | C | 2001-10-09 | 2001-11-05 | Marco
43 | Jose | 10 | --- | ---- | ---- | T | ---- | Do we want to used a standarized IEEE-CRC polinomial? | We decided to use the 802.11 CRC-16 CCITT polinomial | A | C | 2001-10-09 | 2001-10-15 | Jose
43.1 | Monique | 10 | 7.2, 7.2.1.4 | ---- | ---- | T | MAC | This section states that the polinomial we already have is an IEEE CRC!. We need to verify this. | From the source that Phil looked at it stated that the CRC is based on an internaltional standard but he does not know, which one. Closed. Using 802.11 CRC-16 | A | C | 2001-10-09 | 2001-10-15 | Jose
44 | Phil | 10 | 5.4.4.1 | ---- | ---- | T | GENERAL | We need to update 5.4.4.1 through …3 with the new CRC info and addressing. | Already updated and send to Jose | A | C | 2001-10-09 | 2001-10-22 | Phil
45 | Monique | 10 | 7 | ---- | ---- | T | MAC | Improve explanation on SuperFrameOrder. There is no clear explanation in the draft |  | A | C | 2001-10-09 | 2001-11-06 | Phil
46 | Team | 10 | 6 | ---- | ---- | T | PHY | Discussion about the value of using a low-rate mode at all. Recent simulations from Paul/Said has shown a E/N difference of only 0.5 dB between the 2 modes. Waiting info from Dean Gaston & Analisys from Paul/Said to compare original ideas on sensitivity and the new modulation proposal. | Waiting for reaction from Hans, Pat2 | A | C | 2001-10-09 | 2001-10-29 | Paul/Said
47 | Jose | 10 | 6.6.2.9 | ---- | ---- | T | PHY | The PIB entries referenced in the last line of the 2nd paragraph is not in the PIB table 16 (yet). Need a names for them: phyMaxTransmitPower (readonly) and phyCurrentTransmitPower (rw value) |  | A | C | 2001-10-09 | 2001-10-22 | Phil
48 | Robert/Monique | 10 | --- | ---- | ---- | T | MAC/LLC | Get rid of the name "Chunk" | Rename "slot" to "logical channel" and "chunk" to "slot". | A | O | 2001-10-09 | 2001-10-11 | Jose/Marco
49 | Hans | 10 | 6.4 | ---- | ---- | T | PHY | Channel assigment equation should be monotonic with frequency |  | A | C | 2001-10-09 | 2001-11-06 | Paul/Said
50 | Phil | 10 | --- | ---- | ---- | T | GENERAL | Add description of the abstract concept of the primitives in general section (5) (just take section 2.1 from 802.2) |  | A | C | 2001-10-10 |  | Marco
51 | Phil | 10 | 7.5.2 | ---- | ---- | T | MAC | Work on slot identifier section in general. "Time slots" |  | X | C | 2001-10-10 | 2001-11-11 | Phil
52 | Robert | 10 | --- | ---- | ---- | T | MAC | Review collision avoidance timing issues. |  | X | O | 2001-10-10 |  | Robert Poor
53 | Phil | 10 | 7.5.1.1 | 76 | 5 | E | MAC | Bullet 3 says maxmax but is should say macMax |  | A | C | 2001-10-10 | 2001-10-10 | Jose
54 | Phil | 10 | --- | --- | --- | E | GENERAL | Copy section 7.2.1.9 from TG3 spec on CRC and add it as informative section to TG4. |  | X | O | 2001-10-10 |  | Marco
55 | Team | 10 | 6 | ---- | ---- | T | PHY | There is a open discussion about a standard power mode and a higher power mode (optional). Need to share this info with Said/Paul, and the rest of the team |  | A | C | 2001-10-10 | 2001-10-29 | Said/Paul
56 | Team | 10 | 6 | ---- | ---- | T | PHY | In the ADHOC meeting in Cha-Oct-2001 the team discussed about the possibility of removing the low-rate mode in the 2.4GHz band. This means changing "base-rate" to "rate" on the PHY section. |  | A | C | 2001-10-11 | 2001-10-29 | Said/Paul
56.1 | Team | 10 | 6 | ---- | ---- | T | PHY | Related to the above issue in the 868/915 band, the team is thinking in the possibility of having only a "low-rate" mode instead of high-low rates. Hans will provide data to the team so we can make a decision |  | A | C | 2001-10-11 | 2001-10-29 | Hans
57 | Team | 10 | 6 | ---- | ---- | T | PHY | The team decided to contemplate a "standard power" mode and a "extended mode". Discussions about minimum sensitivity and dynamic range numbers are needed. For now is proposed the following numbers: blocking power: -25dBm, sensitivity: -85dBm, Output power 0 dBm. Note: The link margin difference between the high-density low-power mode and the high-power/low-density mode is 30dBms! |  | A | C | 2001-10-11 | 2001-10-29 | Said/Paul
58 | Ed | 10 | 7 | ---- | ---- | T | MAC | Should we add a flag in the MAC header to allow data packets to be processed in the MAC layer? | None | R | C | 2001-10-11 | 2001-11-06 | Monique
59 | Monique | 10 | 7 | ---- | ---- | T | MAC | Need a way to time-stamp incoming data for mediation device use. |  | A | C | 2001-10-11 | 2001-11-06 | Monique
60 | Monique | 10 | 7 | ---- | ---- | T | MAC | For cluster-tree it may be necessary to have a backoff mechanism different than random backoff (maintaining the CSMA structure) |  | C | A | 2001-10-11 | 2001-11-06 | Monique
61 | Phil | 10 | 7 | ---- | ---- | T | MAC | Some explanation needs to be added concerning the actual byte format of the different addresses used. (MAC) |  | X | O | 2001-10-12 |  | Phil/Monique
62 | Phil | 10 | 6 | ---- | ---- | T | PHY | Update the specification for Said's synchronisation burst. |  | A | C | 2001-10-12 | 2001-10-22 | Said
63 | Pat Kinney | 12 | 6 | ---- | ---- | T | PHY | Do we need to perform CCA on the acknowledge packets? Ack packet are special, this change may reduce complexity. Check Japanese regulations, there may be an issue |  | A | C | 2001-10-25 | 2001-11-06 | Robert Poor/Phil
64 | Pat Kinney | 12 | 5,7,8 | ---- | ---- | T | MAC/LLC | The packet duration for a 868/915MHz frame is very long in comparison with the a frame at 250kbps. Can we limit the length of the frame payload to a lower number in order to decrease the packet duration? Pat suggest a payload of 32 bytes, Jose wants >=8. |  | X | O | 2001-10-26 |  | Phil/Said
65 | Phil/Robert | 12 | 7 | ---- | ---- | T | MAC | Backoff should be applied before the CCA test |  | X | O | 2001-10-29 |  | Phil/Robert
66 | Robert | 12 | 6 | ---- | ---- | T | PHY | Devise an effective mechanism for low jitter time-stamps or become convinced if not necessary |  | X | O | 2001-10-30 |  | Robert/Said
67 | Pat Gonia | 12 | 8.4.1.2 | 109 | 19 | E | LLC | Define behavior for when handshake is not required. |  | X | O | 2001-11-07 |  | Phil
68 | Robert Poor | 12 | 6 | ---- | ---- | T | PHY | Issue about using was the 8 bits instead of 3 bits for encoding the RSSI value. See more explanation in the minutes from Nov 5th |  | X | O | 2001-11-05 |  | Phil/Said/Paul
69 | Pat Kinney | 12 |  | 10 |  | T | MAC | We have specified 64 bit MAC addresses, what are the implications of this? |  |  | O | 2001-11-12 |  | Pat
70 | Pat Kinney | 12 |  | 10 |  | E | MAC | Don’t use an acronym for network layer |  |  | O | 2001-11-12 |  | Jose
71 | Pat Kinney | 12 |  | 12 |  | T | MAC | Why limit network joining to a passive mode? Active is faster. |  |  | O | 2001-11-12 |  | Phil
72 | Pat Kinney | 12 |  | 48 |  | T | PHY | Spec for 2.4 GHz only has one data rate |  |  | O | 2001-11-12 |  | Said
73 | Pat Kinney | 12 |  | 51 |  | T | PHY | Does Japan really have a 900 MHz band? |  |  | O | 2001-11-12 |  | Hans
74 | Pat Kinney | 12 |  | 51 |  | T | PHY | Why 500 uS turnaround? 250 uS is not a severe penalty |  |  | O | 2001-11-12 |  | Robert
75 | Pat Kinney | 12 |  | 54 |  | T | PHY | CCA shouldn’t be based solely upon RSSI in an ISM band |  |  | O | 2001-11-12 |  | Said
76 | Pat Kinney | 12 |  | 56 |  | T | MAC | MSDU length is less than 101 bytes? Why not allow it to rise if using short addresses? |  |  | O | 2001-11-12 |  | Phil
77 | Pat Kinney | 12 |  |  |  | T | MAC | What if a network chooses a network ID of another network within listening distance? Standardized resolution ? |  |  | O | 2001-11-13 |  | Phil
78 | Jose | 12 |  |  |  | E |  | Rewrite the system and MAC sections definitions of packet, frame; eliminate super frame references. Place definitions of frame and packet from 802 glossary into 802.15.4’s glossary |  |  | C | 2001-11-13 |  | Jose