## IEEE-Cover
November 2000 |  | IEEE P802.15.3-00/354r1
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | P802-15_TG3 MAC Open Issues List
Date Submitted | [April, 2001]
Source | [Bill Shvodian] | Voice: [(703)-269-3022]
| XtremeSpectrum, Inc. | Fax: [ ]
| [8133 Leesburg Pike] | E-mail: [adheberling@ieee.org ]
[ Vienna, VA 22182 ]
Re: | 00000d02P802-15-3_Draft-Standard.pdf
Abstract
Purpose | [This document provides a home for all comments, open issues and suggested resolutions concerning the TG3 MAC clauses specified in 00000d02P802-15-3_Draft-Standard.pdf. In addition, this document will keep a running status of the disposition of the suggested resolutions.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## OI-List-Srtd
| Color Codes |  |  |  |  | W | Changes approved
|  | C | Closed |  |  | A | Assigned
|  | P | Proposal pending |  |  | O | Open, not assigned
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Issue Status X,D,Q,A,R | Resolution Status O,W,C,U,Z | Date Entered | Date Completed | Asignee
3 | ADH | 2 | 5 | 12 | 30 | E | OvrView | The overview clause is incomplete. | Please complete. |  | D | A |  |  | Gilb | Due 9/17/01
4 | ADH | 2 | 5.2 | 11 | 30-31 | E | OvrView | This sentence is inaccurate. | This sentence needs to be struck. |  | D | A |  |  | Gilb | Due 9/17/01
5 | ADH | 2 | 5.2.2 | 12 | 4-5 | E | OvrView | This sentence needs to be reworked to emphasize the concept of access portals and minimize the inferred LAN capability. | Please rework sentence to minimize inferred LAN bias. |  | D | A |  |  | Gilb | Due 9/17/01
11 | WMS | 6 | 6.3, 6.7, 6.8 | 15 | 32-42 |  | MLME SAP | It would be nice to have a list of primatives and a short description | Please add the appropriate definitions. | R. Roberts will add an MLME primitives table similar to the one for the PHY-SAP. Also add MAC-SAP and PLME-SAP tables | A | A |  |  | Gilb | Due 9/4/01
13 | RDR | 6 | 6.3.1 |  |  | T | PwrMgt | MLME-Powermanagment.request needs to be made consistent with 15.3 Powermanagement Policy |  | Apply changes in document 01/262r3 | D | A |  |  | Gilb | Due 9/4/01
26 | RDR | 6 | 6.3.4 | 21 | 14-54 | T | Auth | Authentication Process needs to be defined. Currently, TBD. | Please Define. | Auth. Policy is being investigated. | X | A |  |  | Rasor
27 | ADH | 6 | 6.3.4.1 | 21 | 18 | T | Auth | Until we define an Authentication Policy there is no point in defining an MLME-Authenticate.request signal and its parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor
28 | ADH | 6 | 6.3.4.2 | 22 | 6 | T | Auth | Until we define an Authentication Policy there is no point in defining an MLME-Authenticate.confirm signal and its parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor
29 | ADH | 6 | 6.3.4.3 | 23 | 1 | T | Auth | Until we define an Authentication Policy there is no point in defining an MLME-Authenticate.indication signal and its parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor
30 | ADH | 6 | 6.3.5 | 23 | 35 | T | Auth | Until we define an Authentication Policy there is no point in defining MLME-DeAuthenticate.xxx signals and their parameters. | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor |  |  | x
31 | RDR | 6 | 6.3.5 | 23 | 35 | T | Auth | De-Authenticate Policy is undefined in 802.15.3 | Please Remove. | Auth. Policy is being investigated. | X | A |  |  | Rasor |  |  | x
36 | MkS | 6 | 7.2 |  |  |  |  | The implementation of almost any second mode of MAC operation will require some additional information in the MAC header. I therefore request 1 byte be reserved so that the possibility of additional MAC functionality is not eliminated from the standard. |  | This item to be discussed during telecons. Mark Schrader will do a submission for Portland to add a MAC mode information element. | X | A |  |  | Schrader | Tabled, proposal due by 9/17/01 | Pending Presentation
41 | ADH | 6 | 7.5 | 49 | 30 | T | Auth | When we define an Authentication Policy, we will need to add an Authentication frame type to this table. |  | Auth. Policy is being investigated. | X | A |  |  | Rasor
52 | WMS | 6 | 6.3.10, et. al |  |  |  | StrmMgt | How is a packet from the upper layers mapped to a Stream index? | Look at how 802.11e is doing it. May need convergence layer. Maybe use "routing information from MA Unidata.request |  | D | A |  |  | Heberling | Tabled | Pending results of further study.
69 | ADH | 6 | 7.5.2 | 56 | 49 | T | Assoc | Authentication Process needs to be defined before we have a valid association policy. | Please Define. | Auth. Policy is being investigated. | X | A |  |  | Rasor
70 | ADH | 6 | 7.5.2 | 56 | 25 | t | Auth | Isn't this better suited for inclusion in an authentication frame type? |  | Auth. Policy is being investigated. | X | A |  |  | Rasor
72 | WMS | 6 | 7.5.2 | 81 |  |  | Assoc. | What is the purpose of the Association Timeout period? | Describe how it is used or remove | ATP is the heartbeat of the piconet | D | A |  |  | Akahane | Proposal due 9/17/01 | Dependent upon PwrSave resolution
75 | WMS | 6 | 7.5.3 | 82 |  |  | Assoc. | What is the purpose of the Association Timeout period? | Describe how it is used or remove | ATP is the heartbeat of the piconet | D | A |  |  | Akahane | Proposal due 9/17/01
76 | WMS | 6 | 7.5.2, 7.5.3 |  |  |  | Assoc. | Remove Challenge Test from Association Request and Response. |  | Auth. Policy is being investigated. | X | A |  |  | Rasor
90 | ADH | 6 | 7.3.4 | 59 | 43 | t | StrmMgt | Too many TBDs for the Stream Data frame format. | Please provide specific ranges or values regarding Encryption field and max length of the data field. | Raju to provide feedback in 292r1 | D | A |  |  | Gubbi | ? | Dependent upon Security/Privacy recommendations
101 | ADH | 6 | 7.4.7 | 64 | 1 | T | Auth | Security Parms are TBD. | Please identify security parms. | Auth. And Privacy Policy is being investigated. | X | A |  |  | Rasor
102 | ADH | 6 | 7.4.8 | 64 | 5 | T | PwrMgt | Power Save Parms are TBD. | Please define TBD PwrSve Parms | Make changes indicated in 01/262r3 | D | A |  |  | Bain | Table
122 | WMS | 6 | 7.5.5.2 | 68 | 39+ |  | Cmd Types | What is the purpose of the Channel Time Grant command if it has the same information as the Beacon? | Need to describe when and why the Channel Time Grant is used. | The frame is defined, but we need to add information about when is should be used. | D | A |  |  | Gubbi | ? | Defined in D05 Clause 7.5.1.2, Clause 8.2.3.2
143 | ADH | 6 | 8.2.8 | 83 | 9-18 | T | CoordHndOff | Does this mean that all the devices originally associated with the first AC now have to reassociate themselve with the new coordinator? Or does the new coordinator use the same PNID as the original coordinator? If it does reuse the PNID does this represent a security problem? |  | Auth. And Privacy Policies are being investigated. | X | A |  |  | Rasor
168 | Ol | 6 | 6.3.10, 6.3.11 | 92 | 27-28 | T | StrmMgt | These stream management signals need to be defined in the MAC management clause: MLME-Stream-Connect.request, MLME-Stream-connect.indication, MLME-Stream-Disconnect.request, MLME-Stream-Disconnect.indication | Need to define the parameters, "when generated", and "effect of receipt" for each of the stream management entities identified to the left. Add to section 6. |  | D | A |  |  | Roberts | Pending resolution from Heberling |  | x
169 | EdNote | 2 | 8.4 | 92 | 31 | t | CAP | When does stream negotiation occur? During CAP or CFP? | I recommend during MTS(Management Time Slots) | Devices can transmit data frames during the CAP if it has no appropriate GTS slots. See table 46 section 8.13 in 293r1 | A | A |  |  | Shvodian | Proposal due from B. Shvodian, due 09/17/01 | See R.Gubbi | x
170 | ADH | 6 | 8.5.3 | 94 | 48-49 | T | Priorities | I disagree with the statement that the priority algorithms are beyond the scope of this standard. One of the problems BT type devices are running into is the problem of interoperability. If two or more devices have different rules for priority of data transmissions, I would expect a failure to communicate. | 802.1D describes the use of priorities, we will add one bit for for Isochronous/asynchronous. See 293r1 |  |  | A |  |  | Heberling |  | Amendment Approval
177 | WMS | 293r1 | 8.11 | 99 | 11-24 |  | PwrMgt | Should we support remote wake-up? |  |  | D | A |  |  | Bain | Tabled, proposal due by 9/17/01
218 | WMS | 6 | 7.4.10 |  |  | T | CTA | It may be worth while to add a bit to each CTA, and for the entire set of CTAs to indicate that a change in the CTAs has taken place. |  | Not really necessary if static GTS slots are allocated. | D | A |  |  | Shvodian | Table |  | x
221 | WMS | 6 | 8.3.3 | 92 |  | T | CFP | Need to desciribe how SIFS fits in to GTS assignments: Is it at the end of a GTS, the start, or are the GTS slots assigned so that the end of one and the start of the next are spaced by a SIFS? | Bill will add text into 01259 to discuss Guard Time | Need a proposal. Possibly need to define the accuracy requiremejnts of the MAC clock. | D | A |  |  | Shvodian | Table | Pending results of further study. | x
222 | Vienna | 4 |  |  |  | T | CAP | Can data be sent during the CAP? Don't want stations to have to listen to the CAP. | Bill will add text into 01259 Need to address all sections of Draft |  | D | A |  |  | Shvodian | Proposal due from B. Shvodian, due 09/17/01 | Separate item proposal
223 | Vienna | 6 | 5 |  |  | E | Overview | Clause 5 needs updating to match clause 7 and 8 |  |  | D | A |  |  | Gilb | Assigned
224 | Vienna | 4 | 8.8 | 99 |  | T | Repeater | What are the permitted ACK policies for for the repeater function? How do they function? | Needs clarification to handle point to point and/or end to end ACK policies. Raju thinks delayed ACK is needed. |  | D | A |  |  | Gubbi | Proposal due from R. Gubbi, 09/17/01 | Approval of text in col. K
229 | Vienna | 4 | 7.4.3 | 72 |  | T | Capability | Need to clarify the use of the Des-mode bit. |  |  | D | A |  |  | Gubbi | Proposal due from R. Gubbi, 09/17/01
230 | Vienna | 4 | 8.1.3 |  |  | T | CoordSel | Need to clarify the use of the Des-mode bit in the coordinator selection process. |  |  | D | A |  |  | Shvodian | Proposal due from R. Gubbi, 09/17/01
233 | Vienna | 6 | 8.2.8 | 88 |  | T | CoordSel | Need to add text describing how the PNC can review the capabilities of associating Devs and decide to perform PNC handover if the new device is more capable. Need to address Security Implications. |  | Already finished except for the xref to the security procedure which is TBD until authentication is defined. | D | A |  |  | Akahane | Table | Pending results of further study.
234 | Vienna | 6 | 8.2.8 | 88 |  | T | CoordSel | Need to add text describing how the PNC can review the capabilities of associating Devs and decide to perform PNC handover if the new device is more capable. Members may need to vote because the most capable PNC may not be the best geographically located. Sony's proposal 01304r0 addresses Piconet initialization, but an existing piconet also needs to be addressed. |  |  | D | A |  |  | Akahane | Table, proposal due 9/17/01 | Pending results of further study.
235 | Vienna | 6 | 7.5.2 and 8.TBD |  |  | T | Heartbeat | Should we add an unsolicited heartbeat function? An unsolicited Heartbeat function may be beneficial for power save devices as described in Sony document 01306r0. |  |  | D | A |  |  | Akahane | Table, proposal due 9/17/01 | Pending results of further study.
236 | Vienna | 6 | 8.3.3 and others |  |  | T | CFP | Do we want to add static GTS slots for robustness and/or ease of implementation? |  |  | D | A |  |  | Shvodian | Table, proposal due 9/17/01
146 | ADH | 2 | 8.2.1 | 84 | 23 | t | IFS | How long is a slot? Is this slot the same as a GTS? Or is it the same as a backoff slot? | Please clarify. | MAC committee amendment recommends aBackoffSlot see doc 01/355. | D | W |  |  | Gilb | Due 09/17/01 | J. Gilb editing D05
205 | WMS | 4 | 7.3.4 | 64 | 12-32 |  | CoordSel | Modify Coordinator Selection frame Body to reflect new coordinator criteria | In figure 6 remove total external connections, active external connections, total system memory, available system memory, Maximum PHY transmit power, Maximum PHY rate. Add Battery/AC power, designated coordinator bit, MAX GTS slots, Repeater memory, Max Repeater Rate. Review with Raju | WMS to provide additional detail in doc: 01/259r0 | A | W |  |  | Gilb | Due 09/17/01 | Amendment approval
207 | WMS | 4 | 6 |  |  |  | CoordSel | Update PIB and SAPs to reflect new coordinator comparison criteria | WMS to supply changes to PIB and SAPs to reflect the new coordinator comparison criterion. Review with Raju | WMS to provide additional detail in doc: 01/259r0 | A | W |  |  | Shvodian | Due 09/17/01 | Amendment approval
[9 empty] | Issue Status | Resolution Status
[9 empty] | X - received | O -Open
[9 empty] | D - Dispatched | W - Written
[9 empty] | A - Accepted | C - Closed
|  |  |  | Color Code |  |  |  |  | R - Rejected | A - unsatisfied
|  |  |  | Closed | [5 empty] | Z - Withdrawn
Changes approved
Proposal pending
Assigned
Open, not assigned

## Closed issues
| Color Codes |  |  |  | Changes approved
|  | Proposal pending |  |  | Assigned
|  | Proposal pending |  |  | Open, not assigned
Issue Number | Commenter's Initials | Draft Version Number | Clause number e.g., 8.10.2 | Page number e.g., 1-1130, etc. | Line number e.g., 1-54 | Type of comments (E/e/T/t) | Class of Problem | Comment/Rationale (Issue and reasoning behind it.) | Recommended change (What change(s) it would take to make this clause acceptable.) | Disposition/Rebuttal (Do not write here during ballot phase; this is for comment resolution phase.) | Issue Status X,D,Q,A,R | Resolution Status O,W,C,U,Z | Date Entered | Date Completed | Asignee | Amendment Doc #
2 | WMS |  | 4. | 8 |  |  | Acronyms | IFS, RIFS, SIFS, TIFS, MIFS are missing from the acronym clause. | Please provide accronyms | Please add acronyms to acronym list and definition to definitions list. | A | C |  |  | Gilb | Done in D06
6 | ADH | 2 | 6.1 | 13 | 16-17 | t | SNMP | What is meant by standard management protocols? Does this statement imply support for SNMP? | Please Clarify | R. Roberts will remove reference to SNMP | A | C |  |  | Roberts | Done in D06
12 | ADH | 2 | 6.3.1.1 | 16 | 19-24 | t | Synch | Are we going to support a DTIM mechanism? | Please provide justification. |  | D | C |  |  | Bain | Withdrawn
22 | MCO | 6 | 6.3.3.1 | 19 | 46 | T | Synch | Should Operation Rate Set be added back in? | Resolve this. | Will be in draft 5. Voted on in 222r1 in Portland, now in capability information field. Need to add data rate to bit mapping in PHY section. | A | C |  |  | Gilb | Due 9/17/01
39 | WMS | 2 | 7.1.3.1.3 | 49 | 1 | E | Stream-Data | Need to define Stream-Data | Change "Stream-Data" to "Data (Stream or non-Stream)" everywhere in the draft. | Do Global change. Maybe find a better name. | A | C |  |  | Gubbi | Done in D05
48 | ADH | 2 | 7.1.3.2 | 50 | 36 | T | PNID | How is the PNID generated? Is it based on the coordinator's MAC address? Is it some PRN generated 2 octet value? | Please Clarify. | Add following to 8.1.2 :"Seed for the randomization process is required to choose the PNID shall be 48bit device ID of the PNC." | D | C |  |  | Gubbi | Pending | Amendment approval if col. K text
51 | ADH | 2 | 7.1.3.4 | 51 | 7 | t | StrmMgt | What are considered non-stream data? Command packets? ACKs? What about short message packets? Is an asynchronous bulk transfer of data considered a non stream data type? Or is it a type of streaming data? | Add the following text to the last paragraph in section 7.2.1.4 in 292r1: The use of a stream connection for asynchronous data is up to the device. | Add the following text to the last paragraph in section 7.2.1.4 in 292r1: The use of a stream connection for asynchronous or isochronous data is up to the device. | D | C |  |  | Gubbi | Done in D05
68 | WMS | 2 | 7.2.3.x | 55 | 19 | t | CoordSel |  | Recommend changing the Coordinator Selection Fields to more appropriate criteria. | WMS to provide exact details in doc: 01/259r0. Reviewed at Vienna ad hoc | A | C |  |  | Shvodian | Done in D06
71 | WMS | 2 | 7.2.4 | 56 | 16-19 |  | Assoc | Why is Network ID field null in Association Requests from un-associated STAs? | Recommend using in the MAC header the PNID of the PicoNet the device is trying to join. | Replace current text in L16-19 with proposed text | A | C |  |  | Gubbi | Done in D07
73 | WMS | 2 | 7.2.4 | 56 | 25-35 |  | Assoc. | What is the purpose of the Allocated Station Address field in the Association Request command? If it is always FE, does it serve any purpose? | If the purpose is to keep the request and response the same, it makes sense. | Need Feedback from Raju as to why. | D | C |  |  | Gubbi | Withdraw
80 | ADH | 2 | 7.2.5 | 57 | 44 | E | Assoc | Reason codes should be defined here first |  |  |  | C |  |  | Gubbi | Done in D05
86 | WMS | 2 | 7.2.6 | 58 | 8-14 |  | Assoc. | Why is station device ID needed in Disassociation Request? Is this a directed Frame or broadcast? |  | Need Feedback from Raju as to why. |  | C |  |  | Gubbi | Withdrawn
95 | WMS | 2 | 7.3.2 | 61 | 39-40 |  | Superframe Duration | 0-524280 uS is too large a range for superframe duration | Change minimum beacon interval to .5 Kus and maximum to 100 Kus | Adopt this proposal. Add to MAC committee resolution. | A | C |  |  | Gubbi | Done in D05
103 | ADH | 2 | 7.3.8 | 64 | 9 | T | TxPwr | Transmit Pwr Cntl Parms are TBD. | Please define. |  |  | C |  |  |  | Done in D07
111 | WMS | 2 | 7.3.9 | 64 | 14+ |  | CTA | Is there any way to limit the number of CTAs that are assigned to a terminal? Would this be a negotiated parameter? | Please Clarify | WMS to provide exact details in doc: 01/259r0. Reviewed at Vienna ad hoc | A | C |  |  | Gubbi | Pending | Approval of Amendments
120 | WMS | 2 | 7.4.1.1 | 68 | 11-22 | T | Latency | What does "Latency" Mean in a channel time request? Is it latency from the time the request is made until the slot is assigned? The time bewtween slots? | Define "latency" | The name was changed from latency to duration between slots | D | C |  |  | Gubbi | Done in D05 | 7.5.1.1
121 | WMS | 2 | 7.4.1.1 | 68 | 1-9 | T | Latency | Why does a station make requests for different levels of "latency?" Doesn't isochronous demand low latency and asynchronous is latency insensitve? | Remove Latency from the channel time request since it is implied by isochronous vs. asynchronous. | Get feedback from Raju. Latency removed from channel time requests in 01292r1, but Channel time request is different than wat was discussed in Orlando. | D | C |  |  | Gubbi | Done in D05 | 7.5..1.1
127 | WMS | 2 | 7.4.4 | 71 | 9-35 |  | Cmd Types | Is the Remain Quiet Command needed, or can the coordiator accomplish this by setting CTAs to zero? | Remove Remain Quiet Command | Remove Remain Quiet Command | A | C |  |  |  | Withdraw
128 | ADH | 2 | 7.4.6 | 72 | 46 | t | CoordHndOff | What is the preferred range for this duration? | Please Clarify. | Variables to be added: minHandOvrTO(.25sec) and maxHandOvrTO(1.0sec).Also change HandOvr timer resolution to 1Kus . | D | C |  |  | Gubbi | Done in D06 | Amendment Approval
129 | ADH | 2 | 7.4.7.1 | 73 | 20-21 | E | DevInfo | Line 21 is unclear in its meaning | Please clarify. | In Figure 33, Clause 7.5.10.1/d05 remove Requester Dev. ID field | D | C |  |  | Gubbi | Done in D06 | AmendmentApproval
133 | ADH | 2 | 8.1.3 | 81 | 36 | t | CoordSel | Why doesn't the losing AC just keep itsTx quiet? Why does it need to send a signal indicating that it has removed itself? |  | Delete directed frames since they are not possible and have losing ACs remain quiet. | D | C |  |  | Heberling | Done in D07 | Pending results of further study.
134 | ADH | 2 | 8.1.3 | 81 | 39 | t | CoordSel | If all the ACs were comparing parameters then the one with the highest ranking would already know that it is the new coordinator for the piconet. | Simplify Coordinator Selection Process. | Delete directed frames since they are not possible and have losing ACs remain quiet. | D | C |  |  | Heberling | Done in D07 | Pending results of further study.
141 | ADH | 2 | 8.1.6 | 82 | 45 | E | Auth | The Authentication Clause should come before the Association Clause. Why allow Association if you haven't been Authenticated to some level of Security? | Move Auth. Clause 8.1.6 to 8.1.4 and slip 8.1.4 to 8.15 and 8.1.5 to 8.1.6. I42 | Auth. And Privacy Policy is being investigated. | X | C
142 | ADH | 2 | 8.1.7 | 82 | 49-54 | T | DevReg | This scenario works fine for a non secure public implemetation. However, there needs to be a more secure scenario provided as well. | The policies of device registration and association are dependent upon the Security policies defined for a piconet environment. | Auth. And Privacy Policies are being investigated. | X | C
166 | WMS | 2 | 8.3.1 | 91 | 18+ | T | TSF | If we get rid of TSF and replace it with beacon number and offset time, a reference point will be required. The current reference point is the TSF field. | Replace the TSF and substitute a beacon count and offset time. | WMS to provide a detailed superframe timing diagram in 01259. Also WMS to synch with S. Ling and J.Gilb in the phy committee. | D | C |  |  | Shvodian | Done in D06
167 | Ol | 2 | 8.3.2 | 91 | 42-43 | t | TSF | Clock accuracy (or MAC clock accuraccy): +/- % accuracy or x ppm? | Please specify |  | D | C |  |  | Shvodian | Done in D05 | 8.3.2
176 | ADH | 2 | 8.10 | 98 | 38 | T | PwrMgt | Power Mgt. needs to be defined. | Please Define. | Make changes indicated in 0/1262r3 | D | C |  |  | Bain | Done in D07
178 | ADH | 2 | 8.11 | 98 | 42 | T | TxPwr | Transmit Power Cntrl needs to be defined. | Please define. |  | D | C |  |  | Roberts, Bain, Gubbi | Table
181 | ADH | 2 | 11.4.1 | 115 | 17 | T |  | What is the PHY header format? | Please define |  | D | C |  |  | Gilb | Done in D05 | Defined in Clause 11.4.4
182 | MCO | ? | 8.7 |  |  |  | Assoc | How does the coordinator determine if a station is still present in the network? | Any device can send any directed command frame to any other device to see if it is present. Add to peer discovery clause. | Add to peer discovery clause | A | C |  |  | Gubbi | Done in D05
186 | WMS | 4 | 7.2.1.1.3 | 59 | 10 | t | Frame Type | Folding commands into frame types requires using 6 bits to the Frame Type Field | Change text to "The frame type field is six bits in length." | Change frame formats to ammendments adopted in 01/298r0 | A | C |  |  | Gubbi | Done in D06
192 | WMS | 4 | 7.5.2 | 77 |  |  | Cmd Types | Probe Information, Channel Status Request, Device information commands should be request/response or request/indication frames | Change to request and response or indication. see doc:01/259r0 for text detail and change to frame format. Raju included Channel Status Request and response, Device Information request and response in 01292r1table 42. Probe information still does not have request and response. | Raju should add Probe information Request and Probe information response. | A | C |  |  | Gubbi | Done in D06
198 | WMS | 4 | 7.5.1.1 | 75 |  |  | Channel Time Request | Need to add destination station address to Channel Time Request. | WMS to supply text to describe new Channel time request message structure. Note Raju changed Channel Time Request to use stream Index in 01292r1. | WMS to provide additional detail in doc: 01/259r0 | A | C |  |  | Gubbi | Done in D05
206 | WMS | 4 | 7.3.4 |  |  | T | CoordSel | Modify Comparison order of fields in the AC announcement frame | WMS to supply text Review with Raju. | WMS to provide additional detail in doc: 01/259r0 | A | C |  |  | Gubbi | Pending | Amendment approval
208 | WMS | 4 | 8.3 |  |  |  | TSF |  | WMS needs to identify the WMS to supply detailed timing diagram to show the position of time zero in the superframe | WMS to supply details in 01259rx | A | C |  |  | Shvodian | Done in D06
209 | WMS | 4 | 7.4.2 | 72 | 8 |  | TSF | Replace the TSF field with beacon number | Remove 8 byte Time Stamp field and replace with 4 byte Beacon Number field | WMS to supply details in 01259rx | A | C |  |  | Shvodian | Done in D06
210 | WMS | 4 | 7.3.2 | 64 | 17 |  | TSF | Replace the TSF field with beacon number | Change "TSF Element" to "Beacon Number". Add number of bits to 01259 | WMS to supply details in 01259rx | A | C |  |  | Shvodian | Done in D06
211 | WMS | 4 | 8.1.4 | 88 |  |  | Assoc | Broadcast the device information table when a station associates | WMS to supply modified text for section 8.1.4 | WMS to provide detail in doc: 01/259r0 | D | C |  |  | Shvodian | Done in D06, 8.2.9 | Amendment Approval
212 | WMS | 4 | 8.1.5 | 89 |  |  | Disassociation | Broadcast the device inforamtion table when a station disassociates | WMS to supply modified text for section 8.1.5 | WMS to provide detail in doc: 01/259r0 | D | C |  |  | Shvodian | Done in D06 | Amendment Approval
213 | WMS | 4 | 7.4.3 | 72 | 43-48 |  | Capability | Add MAX GTS slots to the capability field. This puts a limit on how many GTS slots can be assigned to a station. This is the combined number of source and destiantion slots for the station | Add 8 bit MAX GTS slot field to the capability field. Change reserved bits to 3 reserved bits. | WMS to provide detail in doc: 01/259r0. | A | C |  |  | Shvodian | Done in D05 | Additional Parms defined in Amendment Doc 355
214 | WMS | 4 | 7.3.3 | 64 | 34-36 | T | Ack | Stream index and sequence control fields are not needed for immediate Acks. | Remove this sentence, and add stream index and sequence control to lines 28 and 29 so that these fields are unused and set to zero. | Remove this sentence, and add stream index and sequence control to lines 28 and 29 so that these fields are unused and set to zero. | A | C |  |  | Gubbi | Done in D05 | 7.3.2
215 | WMS | 4 | 7.5.1.1 | 76 | 9-14 | T | Priorities | Are 3 priorities of asynchronous traffic really needed? | Need to look at 802.1D | These priorities were removed in D06 | D | C |  |  | Heberling | Done in D06 | Amendment Approval
216 | WMS | 4 | 8.4.1 | 94 |  | T | Stream Mgt | Why is the coordinator in the loop for stream negotiation? Stream negotiation does not address channel time requests. | Remove the coordinator from stream negotiation. Have stream index be unique for a SA/DA pair. | Reduce the stream index to 8 bits with the remaining 3 bits reserved. So this results in simpler implementation based on global stream index that is allocated by PNC. An implementation based stream index that is unique for SA/DA pair results in more complex implementation. Add Stream-index to ChnlTimeReq by replacing reserved field in Fig.22, Clause 7.5.1.1; Add Stream-index to ChnlTimeAllocationBlock alog with one reserved byte in figure 20 clause 7.4.9; Remove time slot duration from CTA block in Fig. 20, clause 7.4.9; Add ChnlTimeReq Block to Stream QoS parms in Stream Mgt . Cmnd in figure 42 Clause 7.5.12; Retain StreamID in Stream QoS parms.; Add descriptions for each of the "new" fields. | X | C |  |  |  | Done in D06 | Add text in col K to doc: 355. Approval of Amendments
217 | WMS | 4 | 7.5.1.1 | 76 |  | t | Channel time | A)How long is a channel time request good for? Until the next one? B)What happens if the PNC allocates less channel time than what was allocated? Does it allocate more if it becomes available? |  | A is addressed in Amendment Doc: 355. B)What happens if the PNC allocates less channel time than what was allocated? Does it allocate more if it becomes available? Yes. Add clarification in 8.2.3.2 | X | C |  |  | Gilb | Done in D06 | Approval of Amendments
219 | WMS | 4 | 8.2.3.1 | 92 | 14-15 | T | CAP | Resolution (quantzation) of the random backoff timer needs to be specified. | Bill will provide resolution recommendation in 01259 |  | D | C |  |  | Shvodian | Done in D06, 8.3.2.1 | Amendment Approval
220 | WMS | 4 | 8.1.3 | 87 | 1-54 | E | CoordSel | This section refers to the CS-Frames being transmitted. The action (AC announcement, AC pullout, New Coord. Announcement) should be spelled out for clarity. | Make specifiic references to the action type of the each CS-Frame. | Make specifiic references to the action type of the each CS-Frame. | A | C |  |  | Gubbi | Done in D05 | 8.1.3
225 | Vienna | 4 | 8.1.7 | 89 |  | E | DevReg | Better definition of registration is needed | Add text based on Raju's e-mail of 6/18/01and verify that it fits with the security clause. PNID should always have the PNID that appears in the Beacon. Open registration should be accomplished through a new open registration command (if needed) and not via a null PNID. | Add text based on Raju's e-mail of 6/18/01and verify that it fits with the security clause. PNID should always have the PNID that appears in the Beacon. Open registration should be accomplished through a new open registration command (if needed) and not via a null PNID. | A | C |  |  | Gilb | Done in D07 | Ammendment approval
226 | MKS | 4 |  |  |  | T | Stream Mgt | Look at merging channel time requests and stream management |  |  |  | C |  |  | Gilb | Done | see item 216
227 | Vienna | 4 | 6 | 17 | 19 | T | SME | Remove the top of the SME box to indicate that an undefined interfaceto the SME exists a la 802.11. |  | Remove the top of the SME box to indicate that an undefined interfaceto the SME exists a la 802.11. | A | C |  |  | Roberts | Done in D05
228 | Vienna | 4 | 7.1.2 | 48 | 7 | T | Frame Body | Max Frame body size is inconsistent between section 7.1.2 and section 11.2.7 |  | MAX Frame parameter is Phy dependent parameter that is used in both MAC and PHY clauses. | D | C |  |  | Gubbi/Gilb | Done in D06
231 | Vienna | 4 | 6.5 | 39 |  | T | CoordSel | Need to add the Des-mode bit into the MAC PIB | Add MACPIBPNCDesMode to the MAC PIB. | Add MACPIBPNCDesMode to the MAC PIB. | A | C |  |  | Roberts | Done in D06 | Amendment approval
232 | Vienna | 4 | 7 and 8 |  |  | T | CoordSel | Do a global change of Des-Mode to PNC-Des-Mode in Clause 7 and 8. | Do a global change of Des-Mode to PNC-Des-Mode in Clause 7 and 8. | Do a global change of Des-Mode to PNC-Des-Mode in Clause 7 and 8. | A | C |  |  | Gubbi | Done in D05
237 | Vienna | 4 |  |  |  | T | TxPwr | How is the Tx Power control managed and reported to the SME for each destination (does it need to be in the PIB?) |  | SME doesn't need to know this, the MAC keeps the information internal to itself. | D | C |  |  | Roberts/Bain | Rejected | Pending results of further study.
238 | Vienna | 4 |  |  |  | T | Immediate ACK | How often does a DEV retry Immediate ACK frames? | Retry limit is in stream negotiation. What about non-stream? |  | X | C |  |  |  | Done in D05
239 | Vienna | 01292r1 | 7.5 | 69 | Table 42 | T | Cmd Types | Repeater service Reject and Repeater Service Grant should be Repeater Service Response, Sleep state Permit and Reject should be consolidated to Response. |  | A)Repeater service Reject and Repeater Service Grant should be Repeater Service Response, B)Sleep state Permit and Reject should be consolidated to Response. | A | C |  |  | Gubbi | Done in D05 | A withdrawn, B adopted.
240 | James | 6 | 8.2.7 | 99 |  | T | DevReg | Registration is a higher layer function. | Delete reference to registration in D07, i.e. delete 8.2.7. |  |  | C |  |  | Gilb | Done in D07
[9 empty] | Issue Status | Resolution Status
[9 empty] | X - received | O -Open
[9 empty] | D - Dispatched | W - Written
[9 empty] | A - Accepted | C - Closed
|  |  |  | Color Code |  |  |  |  | R - Rejected | A - unsatisfied
|  |  |  | Closed | [5 empty] | Z - Withdrawn
Changes approved
Proposal pending
Assigned
Open, not assigned