## IEEEcover
October 2002 |  | IEEE P802.15-02/406r5
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG3 LB19 comment drafting status
Date Submitted | [October 2, 2002]
Source | [James P. K. Gilb] | Voice: [(858)-538-3903]
| [Appairent Technologies] | Fax: [(858)-538-3903 ]
| [9921 Carmel Mountain Rd., #247] | E-mail: [gilb@ieee.org ]
[San Diego, CA 92129]
Re: | [00000D10P802.15.3-Draft-Standard]
Abstract | [This spreadsheet tracks the comment drafting status for both the assignments of issues to people as well as tracking when the resolutions are applied to the draft.]
Purpose | [To track the status of comment resolution and the application of the resolutions to the draft.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Commentswritten
|  | Left to go | 390
|  | Total finished | 161
|  | Left to claim | 0 | Enter 'done' when comment applied
CID | Status | Heberling | ADH comments | Gilb | JPKG comments | Singer | AS comments | Sarallo | JS comments | Schrader | MKS comments | Bain | JB comments | Tally | Claimed
1 | AS+ |  |  |  |  | AS+ | [7 empty] | 0 | 0
2 | AS+ |  |  |  |  | AS+ | [7 empty] | 0 | 0
3 | AS+ |  |  |  |  | AS+ | [7 empty] | 0 | 0
4 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
5 | AS+ |  |  |  |  | AS+ | [7 empty] | 0 | 0
6 | Heberling | Heberling | [11 empty] | 0 | 0
7 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
8 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
9 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
10 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
11 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
12 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
13 | Heberling | Heberling | [11 empty] | 0 | 0
14 | Heberling | Heberling | [11 empty] | 0 | 0
15 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
16 | Heberling | Heberling | [11 empty] | 0 | 0
17 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
18 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
19 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
20 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
21 | Heberling | Heberling | [11 empty] | 0 | 0
22 | Heberling | Heberling | [11 empty] | 0 | 0
23 | jcb | [10 empty] | jcb |  | 0 | 0
24 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
25 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
26 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
27 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
28 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
29 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
30 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
31 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
32 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
33 | jcb | [10 empty] | jcb | there may be some holes in the resolution. If nothing else we have a subclause that is rearly empty (8.6.4) - multi-clause | 0 | 0
34 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
35 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
36 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
37 | jcb | [10 empty] | jcb | what is the "table" | 0 | 0
38 | Heberling | Heberling | [11 empty] | 0 | 0
39 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
40 | Heberling | Heberling | [11 empty] | 0 | 0
41 | Heberling | Heberling | [11 empty] | 0 | 0
42 | jcb | [10 empty] | jcb | not clear on the arrow! | 0 | 0
43 | Heberling | Heberling | [11 empty] | 0 | 0
44 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
45 | Heberling | Heberling | [11 empty] | 0 | 0
46 | jcb | [10 empty] | jcb | MSCs need creation | 0 | 0
47 | jcb | [10 empty] | jcb |  | 0 | 0
48 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
49 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
50 | jcb | [10 empty] | jcb | unclear text instructions | 0 | 0
51 | jcb | [10 empty] | jcb | may take some time to interpret | 0 | 0
52 | jcb | [10 empty] | jcb |  | 0 | 0
53 | jcb | [10 empty] | jcb |  | 0 | 0
54 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
55 | jcb | [10 empty] | jcb |  | 0 | 0
56 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
57 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
58 | jcb | [10 empty] | jcb |  | 0 | 0
59 | jcb | [10 empty] | jcb | not resolved - what is push? | 0 | 0
60 | jcb | [10 empty] | jcb | multi-location | 0 | 0
61 | Done | [10 empty] | Done | Withdrawn | 1 | 0
62 | JPKG |  |  | JPKG | PICS | [8 empty] | 0 | 0
63 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
64 | AS+ |  |  |  |  | AS+ | [7 empty] | 0 | 0
65 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
66 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
67 | jcb | [10 empty] | jcb |  | 0 | 0
68 | jcb | [10 empty] | jcb | what is push? | 0 | 0
69 | jcb | [10 empty] | jcb | not yet interpreted | 0 | 0
70 | jcb | [10 empty] | jcb |  | 0 | 0
71 | Heberling | Heberling | [11 empty] | 0 | 0
72 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
73 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
74 | jcb | [10 empty] | jcb | multi-location and not clear where everything goes. | 0 | 0
75 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
76 | JPKG | [12 empty] | 0 | 0
77 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
78 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
79 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
80 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
81 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
82 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
83 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
84 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
85 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
86 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
87 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
88 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
89 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
90 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
91 | AS+?Sarallo |  |  |  |  | AS+? |  | Sarallo | [5 empty] | 0 | 0
92 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
93 | AS+Sarallo |  |  |  |  | AS+ |  | Sarallo | [5 empty] | 0 | 0
94 | Heberling | Heberling | [11 empty] | 0 | 0
95 | Heberling | Heberling | [11 empty] | 0 | 0
96 | Heberling | Heberling | [11 empty] | 0 | 0
97 | Heberling | Heberling | [11 empty] | 0 | 0
98 | AS+? |  |  |  |  | AS+? | [7 empty] | 0 | 0
99 | Heberling | Heberling | [11 empty] | 0 | 0
100 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
101 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
102 | AS+? |  |  |  |  | AS+? | [7 empty] | 0 | 0
103 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
104 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
105 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
106 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
107 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
108 | AS+ |  |  |  |  | AS+ | [7 empty] | 0 | 0
109 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
110 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
111 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
112 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
113 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
114 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
115 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
116 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
117 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
118 | AS |  |  |  |  | AS | Rejected | [6 empty] | 0 | 0
119 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
120 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
121 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
122 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
123 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
124 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
125 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
126 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
127 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
128 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
129 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
130 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
131 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
132 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
133 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
134 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
135 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
136 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
137 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
138 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
139 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
140 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
141 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
142 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
143 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
144 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
145 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
146 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
147 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
148 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
149 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
150 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
151 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
152 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
153 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
154 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
155 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
156 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
157 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
158 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
159 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
160 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
161 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
162 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
163 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
164 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
165 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
166 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
167 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
168 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
169 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
170 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
171 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
172 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
173 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
174 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
175 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
176 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
177 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
178 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
179 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
180 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
181 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
182 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
183 | Heberling | Heberling | [11 empty] | 0 | 0
184 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
185 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
186 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
187 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
188 | Done |  |  | Done | Editorial, changes handled by CID 97 | [8 empty] | 1 | 0
189 | Heberling | Heberling | [11 empty] | 0 | 0
190 | Done |  |  | Done | Editorial, changes handled by CID 97 | [8 empty] | 1 | 0
191 | Heberling | Heberling | [11 empty] | 0 | 0
192 | Heberling | Heberling | [11 empty] | 0 | 0
193 | Heberling | Heberling | [11 empty] | 0 | 0
194 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
195 | Heberling | Heberling | [11 empty] | 0 | 0
196 | Heberling | Heberling | [11 empty] | 0 | 0
197 | Heberling | Heberling | [11 empty] | 0 | 0
198 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
199 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
200 | Heberling | Heberling | [11 empty] | 0 | 0
201 | Heberling | Heberling | [11 empty] | 0 | 0
202 | Heberling | Heberling | [11 empty] | 0 | 0
203 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
204 | Heberling | Heberling | [11 empty] | 0 | 0
205 | Heberling | Heberling | [11 empty] | 0 | 0
206 | Heberling | Heberling | [11 empty] | 0 | 0
207 | Heberling | Heberling | [11 empty] | 0 | 0
208 | Heberling | Heberling | [11 empty] | 0 | 0
209 | Heberling | Heberling | [11 empty] | 0 | 0
210 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
211 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
212 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
213 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
214 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
215 | Heberling | Heberling | [11 empty] | 0 | 0
216 | Heberling | Heberling | [11 empty] | 0 | 0
217 | Heberling | Heberling | [11 empty] | 0 | 0
218 | jcb | [10 empty] | jcb |  | 0 | 0
219 | Heberling | Heberling | [11 empty] | 0 | 0
220 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
221 | Heberling | Heberling | [11 empty] | 0 | 0
222 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
223 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
224 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
225 | Heberling | Heberling | [11 empty] | 0 | 0
226 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
227 | Heberling | Heberling | [11 empty] | 0 | 0
228 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
229 | Heberling | Heberling | [11 empty] | 0 | 0
230 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
231 | Heberling | Heberling | [11 empty] | 0 | 0
232 | jcb | [10 empty] | jcb |  | 0 | 0
233 | Heberling | Heberling | [11 empty] | 0 | 0
234 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
235 | Heberling | Heberling | [11 empty] | 0 | 0
236 | Done |  |  | Done | Editorial, changes handled by CID 221 | [8 empty] | 1 | 0
237 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
238 | jcb | [10 empty] | jcb |  | 0 | 0
239 | Heberling | Heberling | [11 empty] | 0 | 0
240 | Done |  |  | Done | Editorial, changes handled by CID 221 | [8 empty] | 1 | 0
241 | Heberling | Heberling | [11 empty] | 0 | 0
242 | jcb | [10 empty] | jcb |  | 0 | 0
243 | Heberling | Heberling | [11 empty] | 0 | 0
244 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
245 | Heberling | Heberling | [11 empty] | 0 | 0
246 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
247 | Heberling | Heberling | [11 empty] | 0 | 0
248 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
249 | Heberling | Heberling | [11 empty] | 0 | 0
250 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
251 | Done |  |  | Done | Editorial, changes handled by CID 251 | [8 empty] | 1 | 0
252 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
253 | Heberling | Heberling | [11 empty] | 0 | 0
254 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
255 | Heberling | Heberling | [11 empty] | 0 | 0
256 | Heberling | Heberling | [11 empty] | 0 | 0
257 | jcb | [10 empty] | jcb |  | 0 | 0
258 | Heberling | Heberling | [11 empty] | 0 | 0
259 | jcb | [10 empty] | jcb |  | 0 | 0
260 | Heberling | Heberling | [11 empty] | 0 | 0
261 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
262 | Heberling | Heberling | [11 empty] | 0 | 0
263 | jcb | [10 empty] | jcb |  | 0 | 0
264 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
265 | jcb | [10 empty] | jcb |  | 0 | 0
266 | Heberling | Heberling | [11 empty] | 0 | 0
267 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
268 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
269 | jcb | [10 empty] | jcb | multi-clause content and ln 44 not clear | 0 | 0
270 | jcb | [10 empty] | jcb |  | 0 | 0
271 | jcb | [10 empty] | jcb |  | 0 | 0
272 | jcb | [10 empty] | jcb |  | 0 | 0
273 | jcb | [10 empty] | jcb |  | 0 | 0
274 | jcb | [10 empty] | jcb |  | 0 | 0
275 | jcb | [10 empty] | jcb | not totally closed in 392 | 0 | 0
276 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
277 | Done | [10 empty] | Done | Withdrawn, 11 September, 2002 | 1 | 0
278 | jcb | [10 empty] | jcb |  | 0 | 0
279 | jcb | [10 empty] | jcb | not resolved | 0 | 0
280 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
281 | jcb | [10 empty] | jcb |  | 0 | 0
282 | jcb | [10 empty] | jcb |  | 0 | 0
283 | Done | [10 empty] | Done | Rejected | 1 | 0
284 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
285 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
286 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
287 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
288 | jcb | [10 empty] | jcb |  | 0 | 0
289 | jcb | [10 empty] | jcb |  | 0 | 0
290 | jcb | [10 empty] | jcb | for email resolution | 0 | 0
291 | Done | [10 empty] | Done | Rejected | 1 | 0
292 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
293 | jcb | [10 empty] | jcb |  | 0 | 0
294 | jcb | [10 empty] | jcb |  | 0 | 0
295 | Heberling | Heberling | [11 empty] | 0 | 0
296 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
297 | jcb | [10 empty] | jcb | Huh? Isn't this one of the Knut & Bob text subjects? | 0 | 0
298 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
299 | Heberling | Heberling | [11 empty] | 0 | 0
300 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
301 | Heberling | Heberling | [11 empty] | 0 | 0
302 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
303 | jcb | [10 empty] | jcb | conflict with cid494 | 0 | 0
304 | jcb | [10 empty] | jcb |  | 0 | 0
305 | jcb | [10 empty] | jcb |  | 0 | 0
306 | Heberling | Heberling | [11 empty] | 0 | 0
307 | jcb | [10 empty] | jcb |  | 0 | 0
308 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
309 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
310 | jcb | [10 empty] | jcb |  | 0 | 0
311 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
312 | jcb | [10 empty] | jcb |  | 0 | 0
313 | jcb | [10 empty] | jcb |  | 0 | 0
314 | jcb | [10 empty] | jcb |  | 0 | 0
315 | jcb | [10 empty] | jcb |  | 0 | 0
316 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
317 | jcb | [10 empty] | jcb |  | 0 | 0
318 | Heberling | Heberling | [11 empty] | 0 | 0
319 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
320 | jcb | [10 empty] | jcb |  | 0 | 0
321 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
322 | jcb | [10 empty] | jcb |  | 0 | 0
323 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
324 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
325 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
326 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
327 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
328 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
329 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
330 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
331 | Heberling | Heberling | [11 empty] | 0 | 0
332 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
333 | Done |  |  | Done | Editorial, changes handled by CID 86 | [8 empty] | 1 | 0
334 | Done |  |  | Done | Editorial, changes handled by CID 86 | [8 empty] | 1 | 0
335 | Heberling | Heberling | [11 empty] | 0 | 0
336 | Heberling | Heberling | [11 empty] | 0 | 0
337 | jcb | [10 empty] | jcb | multi-clause content | 0 | 0
338 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
339 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
340 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
341 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
342 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
343 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
344 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
345 | Heberling | Heberling | [11 empty] | 0 | 0
346 | Heberling | Heberling | [11 empty] | 0 | 0
347 | Heberling | Heberling | [11 empty] | 0 | 0
348 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
349 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
350 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
351 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
352 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
353 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
354 | jcb | [10 empty] | jcb | not resolved - MTS | 0 | 0
355 | jcb | [10 empty] | jcb | MTS stuff | 0 | 0
356 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
357 | jcb | [10 empty] | jcb |  | 0 | 0
358 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
359 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
360 | Heberling | Heberling | [11 empty] | 0 | 0
361 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
362 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
363 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
364 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
365 | jcb | [10 empty] | jcb | not resolved – PM | 0 | 0
366 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
367 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
368 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
369 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
370 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
371 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
372 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
373 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
374 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
375 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
376 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
377 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
378 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
379 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
380 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
381 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
382 | AS |  |  |  |  | AS | [7 empty] | 0 | 0
383 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
384 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
385 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
386 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
387 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
388 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
389 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
390 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
391 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
392 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
393 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
394 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
395 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
396 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
397 | Heberling | Heberling | [11 empty] | 0 | 0
398 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
399 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
400 | Heberling | Heberling | [11 empty] | 0 | 0
401 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
402 | Heberling | Heberling | [11 empty] | 0 | 0
403 | Heberling | Heberling | [11 empty] | 0 | 0
404 | Heberling | Heberling | [11 empty] | 0 | 0
405 | Heberling | Heberling | [11 empty] | 0 | 0
406 | Heberling | Heberling | [11 empty] | 0 | 0
407 | Heberling | Heberling | [11 empty] | 0 | 0
408 | Heberling | Heberling | [11 empty] | 0 | 0
409 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
410 | Heberling | Heberling | [11 empty] | 0 | 0
411 | Heberling | Heberling | [11 empty] | 0 | 0
412 | Heberling | Heberling | [11 empty] | 0 | 0
413 | Heberling | Heberling | [11 empty] | 0 | 0
414 | Heberling | Heberling | [11 empty] | 0 | 0
415 | Heberling | Heberling | [11 empty] | 0 | 0
416 | Heberling | Heberling | [11 empty] | 0 | 0
417 | Heberling | Heberling | [11 empty] | 0 | 0
418 | Heberling | Heberling | [11 empty] | 0 | 0
419 | Heberling | Heberling | [11 empty] | 0 | 0
420 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
421 | JPKG |  |  | JPKG | Editorial | [8 empty] | 0 | 0
422 | Heberling | Heberling | [11 empty] | 0 | 0
423 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
424 | Heberling | Heberling | [11 empty] | 0 | 0
425 | Heberling | Heberling | [11 empty] | 0 | 0
426 | Heberling | Heberling | [11 empty] | 0 | 0
427 | Heberling | Heberling | [11 empty] | 0 | 0
428 | Heberling | Heberling | [11 empty] | 0 | 0
429 | Heberling | Heberling | [11 empty] | 0 | 0
430 | Heberling | Heberling | [11 empty] | 0 | 0
431 | Heberling | Heberling | [11 empty] | 0 | 0
432 | Heberling | Heberling | [11 empty] | 0 | 0
433 | Heberling | Heberling | [11 empty] | 0 | 0
434 | Heberling | Heberling | [11 empty] | 0 | 0
435 | Heberling | Heberling | [11 empty] | 0 | 0
436 | Heberling | Heberling | [11 empty] | 0 | 0
437 | Heberling | Heberling | [11 empty] | 0 | 0
438 | Heberling | Heberling | [11 empty] | 0 | 0
439 | Heberling | Heberling | [11 empty] | 0 | 0
440 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
441 | Heberling | Heberling | [11 empty] | 0 | 0
442 | Heberling | Heberling | [11 empty] | 0 | 0
443 | Heberling | Heberling | [11 empty] | 0 | 0
444 | JPKG |  |  | JPKG | Probably handled by other comments, but don't forget to apply this one. | [8 empty] | 0 | 0
445 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
446 | Heberling | Heberling | [11 empty] | 0 | 0
447 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
448 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
449 | Heberling | Heberling | [11 empty] | 0 | 0
450 | Heberling | Heberling | [11 empty] | 0 | 0
451 | Heberling | Heberling | [11 empty] | 0 | 0
452 | Heberling | Heberling | [11 empty] | 0 | 0
453 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
454 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
455 | Heberling | Heberling | [11 empty] | 0 | 0
456 | Heberling | Heberling | [11 empty] | 0 | 0
457 | Done | [10 empty] | Done | Rejected | 1 | 0
458 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
459 | jcb | [10 empty] | jcb | not resolved | 0 | 0
460 | Done | [10 empty] | Done | Rejected | 1 | 0
461 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
462 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
463 | jcb | [10 empty] | jcb | done with 269 | 0 | 0
464 | jcb | [10 empty] | jcb | ed note to combine lacks text | 0 | 0
465 | jcb | [10 empty] | jcb |  | 0 | 0
466 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
467 | Done |  |  | Done | Rejected | [8 empty] | 1 | 0
468 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
469 | jcb | [10 empty] | jcb |  | 0 | 0
470 | jcb | [10 empty] | jcb | change is in clause 7, cid 221 | 0 | 0
471 | jcb | [10 empty] | jcb | change is in clause 7, cid 221 | 0 | 0
472 | jcb | [10 empty] | jcb |  | 0 | 0
473 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
474 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
475 | jcb | [10 empty] | jcb | I havn't digested this one yet | 0 | 0
476 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
477 | Done | [10 empty] | Done | Rejected, see spelling of associating pg 165 lin 54 | 1 | 0
478 | Done | [10 empty] | Done | Rejected | 1 | 0
479 | Done | [10 empty] | Done | Rejected | 1 | 0
480 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
481 | jcb | [10 empty] | jcb |  | 0 | 0
482 | jcb | [10 empty] | jcb |  | 0 | 0
483 | jcb | [10 empty] | jcb | change is in clause 3.2 | 0 | 0
484 | jcb | [10 empty] | jcb | this and 485 address the same sentence! | 0 | 0
485 | jcb | [10 empty] | jcb |  | 0 | 0
486 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
487 | jcb | [10 empty] | jcb |  | 0 | 0
488 | jcb | [10 empty] | jcb |  | 0 | 0
489 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
490 | jcb | [10 empty] | jcb |  | 0 | 0
491 | jcb | [10 empty] | jcb |  | 0 | 0
492 | Done | [10 empty] | Done | Rejected | 1 | 0
493 | jcb | [10 empty] | jcb | no change required | 0 | 0
494 | jcb | [10 empty] | jcb |  | 0 | 0
495 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
496 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
497 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
498 | Done | [10 empty] | Done | Rejected | 1 | 0
499 | jcb | [10 empty] | jcb | see ed note for the comment | 0 | 0
500 | jcb | [10 empty] | jcb |  | 0 | 0
501 | Done | [10 empty] | Done | Rejected | 1 | 0
502 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
503 | jcb | [10 empty] | jcb |  | 0 | 0
504 | jcb | [10 empty] | jcb |  | 0 | 0
505 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
506 | jcb | [10 empty] | jcb |  | 0 | 0
507 | Done | [10 empty] | Done | Rejected | 1 | 0
508 | jcb | [10 empty] | jcb | need text | 0 | 0
509 | jcb | [10 empty] | jcb | no change required | 0 | 0
510 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
511 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
512 | Done |  |  | Done | Rejected | [8 empty] | 1 | 0
513 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
514 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
515 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
516 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
517 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
518 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
519 | jcb | [10 empty] | jcb |  | 0 | 0
520 | jcb | [10 empty] | jcb |  | 0 | 0
521 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
522 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
523 | jcb | [10 empty] | jcb |  | 0 | 0
524 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
525 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
526 | jcb | [10 empty] | jcb |  | 0 | 0
527 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
528 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
529 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
530 | jcb | [10 empty] | jcb | it seems that the second part goes at the end of the 2nd paragraph | 0 | 0
531 | Heberling | Heberling | [11 empty] | 0 | 0
532 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
533 | jcb | [10 empty] | jcb |  | 0 | 0
534 | Heberling | Heberling | [11 empty] | 0 | 0
535 | Heberling | Heberling | [11 empty] | 0 | 0
536 | Heberling | Heberling | [11 empty] | 0 | 0
537 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
538 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
539 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
540 | jcb | [10 empty] | jcb |  | 0 | 0
541 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
542 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
543 | jcb | [10 empty] | jcb | not resolved - PM | 0 | 0
544 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
545 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
546 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
547 | jcb | [10 empty] | jcb |  | 0 | 0
548 | Sarallo | [6 empty] | Sarallo | [5 empty] | 0 | 0
549 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
550 | Heberling | Heberling | [11 empty] | 0 | 0
551 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
Total resolved |  | 0 |  | 148 |  | 0 |  | 0 |  | 0 |  | 13
Total assigned

## Commentsresolved
Total left to close | 53 |  | Assigned to others | 2 | Assigned to Gilb | 3 | Assigned to Odman | 0 | Assigned to Schrader/Bain | 3 | PM | 9 | Pmwake | 1 | Editorials for Gilb | 6
Total left to assign | 0 |  |  |  | Assigned to Singer | 11 | Assigned to Heberling | 3 | Assigned to Bain | 0 | MTS | 11 | MaxCTAs | 0 | T & TR's left | 47
Comment ID | Assigned to | Status | Due date | Not Assigned | Assgned to Schrader | 4 | Assigned to Sarallo | 0
1 | Closed |  |  | 0
2 | Closed |  |  | 0
3 | Closed |  |  | 0
4 | Closed |  |  | 0
5 | Closed | John, do you approve? |  | 0
6 | Closed |  |  | 0
7 | Closed |  |  | 0
8 | Closed |  |  | 0
9 | Closed |  |  | 0
10 | Closed |  |  | 0
11 | Closed |  |  | 0
12 | Closed |  |  | 0
13 | Closed |  |  | 0
14 | Closed |  |  | 0
15 | Closed |  |  | 0
16 | Closed |  |  | 0
17 | Closed |  |  | 0
18 | Closed |  |  | 0
19 | Closed |  |  | 0
20 | Closed |  |  | 0
21 | Closed |  |  | 0
22 | Closed |  |  | 0
23 | Closed |  |  | 0
24 | Closed |  |  | 0
25 | Closed |  |  | 0
26 | Closed |  |  | 0
27 | Gilb | Written |  | 0
28 | Closed |  |  | 0
29 | Closed |  |  | 0
30 | Closed |  |  | 0
31 | Closed |  |  | 0
32 | Closed |  |  | 0
33 | Closed |  |  | 0
34 | Closed |  |  | 0
35 | Closed |  |  | 0
36 | Closed |  |  | 0
37 | Closed |  |  | 0
38 | Closed |  |  | 0
39 | Closed |  |  | 0
40 | Closed |  |  | 0
41 | Closed |  |  | 0
42 | Closed |  |  | 0
43 | Closed |  |  | 0
44 | Closed |  |  | 0
45 | Closed |  |  | 0
46 | Closed |  |  | 0
47 | Closed |  |  | 0
48 | Closed |  |  | 0
49 | Closed |  |  | 0
50 | Closed |  |  | 0
51 | Closed |  |  | 0
52 | Closed |  |  | 0
53 | Closed |  |  | 0
54 | Closed |  |  | 0
55 | Closed |  |  | 0
56 | MTS |  |  | 0
57 | Closed |  |  | 0
58 | Closed |  |  | 0
59 | Closed |  |  | 0
60 | Closed |  |  | 0
61 | Closed |  |  | 0
62 | Closed |  |  | 0
63 | Singer | Written |  | 0
64 | Closed |  |  | 0
65 | Pmwake |  |  | 0
66 | Closed |  |  | 0
67 | Closed |  |  | 0
68 | Closed |  |  | 0
69 | Closed |  |  | 0
70 | Closed |  |  | 0
71 | Closed |  |  | 0
72 | Closed |  |  | 0
73 | Closed |  |  | 0
74 | Closed |  |  | 0
75 | Gilb/Editorial |  |  | 0
76 | Gilb/Editorial |  |  | 0
77 | Closed |  |  | 0
78 | Closed |  |  | 0
79 | Closed |  |  | 0
80 | Closed |  |  | 0
81 | Closed |  |  | 0
82 | Closed |  |  | 0
83 | Closed |  |  | 0
84 | Closed |  |  | 0
85 | Closed |  |  | 0
86 | Closed |  |  | 0
87 | Closed |  |  | 0
88 | Closed |  |  | 0
89 | Closed |  |  | 0
90 | Closed |  |  | 0
91 | Closed |  |  | 0
92 | Closed |  |  | 0
93 | Singer | Written |  | 0
94 | Closed |  |  | 0
95 | Closed |  |  | 0
96 | Closed |  |  | 0
97 | Closed |  |  | 0
98 | Closed |  |  | 0
99 | Closed |  |  | 0
100 | Closed |  |  | 0
101 | Singer |  |  | 0
102 | Closed |  |  | 0
103 | Closed |  |  | 0
104 | Closed |  |  | 0
105 | Singer | Written |  | 0
106 | Closed |  |  | 0
107 | Closed |  |  | 0
108 | Closed |  |  | 0
109 | Gilb/Editorial |  |  | 0
110 | Closed |  |  | 0
111 | Singer | Written |  | 0
112 | Singer | Written |  | 0
113 | Closed |  |  | 0
114 | Closed |  |  | 0
115 | Closed |  |  | 0
116 | Singer | Written |  | 0
117 | Gilb/Editorial |  |  | 0
118 | Closed |  |  | 0
119 | Closed |  |  | 0
120 | Closed |  |  | 0
121 | Closed |  |  | 0
122 | Closed |  |  | 0
123 | Closed |  |  | 0
124 | Singer | Written |  | 0
125 | Closed |  |  | 0
126 | Closed |  |  | 0
127 | Closed |  |  | 0
128 | Closed |  |  | 0
129 | Closed |  |  | 0
130 | Closed |  |  | 0
131 | Closed |  |  | 0
132 | Closed |  |  | 0
133 | Closed |  |  | 0
134 | Closed |  |  | 0
135 | Closed |  |  | 0
136 | Closed |  |  | 0
137 | Closed |  |  | 0
138 | Closed |  |  | 0
139 | Closed |  |  | 0
140 | Closed |  |  | 0
141 | Closed |  |  | 0
142 | Closed |  |  | 0
143 | Closed |  |  | 0
144 | Closed |  |  | 0
145 | Closed |  |  | 0
146 | Closed |  |  | 0
147 | Closed |  |  | 0
148 | Closed |  |  | 0
149 | Closed |  |  | 0
150 | Closed |  |  | 0
151 | Closed |  |  | 0
152 | Closed |  |  | 0
153 | Closed |  |  | 0
154 | Closed |  |  | 0
155 | Closed |  |  | 0
156 | Closed |  |  | 0
157 | Closed |  |  | 0
158 | Closed |  |  | 0
159 | Closed |  |  | 0
160 | Closed |  |  | 0
161 | Closed |  |  | 0
162 | Closed |  |  | 0
163 | Closed |  |  | 0
164 | Closed |  |  | 0
165 | Closed |  |  | 0
166 | Closed |  |  | 0
167 | Closed |  |  | 0
168 | Closed |  |  | 0
169 | Closed |  |  | 0
170 | Heberling/email | Written |  | 0
171 | Closed |  |  | 0
172 | Closed |  |  | 0
173 | Closed |  |  | 0
174 | Closed |  |  | 0
175 | Closed |  |  | 0
176 | Closed |  |  | 0
177 | Closed |  |  | 0
178 | Closed |  |  | 0
179 | Closed |  |  | 0
180 | Closed |  |  | 0
181 | Closed |  |  | 0
182 | Closed |  |  | 0
183 | Heberling |  |  | 0
184 | Closed |  |  | 0
185 | Closed |  |  | 0
186 | Closed |  |  | 0
187 | Closed |  |  | 0
188 | Closed |  |  | 0
189 | Closed |  |  | 0
190 | Closed |  |  | 0
191 | Closed |  |  | 0
192 | Closed |  |  | 0
193 | Closed |  |  | 0
194 | Closed |  |  | 0
195 | Closed |  |  | 0
196 | Closed |  |  | 0
197 | Closed |  |  | 0
198 | Closed |  |  | 0
199 | Closed |  |  | 0
200 | Closed |  |  | 0
201 | Closed |  |  | 0
202 | Closed |  |  | 0
203 | Closed |  |  | 0
204 | Closed |  |  | 0
205 | Closed |  |  | 0
206 | Closed |  |  | 0
207 | Closed |  |  | 0
208 | Closed |  |  | 0
209 | Closed |  |  | 0
210 | Closed |  |  | 0
211 | Closed |  |  | 0
212 | Closed |  |  | 0
213 | Closed |  |  | 0
214 | Closed |  |  | 0
215 | Closed |  |  | 0
216 | Closed |  |  | 0
217 | Closed |  |  | 0
218 | Closed |  |  | 0
219 | Closed |  |  | 0
220 | Closed |  |  | 0
221 | Closed |  |  | 0
222 | Closed |  |  | 0
223 | Closed |  |  | 0
224 | Closed |  |  | 0
225 | Closed |  |  | 0
226 | Closed |  |  | 0
227 | Closed |  |  | 0
228 | Closed |  |  | 0
229 | Closed |  |  | 0
230 | Closed |  |  | 0
231 | Closed |  |  | 0
232 | Closed |  |  | 0
233 | Closed |  |  | 0
234 | Closed |  |  | 0
235 | Closed |  |  | 0
236 | Closed |  |  | 0
237 | Closed |  |  | 0
238 | Closed |  |  | 0
239 | Closed |  |  | 0
240 | Closed |  |  | 0
241 | Closed |  |  | 0
242 | Closed |  |  | 0
243 | Closed |  |  | 0
244 | Closed |  |  | 0
245 | Closed |  |  | 0
246 | Closed |  |  | 0
247 | Closed |  |  | 0
248 | Closed |  |  | 0
249 | Closed |  |  | 0
250 | Closed |  |  | 0
251 | Closed |  |  | 0
252 | Closed |  |  | 0
253 | Closed |  |  | 0
254 | Closed |  |  | 0
255 | Closed |  |  | 0
256 | Closed |  |  | 0
257 | Closed |  |  | 0
258 | Closed |  |  | 0
259 | Closed |  |  | 0
260 | Closed |  |  | 0
261 | Closed |  |  | 0
262 | Schrader |  |  | 0
263 | Closed |  |  | 0
264 | Closed |  |  | 0
265 | Closed |  |  | 0
266 | Closed |  |  | 0
267 | Closed |  |  | 0
268 | Closed |  |  | 0
269 | Closed |  |  | 0
270 | Closed |  |  | 0
271 | Closed |  |  | 0
272 | Closed |  |  | 0
273 | Closed |  |  | 0
274 | Closed |  |  | 0
275 | Closed |  |  | 0
276 | Closed |  |  | 0
277 | Closed |  |  | 0
278 | Closed |  |  | 0
279 | Closed |  |  | 0
280 | Closed |  |  | 0
281 | Closed |  |  | 0
282 | Closed |  |  | 0
283 | Closed |  |  | 0
284 | Closed |  |  | 0
285 | Closed |  |  | 0
286 | Closed |  |  | 0
287 | Closed |  |  | 0
288 | Closed |  |  | 0
289 | Closed |  |  | 0
290 | Heberling |  |  | 0
291 | Closed |  |  | 0
292 | Closed |  |  | 0
293 | Closed |  |  | 0
294 | Heberling |  |  | 0
295 | Closed |  |  | 0
296 | Closed |  |  | 0
297 | Closed |  |  | 0
298 | Closed |  |  | 0
299 | Closed |  |  | 0
300 | Closed |  |  | 0
301 | Closed |  |  | 0
302 | Closed |  |  | 0
303 | Closed |  |  | 0
304 | Closed |  |  | 0
305 | Closed |  |  | 0
306 | Closed |  |  | 0
307 | Closed |  |  | 0
308 | Closed |  |  | 0
309 | Closed |  |  | 0
310 | Closed |  |  | 0
311 | Closed |  |  | 0
312 | Closed |  |  | 0
313 | Closed |  |  | 0
314 | Closed |  |  | 0
315 | Closed |  |  | 0
316 | Closed |  |  | 0
317 | Closed |  |  | 0
318 | Closed |  |  | 0
319 | Closed |  |  | 0
320 | Closed |  |  | 0
321 | PM |  |  | 0
322 | Closed |  |  | 0
323 | Closed |  |  | 0
324 | PM |  |  | 0
325 | Closed |  |  | 0
326 | Closed |  |  | 0
327 | Closed |  |  | 0
328 | Closed |  |  | 0
329 | Closed |  |  | 0
330 | Closed |  |  | 0
331 | Closed |  |  | 0
332 | Closed |  |  | 0
333 | Closed |  |  | 0
334 | Closed |  |  | 0
335 | Closed |  |  | 0
336 | Closed |  |  | 0
337 | Closed |  |  | 0
338 | Closed |  |  | 0
339 | PM |  |  | 0
340 | Closed |  |  | 0
341 | Closed |  |  | 0
342 | Closed |  |  | 0
343 | PM |  |  | 0
344 | Closed |  |  | 0
345 | Closed |  |  | 0
346 | Closed |  |  | 0
347 | Closed |  |  | 0
348 | Closed |  |  | 0
349 | MTS |  |  | 0
350 | MTS |  |  | 0
351 | MTS |  |  | 0
352 | MTS |  |  | 0
353 | MTS |  |  | 0
354 | MTS |  |  | 0
355 | MTS |  |  | 0
356 | Schrader/Bain |  |  | 0
357 | Closed |  |  | 0
358 | PM |  |  | 0
359 | Schrader |  |  | 0
360 | PM |  |  | 0
361 | PM |  |  | 0
362 | Singer | Written |  | 0
363 | PM |  |  | 0
364 | PM |  |  | 0
365 | Closed |  |  | 0
366 | Closed |  |  | 0
367 | Closed |  |  | 0
368 | Closed |  |  | 0
369 | Closed |  |  | 0
370 | Singer | Written |  | 0
371 | Closed |  |  | 0
372 | Closed |  |  | 0
373 | Closed |  |  | 0
374 | Closed |  |  | 0
375 | Closed |  |  | 0
376 | Closed |  |  | 0
377 | Closed |  |  | 0
378 | Closed |  |  | 0
379 | Closed |  |  | 0
380 | Closed |  |  | 0
381 | Closed |  |  | 0
382 | Closed |  |  | 0
383 | Closed |  |  | 0
384 | Closed |  |  | 0
385 | Closed |  |  | 0
386 | Closed |  |  | 0
387 | MTS |  |  | 0
388 | Closed |  |  | 0
389 | Closed |  |  | 0
390 | Closed |  |  | 0
391 | Closed |  |  | 0
392 | Closed |  |  | 0
393 | Closed |  |  | 0
394 | Closed |  |  | 0
395 | Closed |  |  | 0
396 | Closed |  |  | 0
397 | Closed |  |  | 0
398 | Closed |  |  | 0
399 | Closed |  |  | 0
400 | Closed |  |  | 0
401 | Closed |  |  | 0
402 | Closed |  |  | 0
403 | Closed |  |  | 0
404 | Closed |  |  | 0
405 | Closed |  |  | 0
406 | Closed |  |  | 0
407 | MTS |  |  | 0
408 | Closed |  |  | 0
409 | Closed |  |  | 0
410 | Closed |  |  | 0
411 | Closed |  |  | 0
412 | Closed |  |  | 0
413 | Closed |  |  | 0
414 | Closed |  |  | 0
415 | Closed |  |  | 0
416 | Closed |  |  | 0
417 | Closed |  |  | 0
418 | Closed |  |  | 0
419 | Closed |  |  | 0
420 | Closed |  |  | 0
421 | Gilb/Editorial |  |  | 0
422 | Closed |  |  | 0
423 | Closed |  |  | 0
424 | Closed |  |  | 0
425 | Closed |  |  | 0
426 | Closed |  |  | 0
427 | Gilb | Written |  | 0
428 | Closed |  |  | 0
429 | Closed |  |  | 0
430 | Closed |  |  | 0
431 | Singer | Written |  | 0
432 | Closed |  |  | 0
433 | Closed |  |  | 0
434 | Closed |  |  | 0
435 | Closed |  |  | 0
436 | Closed |  |  | 0
437 | Closed |  |  | 0
438 | Closed |  |  | 0
439 | Closed |  |  | 0
440 | Closed |  |  | 0
441 | Closed |  |  | 0
442 | Closed |  |  | 0
443 | Closed |  |  | 0
444 | Closed |  |  | 0
445 | Closed |  |  | 0
446 | Closed |  |  | 0
447 | Closed |  |  | 0
448 | Closed |  |  | 0
449 | Closed |  |  | 0
450 | Schrader |  |  | 0
451 | Closed |  |  | 0
452 | Closed |  |  | 0
453 | Closed |  |  | 0
454 | Closed |  |  | 0
455 | Closed |  |  | 0
456 | Closed |  |  | 0
457 | Closed |  |  | 0
458 | Closed |  |  | 0
459 | Closed |  |  | 0
460 | Closed |  |  | 0
461 | Closed |  |  | 0
462 | Closed |  |  | 0
463 | Closed |  |  | 0
464 | Closed |  |  | 0
465 | Closed |  |  | 0
466 | Closed |  |  | 0
467 | Closed |  |  | 0
468 | Closed |  |  | 0
469 | Closed |  |  | 0
470 | Closed |  |  | 0
471 | Closed |  |  | 0
472 | Closed |  |  | 0
473 | Closed |  |  | 0
474 | Closed |  |  | 0
475 | Closed |  |  | 0
476 | Closed |  |  | 0
477 | Closed |  |  | 0
478 | Closed |  |  | 0
479 | Closed |  |  | 0
480 | Closed |  |  | 0
481 | Shvodian |  |  | 0
482 | Closed |  |  | 0
483 | Closed |  |  | 0
484 | Closed |  |  | 0
485 | Closed |  |  | 0
486 | Closed |  |  | 0
487 | Closed |  |  | 0
488 | Closed |  |  | 0
489 | Closed |  |  | 0
490 | Closed |  |  | 0
491 | Closed |  |  | 0
492 | Closed |  |  | 0
493 | Closed |  |  | 0
494 | Closed |  |  | 0
495 | Closed |  |  | 0
496 | Closed |  |  | 0
497 | Closed |  |  | 0
498 | Closed |  |  | 0
499 | Closed |  |  | 0
500 | Closed |  |  | 0
501 | Closed |  |  | 0
502 | Closed |  |  | 0
503 | Closed |  |  | 0
504 | Closed |  |  | 0
505 | Closed |  |  | 0
506 | Closed |  |  | 0
507 | Closed |  |  | 0
508 | Closed |  |  | 0
509 | Closed |  |  | 0
510 | Closed |  |  | 0
511 | Schrader |  |  | 0
512 | Closed |  |  | 0
513 | MTS |  |  | 0
514 | Closed |  |  | 0
515 | Closed |  |  | 0
516 | Closed |  |  | 0
517 | Closed |  |  | 0
518 | Closed |  |  | 0
519 | Gilb/Editorial |  |  | 0
520 | Closed |  |  | 0
521 | Closed |  |  | 0
522 | Closed |  |  | 0
523 | Closed |  |  | 0
524 | Closed |  |  | 0
525 | Closed |  |  | 0
526 | Closed |  |  | 0
527 | Closed |  |  | 0
528 | Closed |  |  | 0
529 | Closed |  |  | 0
530 | Closed |  |  | 0
531 | Closed |  |  | 0
532 | Closed |  |  | 0
533 | Closed |  |  | 0
534 | Closed |  |  | 0
535 | Schrader/Bain |  |  | 0
536 | Gilb |  |  | 0
537 | Closed |  |  | 0
538 | Closed |  |  | 0
539 | Closed |  |  | 0
540 | Closed |  |  | 0
541 | Closed |  |  | 0
542 | Closed |  |  | 0
543 | Schrader/Bain |  |  | 0
544 | Closed |  |  | 0
545 | Closed |  |  | 0
546 | Closed |  |  | 0
547 | Closed |  |  | 0
548 | Closed |  |  | 0
549 | Closed |  |  | 0
550 | Closed |  |  | 0
551 | Closed |  |  | 0