## IEEEcover
November 2002 |  | IEEE P802.15-02/475r0
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG3 LB22 comment drafting status
Date Submitted | [November 11, 2002]
Source | [James P. K. Gilb] | Voice: [(858)-485-6401]
| [Appairent Technologies] | Fax: [(858)-485-6406]
| [15373 Innovation Dr., #210] | E-mail: [gilb@ieee.org ]
[San Diego, CA 92128]
Re: | [00000D14P802.15.3-Draft-Standard]
Abstract | [This spreadsheet tracks the comment drafting status for both the assignments of issues to people as well as tracking when the resolutions are applied to the draft.]
Purpose | [To track the status of comment resolution and the application of the resolutions to the draft.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Commentswritten
|  | Left to go | 106
|  | Total finished | 139
|  | Left to claim | 101 | Enter 'done' when comment applied
CID | Status | Heberling | ADH comments | Gilb | JPKG comments | Singer | AS comments | Sarallo | JS comments | Schrader | MKS comments | Bain | JB comments | Tally | Claimed
1 | Done |  |  | Done | No change required in the resolution | [8 empty] | 1 | 0
2 | [13 empty] | 0 | 1
3 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
4 | [13 empty] | 0 | 1
5 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
6 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
7 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
8 | Done |  |  | Done | Text added as indicated | [8 empty] | 1 | 0
9 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
10 | [13 empty] | 0 | 1
11 | [13 empty] | 0 | 1
12 | [13 empty] | 0 | 1
13 | [13 empty] | 0 | 1
14 | [13 empty] | 0 | 1
15 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
16 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
17 | [13 empty] | 0 | 1
18 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
19 | [13 empty] | 0 | 1
20 | [13 empty] | 0 | 1
21 | Done |  |  | Done | No change required in the draft, TG will take action to change the PAR | [8 empty] | 1 | 0
22 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
23 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
24 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
25 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
26 | Done |  |  | Done | No change required in the draft, TG will take action to change the PAR | [8 empty] | 1 | 0
27 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
28 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
29 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
30 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
31 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
32 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
33 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
34 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
35 | [13 empty] | 0 | 1
36 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
37 | Done |  |  | Done | Comment is rejected, editorial | [8 empty] | 1 | 0
38 | [13 empty] | 0 | 1
39 | [13 empty] | 0 | 1
40 | [13 empty] | 0 | 1
41 | [13 empty] | 0 | 1
42 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
43 | [13 empty] | 0 | 1
44 | [13 empty] | 0 | 1
45 | [13 empty] | 0 | 1
46 | [13 empty] | 0 | 1
47 | [13 empty] | 0 | 1
48 | [13 empty] | 0 | 1
49 | [13 empty] | 0 | 1
50 | [13 empty] | 0 | 1
51 | [13 empty] | 0 | 1
52 | [13 empty] | 0 | 1
53 | [13 empty] | 0 | 1
54 | [13 empty] | 0 | 1
55 | [13 empty] | 0 | 1
56 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
57 | [13 empty] | 0 | 1
58 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
59 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
60 | Done |  |  | Done | No change required in the resolution | [8 empty] | 1 | 0
61 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
62 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
63 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
64 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
65 | [13 empty] | 0 | 1
66 | [13 empty] | 0 | 1
67 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
68 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
69 | JPKG |  |  | JPKG | Do we gather the items into a single table? | [8 empty] | 0 | 0
70 | Done |  |  | Done | No change required in the resolution | [8 empty] | 1 | 0
71 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
72 | [13 empty] | 0 | 1
73 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
74 | [13 empty] | 0 | 1
75 | [13 empty] | 0 | 1
76 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
77 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
78 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
79 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
80 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
81 | [13 empty] | 0 | 1
82 | [13 empty] | 0 | 1
83 | [13 empty] | 0 | 1
84 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
85 | [13 empty] | 0 | 1
86 | [13 empty] | 0 | 1
87 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
88 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
89 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
90 | [13 empty] | 0 | 1
91 | [13 empty] | 0 | 1
92 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
93 | Done |  |  | Done | MSC modified | [8 empty] | 1 | 0
94 | [13 empty] | 0 | 1
95 | [13 empty] | 0 | 1
96 | [13 empty] | 0 | 1
97 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
98 | Done |  |  | Done | Sentence deleted, editorial | [8 empty] | 1 | 0
99 | Done |  |  | Done | Paragraph deleted, editorial | [8 empty] | 1 | 0
100 | Done |  |  | Done | Sentence deleted, editorial | [8 empty] | 1 | 0
101 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
102 | [13 empty] | 0 | 1
103 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
104 | [13 empty] | 0 | 1
105 | [13 empty] | 0 | 1
106 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
107 | [13 empty] | 0 | 1
108 | [13 empty] | 0 | 1
109 | [13 empty] | 0 | 1
110 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
111 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
112 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
113 | [13 empty] | 0 | 1
114 | [13 empty] | 0 | 1
115 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
116 | [13 empty] | 0 | 1
117 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
118 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
119 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
120 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
121 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
122 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
123 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
124 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
125 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
126 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
127 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
128 | [13 empty] | 0 | 1
129 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
130 | [13 empty] | 0 | 1
131 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
132 | [13 empty] | 0 | 1
133 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
134 | [13 empty] | 0 | 1
135 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
136 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
137 | Done |  |  | Done | Changed as indicated in CID 202 | [8 empty] | 1 | 0
138 | [13 empty] | 0 | 1
139 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
140 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
141 | [13 empty] | 0 | 1
142 | [13 empty] | 0 | 1
143 | [13 empty] | 0 | 1
144 | [13 empty] | 0 | 1
145 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
146 | [13 empty] | 0 | 1
147 | [13 empty] | 0 | 1
148 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
149 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
150 | [13 empty] | 0 | 1
151 | [13 empty] | 0 | 1
152 | [13 empty] | 0 | 1
153 | Done |  |  | Done | No change required in the resolution | [8 empty] | 1 | 0
154 | Done |  |  | Done | Changed as indicated in CID 202 | [8 empty] | 1 | 0
155 | [13 empty] | 0 | 1
156 | [13 empty] | 0 | 1
157 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
158 | [13 empty] | 0 | 1
159 | [13 empty] | 0 | 1
160 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
161 | [13 empty] | 0 | 1
162 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
163 | [13 empty] | 0 | 1
164 | [13 empty] | 0 | 1
165 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
166 | [13 empty] | 0 | 1
167 | [13 empty] | 0 | 1
168 | [13 empty] | 0 | 1
169 | [13 empty] | 0 | 1
170 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
171 | [13 empty] | 0 | 1
172 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
173 | [13 empty] | 0 | 1
174 | [13 empty] | 0 | 1
175 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
176 | [13 empty] | 0 | 1
177 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
178 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
179 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
180 | Done |  |  | Done | Sentence deleted, editorial | [8 empty] | 1 | 0
181 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
182 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
183 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
184 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
185 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
186 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
187 | [13 empty] | 0 | 1
188 | [13 empty] | 0 | 1
189 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
190 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
191 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
192 | Done |  |  | Done | Text added as indicated | [8 empty] | 1 | 0
193 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
194 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
195 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
196 | Done |  |  | Done | Editorial changes | [8 empty] | 1 | 0
197 | [13 empty] | 0 | 1
198 | Done |  |  | Done | The sentence was moved. | [8 empty] | 1 | 0
199 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
200 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
201 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
202 | Done |  |  | Done | Text added as indicated, editorial | [8 empty] | 1 | 0
203 | Done |  |  | Done | Changed as indicated in CID 202 | [8 empty] | 1 | 0
204 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
205 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
206 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
207 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
208 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
209 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
210 | JPKG |  |  | JPKG | [9 empty] | 0 | 0
211 | Done |  |  | Done | Comment is rejected, editorial | [8 empty] | 1 | 0
212 | Done |  |  | Done | Comment is rejected, editorial | [8 empty] | 1 | 0
213 | Done |  |  | Done | Comment is rejected, editorial | [8 empty] | 1 | 0
214 | [13 empty] | 0 | 1
215 | [13 empty] | 0 | 1
216 | Done |  |  | Done | Text added as indicated | [8 empty] | 1 | 0
217 | [13 empty] | 0 | 1
218 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
219 | [13 empty] | 0 | 1
220 | [13 empty] | 0 | 1
221 | [13 empty] | 0 | 1
222 | [13 empty] | 0 | 1
223 | [13 empty] | 0 | 1
224 | [13 empty] | 0 | 1
225 | Done |  |  | Done | Text changed as indicated, editorial | [8 empty] | 1 | 0
226 | [13 empty] | 0 | 1
227 | [13 empty] | 0 | 1
228 | Done |  |  | Done | Changed as indicated in CID 202 | [8 empty] | 1 | 0
229 | [13 empty] | 0 | 1
230 | Done |  |  | Done | Text added as indicated | [8 empty] | 1 | 0
231 | Done |  |  | Done | Withdrawn | [8 empty] | 1 | 0
232 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
233 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
234 | [13 empty] | 0 | 1
235 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
236 | Done |  |  | Done | Changed as indicated in CID 100 | [8 empty] | 1 | 0
237 | [13 empty] | 0 | 1
238 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
239 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
240 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
241 | Done |  |  | Done | Text changed as indicated | [8 empty] | 1 | 0
242 | Done |  |  | Done | No change required in the resolution | [8 empty] | 1 | 0
243 | [13 empty] | 0 | 1
244 | [13 empty] | 0 | 1
245 | Done |  |  | Done | Comment is rejected | [8 empty] | 1 | 0
Total assigned |  | 0 |  | 144 |  | 0 |  | 0 |  | 0 |  | 0 |  | 144
Total resolved |  | 0 |  | 139 |  | 0 |  | 0 |  | 0 |  | 0 |  | 139
Total left to finish |  | 0 |  | 5 |  | 0 |  | 0 |  | 0 |  | 0 |  | 5

## Commentsresolved
Total left to close |  | 243 |  | Assigned to others | 241 | Assigned to Gilb | 2 | Assigned to Odman | 0 | Assigned to Schrader/Bain | 0 | PM | 0 | Pmwake | 0 | Editorials for Gilb | 0
Total left to assign |  | 243 |  |  |  | Assigned to Singer | 0 | Assigned to Heberling | 0 | Assigned to Bain | 0 | MTS | 0 | MaxCTAs | 0 | T & TR's left | 245
Comment ID | Assigned to | Closed/open | Status | Due date | Not Assigned | Assgned to Schrader | 0 | Assigned to Sarallo | 0
1 |  |  |  |  | 1
2 |  |  |  |  | 1
3 |  |  |  |  | 1
4 |  |  |  |  | 1
5 |  |  |  |  | 1
6 |  |  |  |  | 1
7 | Gilb | Closed |  |  | 0
8 |  |  |  |  | 1
9 |  |  |  |  | 1
10 |  |  |  |  | 1
11 |  |  |  |  | 1
12 |  |  |  |  | 1
13 |  |  |  |  | 1
14 |  |  |  |  | 1
15 |  |  |  |  | 1
16 |  |  |  |  | 1
17 |  |  |  |  | 1
18 |  |  |  |  | 1
19 |  |  |  |  | 1
20 |  |  |  |  | 1
21 |  |  |  |  | 1
22 |  |  |  |  | 1
23 |  |  |  |  | 1
24 |  |  |  |  | 1
25 |  |  |  |  | 1
26 |  |  |  |  | 1
27 |  |  |  |  | 1
28 |  |  |  |  | 1
29 |  |  |  |  | 1
30 |  |  |  |  | 1
31 |  |  |  |  | 1
32 |  |  |  |  | 1
33 |  |  |  |  | 1
34 |  |  |  |  | 1
35 |  |  |  |  | 1
36 |  |  |  |  | 1
37 |  |  |  |  | 1
38 |  |  |  |  | 1
39 |  |  |  |  | 1
40 |  |  |  |  | 1
41 |  |  |  |  | 1
42 |  |  |  |  | 1
43 |  |  |  |  | 1
44 |  |  |  |  | 1
45 |  |  |  |  | 1
46 |  |  |  |  | 1
47 |  |  |  |  | 1
48 |  |  |  |  | 1
49 |  |  |  |  | 1
50 |  |  |  |  | 1
51 |  |  |  |  | 1
52 |  |  |  |  | 1
53 |  |  |  |  | 1
54 |  |  |  |  | 1
55 |  |  |  |  | 1
56 |  |  |  |  | 1
57 |  |  |  |  | 1
58 |  |  |  |  | 1
59 |  |  |  |  | 1
60 |  |  |  |  | 1
61 |  |  |  |  | 1
62 |  |  |  |  | 1
63 |  |  |  |  | 1
64 |  |  |  |  | 1
65 |  |  |  |  | 1
66 |  |  |  |  | 1
67 |  |  |  |  | 1
68 |  |  |  |  | 1
69 |  |  |  |  | 1
70 |  |  |  |  | 1
71 |  |  |  |  | 1
72 |  |  |  |  | 1
73 |  |  |  |  | 1
74 |  |  |  |  | 1
75 |  |  |  |  | 1
76 |  |  |  |  | 1
77 |  |  |  |  | 1
78 |  |  |  |  | 1
79 |  |  |  |  | 1
80 |  |  |  |  | 1
81 |  |  |  |  | 1
82 |  |  |  |  | 1
83 |  |  |  |  | 1
84 |  |  |  |  | 1
85 |  |  |  |  | 1
86 |  |  |  |  | 1
87 |  |  |  |  | 1
88 |  |  |  |  | 1
89 |  |  |  |  | 1
90 |  |  |  |  | 1
91 |  |  |  |  | 1
92 |  |  |  |  | 1
93 |  |  |  |  | 1
94 |  |  |  |  | 1
95 |  |  |  |  | 1
96 |  |  |  |  | 1
97 |  |  |  |  | 1
98 |  |  |  |  | 1
99 |  |  |  |  | 1
100 |  |  |  |  | 1
101 |  |  |  |  | 1
102 |  |  |  |  | 1
103 |  |  |  |  | 1
104 |  |  |  |  | 1
105 |  |  |  |  | 1
106 |  |  |  |  | 1
107 |  |  |  |  | 1
108 |  |  |  |  | 1
109 |  |  |  |  | 1
110 |  |  |  |  | 1
111 |  |  |  |  | 1
112 |  |  |  |  | 1
113 |  |  |  |  | 1
114 |  |  |  |  | 1
115 |  |  |  |  | 1
116 |  |  |  |  | 1
117 |  |  |  |  | 1
118 |  |  |  |  | 1
119 |  |  |  |  | 1
120 |  |  |  |  | 1
121 |  |  |  |  | 1
122 |  |  |  |  | 1
123 |  |  |  |  | 1
124 |  |  |  |  | 1
125 |  |  |  |  | 1
126 |  |  |  |  | 1
127 |  |  |  |  | 1
128 |  |  |  |  | 1
129 |  |  |  |  | 1
130 |  |  |  |  | 1
131 |  |  |  |  | 1
132 |  |  |  |  | 1
133 |  |  |  |  | 1
134 |  |  |  |  | 1
135 |  |  |  |  | 1
136 |  |  |  |  | 1
137 |  |  |  |  | 1
138 |  |  |  |  | 1
139 |  |  |  |  | 1
140 |  |  |  |  | 1
141 |  |  |  |  | 1
142 |  |  |  |  | 1
143 |  |  |  |  | 1
144 |  |  |  |  | 1
145 |  |  |  |  | 1
146 |  |  |  |  | 1
147 |  |  |  |  | 1
148 |  |  |  |  | 1
149 |  |  |  |  | 1
150 |  |  |  |  | 1
151 |  |  |  |  | 1
152 |  |  |  |  | 1
153 |  |  |  |  | 1
154 |  |  |  |  | 1
155 |  |  |  |  | 1
156 |  |  |  |  | 1
157 |  |  |  |  | 1
158 |  |  |  |  | 1
159 |  |  |  |  | 1
160 |  |  |  |  | 1
161 |  |  |  |  | 1
162 |  |  |  |  | 1
163 |  |  |  |  | 1
164 |  |  |  |  | 1
165 |  |  |  |  | 1
166 |  |  |  |  | 1
167 |  |  |  |  | 1
168 |  |  |  |  | 1
169 |  |  |  |  | 1
170 |  |  |  |  | 1
171 |  |  |  |  | 1
172 |  |  |  |  | 1
173 |  |  |  |  | 1
174 |  |  |  |  | 1
175 |  |  |  |  | 1
176 |  |  |  |  | 1
177 |  |  |  |  | 1
178 |  |  |  |  | 1
179 |  |  |  |  | 1
180 |  |  |  |  | 1
181 |  |  |  |  | 1
182 |  |  |  |  | 1
183 |  |  |  |  | 1
184 |  |  |  |  | 1
185 |  |  |  |  | 1
186 |  |  |  |  | 1
187 |  |  |  |  | 1
188 |  |  |  |  | 1
189 |  |  |  |  | 1
190 |  |  |  |  | 1
191 |  |  |  |  | 1
192 |  |  |  |  | 1
193 |  |  |  |  | 1
194 |  |  |  |  | 1
195 |  |  |  |  | 1
196 |  |  |  |  | 1
197 |  |  |  |  | 1
198 |  |  |  |  | 1
199 |  |  |  |  | 1
200 |  |  |  |  | 1
201 |  |  |  |  | 1
202 |  |  |  |  | 1
203 |  |  |  |  | 1
204 |  |  |  |  | 1
205 |  |  |  |  | 1
206 |  |  |  |  | 1
207 |  |  |  |  | 1
208 |  |  |  |  | 1
209 |  |  |  |  | 1
210 |  |  |  |  | 1
211 |  |  |  |  | 1
212 |  |  |  |  | 1
213 |  |  |  |  | 1
214 |  |  |  |  | 1
215 |  |  |  |  | 1
216 |  |  |  |  | 1
217 |  |  |  |  | 1
218 |  |  |  |  | 1
219 |  |  |  |  | 1
220 |  |  |  |  | 1
221 |  |  |  |  | 1
222 |  |  |  |  | 1
223 |  |  |  |  | 1
224 |  |  |  |  | 1
225 |  |  |  |  | 1
226 |  |  |  |  | 1
227 |  |  |  |  | 1
228 |  |  |  |  | 1
229 |  |  |  |  | 1
230 |  |  |  |  | 1
231 |  |  |  |  | 1
232 |  |  |  |  | 1
233 |  |  |  |  | 1
234 |  |  |  |  | 1
235 | Gilb | Closed |  |  | 0
236 |  |  |  |  | 1
237 |  |  |  |  | 1
238 |  |  |  |  | 1
239 |  |  |  |  | 1
240 |  |  |  |  | 1
241 |  |  |  |  | 1
242 |  |  |  |  | 1
243 |  |  |  |  | 1
244 |  |  |  |  | 1
245 |  |  |  |  | 1