## IEEEcover
January 2003 |  | IEEE P802.15-03/035r3
IEEE P802.15
Wireless Personal Area Networks
Project | IEEE P802.15 Working Group for Wireless Personal Area Networks (WPANs)
Title | TG3 LB22 comment drafting status
Date Submitted | [January 13, 2003]
Source | [James P. K. Gilb] | Voice: [(858)-485-6401]
| [Appairent Technologies] | Fax: [(858)-485-6406]
| [15373 Innovation Dr., #210] | E-mail: [gilb@ieee.org ]
[San Diego, CA 92128]
Re: | [00000D15P802.15.3-Draft-Standard]
Abstract | [This spreadsheet tracks the comment drafting status for both the assignments of issues to people as well as tracking when the resolutions are applied to the draft.]
Purpose | [To track the status of comment resolution and the application of the resolutions to the draft.]
Notice | This document has been prepared to assist the IEEE P802.15. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after furt
Release | The contributor acknowledges and accepts that this contribution becomes the property of IEEE and may be made publicly available by P802.15.

## Commentswritten
|  | Left to go | 464
|  | Total finished | 362
|  | Left to claim | 446 | Enter 'done' when comment applied
CID | Status | Heberling | ADH comments | Gilb | JPKG comments | Singer | AS comments | Sarallo | JS comments | Schrader | MKS comments | Bain | JB comments | Tally | Claimed
1 | [13 empty] | 0 | 1
2 | [13 empty] | 0 | 1
3 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
4 | [13 empty] | 0 | 1
5 | [13 empty] | 0 | 1
6 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
7 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
8 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
9 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
10 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
11 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
12 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
13 | [13 empty] | 0 | 1
14 | [13 empty] | 0 | 1
15 | [13 empty] | 0 | 1
16 | [13 empty] | 0 | 1
17 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
18 | JPKG |  |  | JPKG | Do we start with a SECID or wait until the first DEV joins? If it uses secure beacons, what key does it use for integrity? | [8 empty] | 0 | 0
19 | [13 empty] | 0 | 1
20 | [13 empty] | 0 | 1
21 | [13 empty] | 0 | 1
22 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
23 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
24 | [13 empty] | 0 | 1
25 | [13 empty] | 0 | 1
26 | [13 empty] | 0 | 1
27 | [13 empty] | 0 | 1
28 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
29 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
30 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
31 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
32 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
33 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
34 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
35 | [13 empty] | 0 | 1
36 | [13 empty] | 0 | 1
37 | [13 empty] | 0 | 1
38 | [13 empty] | 0 | 1
39 | [13 empty] | 0 | 1
40 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
41 | [13 empty] | 0 | 1
42 | [13 empty] | 0 | 1
43 | [13 empty] | 0 | 1
44 | [13 empty] | 0 | 1
45 | [13 empty] | 0 | 1
46 | JPKG |  |  | JPKG | Waiting for figures from Shvodian | [8 empty] | 0 | 0
47 | [13 empty] | 0 | 1
48 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
49 | [13 empty] | 0 | 1
50 | [13 empty] | 0 | 1
51 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
52 | [13 empty] | 0 | 1
53 | [13 empty] | 0 | 1
54 | [13 empty] | 0 | 1
55 | [13 empty] | 0 | 1
56 | [13 empty] | 0 | 1
57 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
58 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
59 | [13 empty] | 0 | 1
60 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
61 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
62 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
63 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
64 | [13 empty] | 0 | 1
65 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
66 | [13 empty] | 0 | 1
67 | [13 empty] | 0 | 1
68 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
69 | [13 empty] | 0 | 1
70 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
71 | [13 empty] | 0 | 1
72 | [13 empty] | 0 | 1
73 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
74 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
75 | [13 empty] | 0 | 1
76 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
77 | [13 empty] | 0 | 1
78 | [13 empty] | 0 | 1
79 | [13 empty] | 0 | 1
80 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
81 | [13 empty] | 0 | 1
82 | [13 empty] | 0 | 1
83 | [13 empty] | 0 | 1
84 | [13 empty] | 0 | 1
85 | [13 empty] | 0 | 1
86 | [13 empty] | 0 | 1
87 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
88 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
89 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
90 | JPKG |  |  | JPKG | Editorial | [8 empty] | 0 | 0
91 | [13 empty] | 0 | 1
92 | [13 empty] | 0 | 1
93 | [13 empty] | 0 | 1
94 | [13 empty] | 0 | 1
95 | [13 empty] | 0 | 1
96 | [13 empty] | 0 | 1
97 | [13 empty] | 0 | 1
98 | [13 empty] | 0 | 1
99 | [13 empty] | 0 | 1
100 | [13 empty] | 0 | 1
101 | [13 empty] | 0 | 1
102 | [13 empty] | 0 | 1
103 | [13 empty] | 0 | 1
104 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
105 | JPKG |  |  | JPKG | Editorial | [8 empty] | 0 | 0
106 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
107 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
108 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
109 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
110 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
111 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
112 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
113 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
114 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
115 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
116 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
117 | [13 empty] | 0 | 1
118 | [13 empty] | 0 | 1
119 | [13 empty] | 0 | 1
120 | [13 empty] | 0 | 1
121 | [13 empty] | 0 | 1
122 | [13 empty] | 0 | 1
123 | [13 empty] | 0 | 1
124 | [13 empty] | 0 | 1
125 | [13 empty] | 0 | 1
126 | [13 empty] | 0 | 1
127 | [13 empty] | 0 | 1
128 | [13 empty] | 0 | 1
129 | [13 empty] | 0 | 1
130 | [13 empty] | 0 | 1
131 | [13 empty] | 0 | 1
132 | [13 empty] | 0 | 1
133 | [13 empty] | 0 | 1
134 | [13 empty] | 0 | 1
135 | [13 empty] | 0 | 1
136 | [13 empty] | 0 | 1
137 | [13 empty] | 0 | 1
138 | [13 empty] | 0 | 1
139 | [13 empty] | 0 | 1
140 | [13 empty] | 0 | 1
141 | JPKG |  |  | JPKG | Editorial | [8 empty] | 0 | 0
142 | [13 empty] | 0 | 1
143 | [13 empty] | 0 | 1
144 | [13 empty] | 0 | 1
145 | [13 empty] | 0 | 1
146 | [13 empty] | 0 | 1
147 | [13 empty] | 0 | 1
148 | [13 empty] | 0 | 1
149 | [13 empty] | 0 | 1
150 | [13 empty] | 0 | 1
151 | [13 empty] | 0 | 1
152 | [13 empty] | 0 | 1
153 | [13 empty] | 0 | 1
154 | [13 empty] | 0 | 1
155 | [13 empty] | 0 | 1
156 | [13 empty] | 0 | 1
157 | [13 empty] | 0 | 1
158 | [13 empty] | 0 | 1
159 | [13 empty] | 0 | 1
160 | [13 empty] | 0 | 1
161 | [13 empty] | 0 | 1
162 | [13 empty] | 0 | 1
163 | [13 empty] | 0 | 1
164 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
165 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
166 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
167 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
168 | [13 empty] | 0 | 1
169 | [13 empty] | 0 | 1
170 | [13 empty] | 0 | 1
171 | [13 empty] | 0 | 1
172 | [13 empty] | 0 | 1
173 | [13 empty] | 0 | 1
174 | [13 empty] | 0 | 1
175 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
176 | [13 empty] | 0 | 1
177 | [13 empty] | 0 | 1
178 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
179 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
180 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
181 | [13 empty] | 0 | 1
182 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
183 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
184 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
185 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
186 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
187 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
188 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
189 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
190 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
191 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
192 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
193 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
194 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
195 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
196 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
197 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
198 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
199 | [13 empty] | 0 | 1
200 | [13 empty] | 0 | 1
201 | [13 empty] | 0 | 1
202 | [13 empty] | 0 | 1
203 | [13 empty] | 0 | 1
204 | [13 empty] | 0 | 1
205 | [13 empty] | 0 | 1
206 | [13 empty] | 0 | 1
207 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
208 | [13 empty] | 0 | 1
209 | [13 empty] | 0 | 1
210 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
211 | Done |  |  | Done | Changed MaxAssociations to MaxAssociatedDEVs | [8 empty] | 1 | 0
212 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
213 | [13 empty] | 0 | 1
214 | JPKG |  |  | JPKG | Editorial | [8 empty] | 0 | 0
215 | [13 empty] | 0 | 1
216 | [13 empty] | 0 | 1
217 | JPKG |  |  | JPKG | Contact Kowalski and MAC people to figure out what to write. | [8 empty] | 0 | 0
218 | [13 empty] | 0 | 1
219 | [13 empty] | 0 | 1
220 | [13 empty] | 0 | 1
221 | [13 empty] | 0 | 1
222 | [13 empty] | 0 | 1
223 | [13 empty] | 0 | 1
224 | [13 empty] | 0 | 1
225 | [13 empty] | 0 | 1
226 | [13 empty] | 0 | 1
227 | [13 empty] | 0 | 1
228 | [13 empty] | 0 | 1
229 | [13 empty] | 0 | 1
230 | [13 empty] | 0 | 1
231 | [13 empty] | 0 | 1
232 | [13 empty] | 0 | 1
233 | [13 empty] | 0 | 1
234 | [13 empty] | 0 | 1
235 | [13 empty] | 0 | 1
236 | [13 empty] | 0 | 1
237 | [13 empty] | 0 | 1
238 | [13 empty] | 0 | 1
239 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
240 | [13 empty] | 0 | 1
241 | [13 empty] | 0 | 1
242 | [13 empty] | 0 | 1
243 | [13 empty] | 0 | 1
244 | [13 empty] | 0 | 1
245 | [13 empty] | 0 | 1
246 | [13 empty] | 0 | 1
247 | [13 empty] | 0 | 1
248 | [13 empty] | 0 | 1
249 | [13 empty] | 0 | 1
250 | [13 empty] | 0 | 1
251 | [13 empty] | 0 | 1
252 | [13 empty] | 0 | 1
253 | [13 empty] | 0 | 1
254 | [13 empty] | 0 | 1
255 | [13 empty] | 0 | 1
256 | [13 empty] | 0 | 1
257 | [13 empty] | 0 | 1
258 | [13 empty] | 0 | 1
259 | [13 empty] | 0 | 1
260 | [13 empty] | 0 | 1
261 | [13 empty] | 0 | 1
262 | [13 empty] | 0 | 1
263 | [13 empty] | 0 | 1
264 | [13 empty] | 0 | 1
265 | [13 empty] | 0 | 1
266 | [13 empty] | 0 | 1
267 | [13 empty] | 0 | 1
268 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
269 | [13 empty] | 0 | 1
270 | [13 empty] | 0 | 1
271 | JPKG |  |  | JPKG | Is this handled by a T comment? Perhaps JPKG one? | [8 empty] | 0 | 0
272 | [13 empty] | 0 | 1
273 | JPKG |  |  | JPKG | Is this handled by a T comment? Perhaps JPKG one? | [8 empty] | 0 | 0
274 | [13 empty] | 0 | 1
275 | [13 empty] | 0 | 1
276 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
277 | [13 empty] | 0 | 1
278 | [13 empty] | 0 | 1
279 | [13 empty] | 0 | 1
280 | [13 empty] | 0 | 1
281 | [13 empty] | 0 | 1
282 | [13 empty] | 0 | 1
283 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
284 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
285 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
286 | [13 empty] | 0 | 1
287 | [13 empty] | 0 | 1
288 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
289 | [13 empty] | 0 | 1
290 | [13 empty] | 0 | 1
291 | [13 empty] | 0 | 1
292 | [13 empty] | 0 | 1
293 | [13 empty] | 0 | 1
294 | [13 empty] | 0 | 1
295 | [13 empty] | 0 | 1
296 | [13 empty] | 0 | 1
297 | [13 empty] | 0 | 1
298 | [13 empty] | 0 | 1
299 | [13 empty] | 0 | 1
300 | [13 empty] | 0 | 1
301 | [13 empty] | 0 | 1
302 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
303 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
304 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
305 | [13 empty] | 0 | 1
306 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
307 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
308 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
309 | [13 empty] | 0 | 1
310 | [13 empty] | 0 | 1
311 | [13 empty] | 0 | 1
312 | [13 empty] | 0 | 1
313 | [13 empty] | 0 | 1
314 | [13 empty] | 0 | 1
315 | [13 empty] | 0 | 1
316 | [13 empty] | 0 | 1
317 | [13 empty] | 0 | 1
318 | [13 empty] | 0 | 1
319 | [13 empty] | 0 | 1
320 | [13 empty] | 0 | 1
321 | [13 empty] | 0 | 1
322 | [13 empty] | 0 | 1
323 | [13 empty] | 0 | 1
324 | [13 empty] | 0 | 1
325 | [13 empty] | 0 | 1
326 | [13 empty] | 0 | 1
327 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
328 | [13 empty] | 0 | 1
329 | [13 empty] | 0 | 1
330 | [13 empty] | 0 | 1
331 | [13 empty] | 0 | 1
332 | [13 empty] | 0 | 1
333 | [13 empty] | 0 | 1
334 | [13 empty] | 0 | 1
335 | [13 empty] | 0 | 1
336 | [13 empty] | 0 | 1
337 | [13 empty] | 0 | 1
338 | [13 empty] | 0 | 1
339 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
340 | [13 empty] | 0 | 1
341 | [13 empty] | 0 | 1
342 | [13 empty] | 0 | 1
343 | [13 empty] | 0 | 1
344 | [13 empty] | 0 | 1
345 | [13 empty] | 0 | 1
346 | [13 empty] | 0 | 1
347 | [13 empty] | 0 | 1
348 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
349 | [13 empty] | 0 | 1
350 | [13 empty] | 0 | 1
351 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
352 | [13 empty] | 0 | 1
353 | [13 empty] | 0 | 1
354 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
355 | [13 empty] | 0 | 1
356 | [13 empty] | 0 | 1
357 | [13 empty] | 0 | 1
358 | [13 empty] | 0 | 1
359 | [13 empty] | 0 | 1
360 | [13 empty] | 0 | 1
361 | [13 empty] | 0 | 1
362 | [13 empty] | 0 | 1
363 | [13 empty] | 0 | 1
364 | [13 empty] | 0 | 1
365 | [13 empty] | 0 | 1
366 | [13 empty] | 0 | 1
367 | [13 empty] | 0 | 1
368 | [13 empty] | 0 | 1
369 | [13 empty] | 0 | 1
370 | [13 empty] | 0 | 1
371 | [13 empty] | 0 | 1
372 | [13 empty] | 0 | 1
373 | [13 empty] | 0 | 1
374 | [13 empty] | 0 | 1
375 | [13 empty] | 0 | 1
376 | [13 empty] | 0 | 1
377 | [13 empty] | 0 | 1
378 | [13 empty] | 0 | 1
379 | [13 empty] | 0 | 1
380 | [13 empty] | 0 | 1
381 | [13 empty] | 0 | 1
382 | [13 empty] | 0 | 1
383 | [13 empty] | 0 | 1
384 | [13 empty] | 0 | 1
385 | [13 empty] | 0 | 1
386 | [13 empty] | 0 | 1
387 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
388 | [13 empty] | 0 | 1
389 | JPKG |  |  | JPKG | Editorial, pending Rene's contribution of a definition. | [8 empty] | 0 | 0
390 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
391 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
392 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
393 | JPKG |  |  | JPKG | Editorial, depends on the naming of the power save modes | [8 empty] | 0 | 0
394 | [13 empty] | 0 | 1
395 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
396 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
397 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
398 | [13 empty] | 0 | 1
399 | [13 empty] | 0 | 1
400 | [13 empty] | 0 | 1
401 | [13 empty] | 0 | 1
402 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
403 | [13 empty] | 0 | 1
404 | [13 empty] | 0 | 1
405 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
406 | [13 empty] | 0 | 1
407 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
408 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
409 | [13 empty] | 0 | 1
410 | [13 empty] | 0 | 1
411 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
412 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
413 | [13 empty] | 0 | 1
414 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
415 | [13 empty] | 0 | 1
416 | [13 empty] | 0 | 1
417 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
418 | [13 empty] | 0 | 1
419 | [13 empty] | 0 | 1
420 | [13 empty] | 0 | 1
421 | [13 empty] | 0 | 1
422 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
423 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
424 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
425 | [13 empty] | 0 | 1
426 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
427 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
428 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
429 | [13 empty] | 0 | 1
430 | [13 empty] | 0 | 1
431 | [13 empty] | 0 | 1
432 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
433 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
434 | [13 empty] | 0 | 1
435 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
436 | [13 empty] | 0 | 1
437 | [13 empty] | 0 | 1
438 | [13 empty] | 0 | 1
439 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
440 | JPKG |  |  | JPKG | Do we rename create-ASIE to update-ASIE or something else? | [8 empty] | 0 | 0
441 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
442 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
443 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
444 | [13 empty] | 0 | 1
445 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
446 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
447 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
448 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
449 | [13 empty] | 0 | 1
450 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
451 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
452 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
453 | [13 empty] | 0 | 1
454 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
455 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
456 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
457 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
458 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
459 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
460 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
461 | [13 empty] | 0 | 1
462 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
463 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
464 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
465 | [13 empty] | 0 | 1
466 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
467 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
468 | [13 empty] | 0 | 1
469 | [13 empty] | 0 | 1
470 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
471 | JPKG |  |  | JPKG | Rename table headings for probe command? | [8 empty] | 0 | 0
472 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
473 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
474 | [13 empty] | 0 | 1
475 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
476 | [13 empty] | 0 | 1
477 | [13 empty] | 0 | 1
478 | [13 empty] | 0 | 1
479 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
480 | [13 empty] | 0 | 1
481 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
482 | [13 empty] | 0 | 1
483 | [13 empty] | 0 | 1
484 | [13 empty] | 0 | 1
485 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
486 | [13 empty] | 0 | 1
487 | [13 empty] | 0 | 1
488 | [13 empty] | 0 | 1
489 | [13 empty] | 0 | 1
490 | [13 empty] | 0 | 1
491 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
492 | [13 empty] | 0 | 1
493 | [13 empty] | 0 | 1
494 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
495 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
496 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
497 | [13 empty] | 0 | 1
498 | [13 empty] | 0 | 1
499 | [13 empty] | 0 | 1
500 | [13 empty] | 0 | 1
501 | [13 empty] | 0 | 1
502 | [13 empty] | 0 | 1
503 | [13 empty] | 0 | 1
504 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
505 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
506 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
507 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
508 | [13 empty] | 0 | 1
509 | [13 empty] | 0 | 1
510 | [13 empty] | 0 | 1
511 | [13 empty] | 0 | 1
512 | [13 empty] | 0 | 1
513 | [13 empty] | 0 | 1
514 | [13 empty] | 0 | 1
515 | [13 empty] | 0 | 1
516 | [13 empty] | 0 | 1
517 | Done |  |  | Done | Changed MaxAssociations to MaxAssociatedDEVs | [8 empty] | 1 | 0
518 | [13 empty] | 0 | 1
519 | [13 empty] | 0 | 1
520 | [13 empty] | 0 | 1
521 | [13 empty] | 0 | 1
522 | [13 empty] | 0 | 1
523 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
524 | [13 empty] | 0 | 1
525 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
526 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
527 | [13 empty] | 0 | 1
528 | [13 empty] | 0 | 1
529 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
530 | [13 empty] | 0 | 1
531 | [13 empty] | 0 | 1
532 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
533 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
534 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
535 | [13 empty] | 0 | 1
536 | [13 empty] | 0 | 1
537 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
538 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
539 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
540 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
541 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
542 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
543 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
544 | [13 empty] | 0 | 1
545 | [13 empty] | 0 | 1
546 | [13 empty] | 0 | 1
547 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
548 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
549 | [13 empty] | 0 | 1
550 | [13 empty] | 0 | 1
551 | [13 empty] | 0 | 1
552 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
553 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
554 | [13 empty] | 0 | 1
555 | [13 empty] | 0 | 1
556 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
557 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
558 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
559 | [13 empty] | 0 | 1
560 | [13 empty] | 0 | 1
561 | [13 empty] | 0 | 1
562 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
563 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
564 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
565 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
566 | [13 empty] | 0 | 1
567 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
568 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
569 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
570 | [13 empty] | 0 | 1
571 | [13 empty] | 0 | 1
572 | [13 empty] | 0 | 1
573 | [13 empty] | 0 | 1
574 | [13 empty] | 0 | 1
575 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
576 | [13 empty] | 0 | 1
577 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
578 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
579 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
580 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
581 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
582 | [13 empty] | 0 | 1
583 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
584 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
585 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
586 | [13 empty] | 0 | 1
587 | JPKG |  |  | JPKG | Pending resolution of power management mode naming | [8 empty] | 0 | 0
588 | [13 empty] | 0 | 1
589 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
590 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
591 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
592 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
593 | [13 empty] | 0 | 1
594 | [13 empty] | 0 | 1
595 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
596 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
597 | [13 empty] | 0 | 1
598 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
599 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
600 | [13 empty] | 0 | 1
601 | [13 empty] | 0 | 1
602 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
603 | [13 empty] | 0 | 1
604 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
605 | [13 empty] | 0 | 1
606 | [13 empty] | 0 | 1
607 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
608 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
609 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
610 | [13 empty] | 0 | 1
611 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
612 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
613 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
614 | [13 empty] | 0 | 1
615 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
616 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
617 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
618 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
619 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
620 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
621 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
622 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
623 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
624 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
625 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
626 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
627 | [13 empty] | 0 | 1
628 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
629 | [13 empty] | 0 | 1
630 | [13 empty] | 0 | 1
631 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
632 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
633 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
634 | [13 empty] | 0 | 1
635 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
636 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
637 | [13 empty] | 0 | 1
638 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
639 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
640 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
641 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
642 | [13 empty] | 0 | 1
643 | [13 empty] | 0 | 1
644 | [13 empty] | 0 | 1
645 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
646 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
647 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
648 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
649 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
650 | [13 empty] | 0 | 1
651 | Done |  |  | Done | Changed everywhere in the draft. | [8 empty] | 1 | 0
652 | [13 empty] | 0 | 1
653 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
654 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
655 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
656 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
657 | [13 empty] | 0 | 1
658 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
659 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
660 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
661 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
662 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
663 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
664 | [13 empty] | 0 | 1
665 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
666 | [13 empty] | 0 | 1
667 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
668 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
669 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
670 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
671 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
672 | [13 empty] | 0 | 1
673 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
674 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
675 | [13 empty] | 0 | 1
676 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
677 | [13 empty] | 0 | 1
678 | [13 empty] | 0 | 1
679 | [13 empty] | 0 | 1
680 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
681 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
682 | [13 empty] | 0 | 1
683 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
684 | [13 empty] | 0 | 1
685 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
686 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
687 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
688 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
689 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
690 | [13 empty] | 0 | 1
691 | [13 empty] | 0 | 1
692 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
693 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
694 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
695 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
696 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
697 | [13 empty] | 0 | 1
698 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
699 | [13 empty] | 0 | 1
700 | [13 empty] | 0 | 1
701 | [13 empty] | 0 | 1
702 | [13 empty] | 0 | 1
703 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
704 | [13 empty] | 0 | 1
705 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
706 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
707 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
708 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
709 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
710 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
711 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
712 | [13 empty] | 0 | 1
713 | [13 empty] | 0 | 1
714 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
715 | Done |  |  | Done | Text changed as indicated in resolution. | [8 empty] | 1 | 0
716 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
717 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
718 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
719 | [13 empty] | 0 | 1
720 | [13 empty] | 0 | 1
721 | [13 empty] | 0 | 1
722 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
723 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
724 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
725 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
726 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
727 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
728 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
729 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
730 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
731 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
732 | [13 empty] | 0 | 1
733 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
734 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
735 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
736 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
737 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
738 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
739 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
740 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
741 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
742 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
743 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
744 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
745 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
746 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
747 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
748 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
749 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
750 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
751 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
752 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
753 | [13 empty] | 0 | 1
754 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
755 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
756 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
757 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
758 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
759 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
760 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
761 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
762 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
763 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
764 | [13 empty] | 0 | 1
765 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
766 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
767 | [13 empty] | 0 | 1
768 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
769 | [13 empty] | 0 | 1
770 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
771 | [13 empty] | 0 | 1
772 | [13 empty] | 0 | 1
773 | JPKG |  |  | JPKG | Pending resolution of power management mode naming | [8 empty] | 0 | 0
774 | [13 empty] | 0 | 1
775 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
776 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
777 | [13 empty] | 0 | 1
778 | [13 empty] | 0 | 1
779 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
780 | [13 empty] | 0 | 1
781 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
782 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
783 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
784 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
785 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
786 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
787 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
788 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
789 | [13 empty] | 0 | 1
790 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
791 | [13 empty] | 0 | 1
792 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
793 | [13 empty] | 0 | 1
794 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
795 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
796 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
797 | [13 empty] | 0 | 1
798 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
799 | [13 empty] | 0 | 1
800 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
801 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
802 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
803 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
804 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
805 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
806 | [13 empty] | 0 | 1
807 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
808 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
809 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
810 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
811 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
812 | JPKG |  |  | JPKG | Pending resolution of power management mode naming | [8 empty] | 0 | 0
813 | JPKG |  |  | JPKG | Pending resolution of power management mode naming | [8 empty] | 0 | 0
814 | JPKG |  |  | JPKG | Pending resolution of power management mode naming | [8 empty] | 0 | 0
815 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
816 | [13 empty] | 0 | 1
817 | [13 empty] | 0 | 1
818 | [13 empty] | 0 | 1
819 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
820 | [13 empty] | 0 | 1
821 | [13 empty] | 0 | 1
822 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
823 | Done |  |  | Done | Editorial | [8 empty] | 1 | 0
824 | [13 empty] | 0 | 1
825 | [13 empty] | 0 | 1
826 | [13 empty] | 0 | 1
Total assigned |  | 0 |  | 380 |  | 0 |  | 0 |  | 0 |  | 0 |  | 380
Total resolved |  | 0 |  | 362 |  | 0 |  | 0 |  | 0 |  | 0 |  | 362
Total left to finish |  | 0 |  | 18 |  | 0 |  | 0 |  | 0 |  | 0 |  | 18

## Commentsresolved
Total left to close |  | 826 |  | Assigned to others | 801 | Assigned to Gilb | 13 | Assigned to Odman | 1 | Assigned to Schrader/Bain | 0 | PM | 0 | Pmwake | 0 | Editorials for Gilb | 0
Total left to assign |  | 824 |  |  |  | Assigned to Singer | 1 | Assigned to Heberling | 3 | Assigned to Bain | 5 | MTS | 0 | MaxCTAs | 0 | T & TR's left | 849
Comment ID | Assigned to | Closed/open | Status | Due date | Not Assigned | Assgned to Schrader | 0 | Assigned to Sarallo | 2
1 |  |  |  |  | 1
2 |  |  |  |  | 1
3 |  |  |  |  | 1
4 | Sarallo |  | Text in email box |  | 1
5 |  |  |  |  | 1
6 |  |  |  |  | 1
7 |  |  |  |  | 1
8 |  |  |  |  | 1
9 |  |  |  |  | 1
10 |  |  |  |  | 1
11 |  |  |  |  | 1
12 |  |  |  |  | 1
13 |  |  |  |  | 1
14 | Bailey |  | Due 1/24 Write sentence “Prohibit distribute key from doing management keys.” |  | 1
15 |  |  |  |  | 1
16 |  |  |  |  | 1
17 |  |  |  |  | 1
18 |  |  |  |  | 1
19 |  |  |  |  | 1
20 |  |  |  |  | 1
21 | Bailey |  | Due 1/24, Write up a short description |  | 1
22 |  |  |  |  | 1
23 |  |  |  |  | 1
24 | Singer |  | Text submitted. |  | 1
25 |  |  |  |  | 1
26 |  |  |  |  | 1
27 |  |  |  |  | 1
28 |  |  |  |  | 1
29 |  |  |  |  | 1
30 |  |  |  |  | 1
31 |  |  |  |  | 1
32 |  |  |  |  | 1
33 |  |  |  |  | 1
34 |  |  |  |  | 1
35 |  |  |  |  | 1
36 |  |  |  |  | 1
37 |  |  |  |  | 1
38 |  |  |  |  | 1
39 |  |  |  |  | 1
40 |  |  |  |  | 1
41 |  |  |  |  | 1
42 |  |  |  |  | 1
43 |  |  |  |  | 1
44 |  |  |  |  | 1
45 | Bain |  | Need input |  | 1
46 |  |  |  |  | 1
47 |  |  |  |  | 1
48 |  |  |  |  | 1
49 | Shvodian |  | Due 1/24, Resolve with CID 677 |  | 1
50 |  |  |  |  | 1
51 |  |  |  |  | 1
52 | Bain |  | Consider withdrawing? |  | 1
53 | JPKG |  | Due 1/28, JPKG to suggest clause 11 text, don't need PIB |  | 1
54 |  |  |  |  | 1
55 |  |  |  |  | 1
56 |  |  |  |  | 1
57 |  |  |  |  | 1
58 |  |  |  |  | 1
59 |  |  |  |  | 1
60 |  |  |  |  | 1
61 |  |  |  |  | 1
62 |  |  |  |  | 1
63 |  |  |  |  | 1
64 |  |  |  |  | 1
65 |  |  |  |  | 1
66 |  |  |  |  | 1
67 |  |  |  |  | 1
68 |  |  |  |  | 1
69 |  |  |  |  | 1
70 |  |  |  |  | 1
71 | Bain |  | Need to generate text for new MLME |  | 1
72 | Bain |  | Need to add for PIB, delete dynamic/static |  | 1
73 |  |  |  |  | 1
74 |  |  |  |  | 1
75 |  |  |  |  | 1
76 |  |  |  |  | 1
77 |  |  |  |  | 1
78 |  |  |  |  | 1
79 |  |  |  |  | 1
80 |  |  |  |  | 1
81 |  |  |  |  | 1
82 | Bain |  | Need to specify the IE |  | 1
83 |  |  |  |  | 1
84 |  |  |  |  | 1
85 |  |  |  |  | 1
86 |  |  |  |  | 1
87 |  |  |  |  | 1
88 |  |  |  |  | 1
89 |  |  |  |  | 1
90 |  |  |  |  | 1
91 | Gilb |  | 1/28 Interop text |  | 1
92 |  |  |  |  | 1
93 |  |  |  |  | 1
94 |  |  |  |  | 1
95 |  |  |  |  | 1
96 |  |  |  |  | 1
97 |  |  |  |  | 1
98 |  |  |  |  | 1
99 |  |  |  |  | 1
100 |  |  |  |  | 1
101 |  |  |  |  | 1
102 |  |  |  |  | 1
103 |  |  |  |  | 1
104 |  |  |  |  | 1
105 |  |  |  |  | 1
106 |  |  |  |  | 1
107 |  |  |  |  | 1
108 |  |  |  |  | 1
109 |  |  |  |  | 1
110 |  |  |  |  | 1
111 |  |  |  |  | 1
112 |  |  |  |  | 1
113 |  |  |  |  | 1
114 |  |  |  |  | 1
115 |  |  |  |  | 1
116 |  |  |  |  | 1
117 |  |  |  |  | 1
118 |  |  |  |  | 1
119 |  |  |  |  | 1
120 |  |  |  |  | 1
121 |  |  |  |  | 1
122 |  |  |  |  | 1
123 |  |  |  |  | 1
124 |  |  |  |  | 1
125 |  |  |  |  | 1
126 |  |  |  |  | 1
127 |  |  |  |  | 1
128 |  |  |  |  | 1
129 |  |  |  |  | 1
130 |  |  |  |  | 1
131 |  |  |  |  | 1
132 |  |  |  |  | 1
133 |  |  |  |  | 1
134 |  |  |  |  | 1
135 |  |  |  |  | 1
136 |  |  |  |  | 1
137 |  |  |  |  | 1
138 |  |  |  |  | 1
139 | Gilb |  | Due 1/28, New handover |  | 1
140 |  |  |  |  | 1
141 |  |  |  |  | 1
142 |  |  |  |  | 1
143 |  |  |  |  | 1
144 |  |  |  |  | 1
145 |  |  |  |  | 1
146 |  |  |  |  | 1
147 |  |  |  |  | 1
148 |  |  |  |  | 1
149 |  |  |  |  | 1
150 |  |  |  |  | 1
151 |  |  |  |  | 1
152 | Gilb |  | Reject with new information. |  | 1
153 |  |  |  |  | 1
154 | Gilb |  | Reject using old text |  | 1
155 |  |  |  |  | 1
156 |  |  |  |  | 1
157 |  |  |  |  | 1
158 |  |  |  |  | 1
159 |  |  |  |  | 1
160 |  |  |  |  | 1
161 |  |  |  |  | 1
162 |  |  |  |  | 1
163 |  |  |  |  | 1
164 |  |  |  |  | 1
165 |  |  |  |  | 1
166 |  |  |  |  | 1
167 |  |  |  |  | 1
168 |  |  |  |  | 1
169 |  |  |  |  | 1
170 |  |  |  |  | 1
171 |  |  |  |  | 1
172 |  |  |  |  | 1
173 |  |  |  |  | 1
174 | Heberling |  | Due 1/24, Need to write definition |  | 1
175 |  |  |  |  | 1
176 |  |  |  |  | 1
177 |  |  |  |  | 1
178 |  |  |  |  | 1
179 |  |  |  |  | 1
180 |  |  |  |  | 1
181 |  |  |  |  | 1
182 |  |  |  |  | 1
183 |  |  |  |  | 1
184 |  |  |  |  | 1
185 |  |  |  |  | 1
186 |  |  |  |  | 1
187 |  |  |  |  | 1
188 |  |  |  |  | 1
189 |  |  |  |  | 1
190 |  |  |  |  | 1
191 |  |  |  |  | 1
192 |  |  |  |  | 1
193 |  |  |  |  | 1
194 |  |  |  |  | 1
195 |  |  |  |  | 1
196 |  |  |  |  | 1
197 |  |  |  |  | 1
198 |  |  |  |  | 1
199 |  |  |  |  | 1
200 |  |  |  |  | 1
201 |  |  |  |  | 1
202 |  |  |  |  | 1
203 |  |  |  |  | 1
204 | Heberling |  | Jan 30 call Discuss with KO |  | 1
205 |  |  |  |  | 1
206 |  |  |  |  | 1
207 |  |  |  |  | 1
208 |  |  |  |  | 1
209 |  |  |  |  | 1
210 |  |  |  |  | 1
211 |  |  |  |  | 1
212 |  |  |  |  | 1
213 |  |  |  |  | 1
214 |  |  |  |  | 1
215 | Gilb |  | New handover |  | 1
216 | Gilb |  | Fix words to indicate that this is not a currently standardized method. |  | 1
217 |  |  |  |  | 1
218 |  |  |  |  | 1
219 |  |  |  |  | 1
220 |  |  |  |  | 1
221 |  |  |  |  | 1
222 |  |  |  |  | 1
223 |  |  |  |  | 1
224 |  |  |  |  | 1
225 |  |  |  |  | 1
226 |  |  |  |  | 1
227 | Shvodian | Done |  |  | 0
228 |  |  |  |  | 1
229 |  |  |  |  | 1
230 |  |  |  |  | 1
231 |  |  |  |  | 1
232 |  |  |  |  | 1
233 |  |  |  |  | 1
234 |  |  |  |  | 1
235 |  |  |  |  | 1
236 |  |  |  |  | 1
237 |  |  |  |  | 1
238 |  |  |  |  | 1
239 |  |  |  |  | 1
240 |  |  |  |  | 1
241 |  |  |  |  | 1
242 |  |  |  |  | 1
243 |  |  |  |  | 1
244 |  |  |  |  | 1
245 |  |  |  |  | 1
246 |  |  |  |  | 1
247 |  |  |  |  | 1
248 |  |  |  |  | 1
249 |  |  |  |  | 1
250 |  |  |  |  | 1
251 |  |  |  |  | 1
252 |  |  |  |  | 1
253 |  |  |  |  | 1
254 | Heberling |  | Resolve as in CID 204 |  | 1
255 |  |  |  |  | 1
256 |  |  |  |  | 1
257 |  |  |  |  | 1
258 |  |  |  |  | 1
259 |  |  |  |  | 1
260 |  |  |  |  | 1
261 |  |  |  |  | 1
262 |  |  |  |  | 1
263 |  |  |  |  | 1
264 |  |  |  |  | 1
265 |  |  |  |  | 1
266 |  |  |  |  | 1
267 |  |  |  |  | 1
268 |  |  |  |  | 1
269 |  |  |  |  | 1
270 |  |  |  |  | 1
271 |  |  |  |  | 1
272 |  |  |  |  | 1
273 |  |  |  |  | 1
274 |  |  |  |  | 1
275 | Schrader |  | Due 1/24, Provide text for limiting async slots |  | 1
276 |  |  |  |  | 1
277 |  |  |  |  | 1
278 |  |  |  |  | 1
279 |  |  |  |  | 1
280 |  |  |  |  | 1
281 |  |  |  |  | 1
282 |  |  |  |  | 1
283 |  |  |  |  | 1
284 |  |  |  |  | 1
285 |  |  |  |  | 1
286 |  |  |  |  | 1
287 |  |  |  |  | 1
288 |  |  |  |  | 1
289 |  |  |  |  | 1
290 |  |  |  |  | 1
291 |  |  |  |  | 1
292 |  |  |  |  | 1
293 |  |  |  |  | 1
294 |  |  |  |  | 1
295 |  |  |  |  | 1
296 |  |  |  |  | 1
297 |  |  |  |  | 1
298 |  |  |  |  | 1
299 |  |  |  |  | 1
300 |  |  |  |  | 1
301 |  |  |  |  | 1
302 |  |  |  |  | 1
303 |  |  |  |  | 1
304 |  |  |  |  | 1
305 |  |  |  |  | 1
306 |  |  |  |  | 1
307 |  |  |  |  | 1
308 |  |  |  |  | 1
309 |  |  |  |  | 1
310 |  |  |  |  | 1
311 |  |  |  |  | 1
312 |  |  |  |  | 1
313 |  |  |  |  | 1
314 |  |  |  |  | 1
315 |  |  |  |  | 1
316 |  |  |  |  | 1
317 |  |  |  |  | 1
318 |  |  |  |  | 1
319 |  |  |  |  | 1
320 |  |  |  |  | 1
321 |  |  |  |  | 1
322 |  |  |  |  | 1
323 |  |  |  |  | 1
324 |  |  |  |  | 1
325 |  |  |  |  | 1
326 |  |  |  |  | 1
327 |  |  |  |  | 1
328 |  |  |  |  | 1
329 |  |  |  |  | 1
330 |  |  |  |  | 1
331 | Shvodian |  | Is there a way to configure multicast groups |  | 1
332 |  |  |  |  | 1
333 |  |  |  |  | 1
334 |  |  |  |  | 1
335 |  |  |  |  | 1
336 |  |  |  |  | 1
337 |  |  |  |  | 1
338 |  | Done |  |  | 0
339 |  |  |  |  | 1
340 |  |  |  |  | 1
341 |  |  |  |  | 1
342 |  |  |  |  | 1
343 |  |  |  |  | 1
344 |  |  |  |  | 1
345 |  |  |  |  | 1
346 |  |  |  |  | 1
347 |  |  |  |  | 1
348 |  |  |  |  | 1
349 |  |  |  |  | 1
350 | Struik |  | Will provide new definitions by Jan 22. |  | 1
351 |  |  |  |  | 1
352 | Gilb |  | New handover |  | 1
353 | Sarallo |  | Provide short section on dependent piconet ending operation. |  | 1
354 |  |  |  |  | 1
355 |  |  |  |  | 1
356 |  |  |  |  | 1
357 |  |  |  |  | 1
358 |  |  |  |  | 1
359 |  |  |  |  | 1
360 |  |  |  |  | 1
361 |  |  |  |  | 1
362 |  |  |  |  | 1
363 |  |  |  |  | 1
364 |  |  |  |  | 1
365 |  |  |  |  | 1
366 |  |  |  |  | 1
367 |  |  |  |  | 1
368 |  |  |  |  | 1
369 |  |  |  |  | 1
370 |  |  |  |  | 1
371 |  |  |  |  | 1
372 |  |  |  |  | 1
373 |  |  |  |  | 1
374 |  |  |  |  | 1
375 |  |  |  |  | 1
376 |  |  |  |  | 1
377 |  |  |  |  | 1
378 |  |  |  |  | 1
379 |  |  |  |  | 1
380 |  |  |  |  | 1
381 |  |  |  |  | 1
382 |  |  |  |  | 1
383 |  |  |  |  | 1
384 |  |  |  |  | 1
385 |  |  |  |  | 1
386 |  |  |  |  | 1
387 |  |  |  |  | 1
388 |  |  |  |  | 1
389 |  |  |  |  | 1
390 |  |  |  |  | 1
391 |  |  |  |  | 1
392 |  |  |  |  | 1
393 |  |  |  |  | 1
394 | Gilb |  | Waiting for 509 |  | 1
395 |  |  |  |  | 1
396 |  |  |  |  | 1
397 |  |  |  |  | 1
398 |  |  |  |  | 1
399 |  |  |  |  | 1
400 |  |  |  |  | 1
401 |  |  |  |  | 1
402 |  |  |  |  | 1
403 |  |  |  |  | 1
404 |  |  |  |  | 1
405 |  |  |  |  | 1
406 |  |  |  |  | 1
407 |  |  |  |  | 1
408 |  |  |  |  | 1
409 |  |  |  |  | 1
410 |  |  |  |  | 1
411 |  |  |  |  | 1
412 |  |  |  |  | 1
413 |  |  |  |  | 1
414 |  |  |  |  | 1
415 |  |  |  |  | 1
416 |  |  |  |  | 1
417 |  |  |  |  | 1
418 |  |  |  |  | 1
419 |  |  |  |  | 1
420 |  |  |  |  | 1
421 |  |  |  |  | 1
422 |  |  |  |  | 1
423 |  |  |  |  | 1
424 |  |  |  |  | 1
425 | Bailey |  | 1/24, Create MLME |  | 1
426 |  |  |  |  | 1
427 |  |  |  |  | 1
428 |  |  |  |  | 1
429 |  |  |  |  | 1
430 |  |  |  |  | 1
431 |  |  |  |  | 1
432 |  |  |  |  | 1
433 |  |  |  |  | 1
434 |  |  |  |  | 1
435 |  |  |  |  | 1
436 |  |  |  |  | 1
437 |  |  |  |  | 1
438 |  |  |  |  | 1
439 |  |  |  |  | 1
440 |  |  |  |  | 1
441 |  |  |  |  | 1
442 |  |  |  |  | 1
443 |  |  |  |  | 1
444 |  |  |  |  | 1
445 |  |  |  |  | 1
446 |  |  |  |  | 1
447 |  |  |  |  | 1
448 |  |  |  |  | 1
449 |  |  |  |  | 1
450 |  |  |  |  | 1
451 |  |  |  |  | 1
452 |  |  |  |  | 1
453 |  |  |  |  | 1
454 |  |  |  |  | 1
455 |  |  |  |  | 1
456 |  |  |  |  | 1
457 |  |  |  |  | 1
458 |  |  |  |  | 1
459 |  |  |  |  | 1
460 |  |  |  |  | 1
461 |  |  |  |  | 1
462 |  |  |  |  | 1
463 |  |  |  |  | 1
464 |  |  |  |  | 1
465 |  |  |  |  | 1
466 |  |  |  |  | 1
467 |  |  |  |  | 1
468 |  |  |  |  | 1
469 |  |  |  |  | 1
470 |  |  |  |  | 1
471 |  |  |  |  | 1
472 |  |  |  |  | 1
473 |  |  |  |  | 1
474 |  |  |  |  | 1
475 |  |  |  |  | 1
476 | Schrader |  | Text due in email 1/21 |  | 1
477 | Gilb |  | Waiting for 509 |  | 1
478 |  |  |  |  | 1
479 |  |  |  |  | 1
480 |  |  |  |  | 1
481 |  |  |  |  | 1
482 |  |  |  |  | 1
483 |  |  |  |  | 1
484 |  |  |  |  | 1
485 |  |  |  |  | 1
486 |  |  |  |  | 1
487 |  |  |  |  | 1
488 |  |  |  |  | 1
489 |  |  |  |  | 1
490 |  |  |  |  | 1
491 |  |  |  |  | 1
492 |  |  |  |  | 1
493 |  |  |  |  | 1
494 |  |  |  |  | 1
495 |  |  |  |  | 1
496 |  |  |  |  | 1
497 |  |  |  |  | 1
498 |  |  |  |  | 1
499 |  |  |  |  | 1
500 |  |  |  |  | 1
501 |  |  |  |  | 1
502 |  |  |  |  | 1
503 |  |  |  |  | 1
504 |  |  |  |  | 1
505 |  |  |  |  | 1
506 |  |  |  |  | 1
507 |  |  |  |  | 1
508 |  |  |  |  | 1
509 | Gilb |  | Suggest to email. |  | 1
510 |  |  |  |  | 1
511 | Gilb |  | Waiting for 509 |  | 1
512 |  |  |  |  | 1
513 |  |  |  |  | 1
514 |  |  |  |  | 1
515 |  |  |  |  | 1
516 |  |  |  |  | 1
517 |  |  |  |  | 1
518 |  |  |  |  | 1
519 |  |  |  |  | 1
520 |  |  |  |  | 1
521 |  |  |  |  | 1
522 |  |  |  |  | 1
523 |  |  |  |  | 1
524 |  |  |  |  | 1
525 |  |  |  |  | 1
526 |  |  |  |  | 1
527 |  |  |  |  | 1
528 | Barr |  | Discuss 1/23 Nees to write new text |  | 1
529 |  |  |  |  | 1
530 |  |  |  |  | 1
531 |  |  |  |  | 1
532 |  |  |  |  | 1
533 |  |  |  |  | 1
534 |  |  |  |  | 1
535 |  |  |  |  | 1
536 |  |  |  |  | 1
537 |  |  |  |  | 1
538 |  |  |  |  | 1
539 |  |  |  |  | 1
540 |  |  |  |  | 1
541 |  |  |  |  | 1
542 |  |  |  |  | 1
543 |  |  |  |  | 1
544 |  |  |  |  | 1
545 |  |  |  |  | 1
546 | Odman |  | 1/24, Write reject text |  | 1
547 |  |  |  |  | 1
548 |  |  |  |  | 1
549 |  |  |  |  | 1
550 |  |  |  |  | 1
551 |  |  |  |  | 1
552 |  |  |  |  | 1
553 |  |  |  |  | 1
554 |  |  |  |  | 1
555 |  |  |  |  | 1
556 |  |  |  |  | 1
557 |  |  |  |  | 1
558 |  |  |  |  | 1
559 |  |  |  |  | 1
560 |  |  |  |  | 1
561 |  |  |  |  | 1
562 |  |  |  |  | 1
563 |  |  |  |  | 1
564 |  |  |  |  | 1
565 |  |  |  |  | 1
566 |  |  |  |  | 1
567 |  |  |  |  | 1
568 |  |  |  |  | 1
569 |  |  |  |  | 1
570 |  |  |  |  | 1
571 |  |  |  |  | 1
572 |  |  |  |  | 1
573 |  |  |  |  | 1
574 |  |  |  |  | 1
575 |  |  |  |  | 1
576 |  |  |  |  | 1
577 |  |  |  |  | 1
578 |  |  |  |  | 1
579 |  |  |  |  | 1
580 |  |  |  |  | 1
581 |  |  |  |  | 1
582 |  |  |  |  | 1
583 |  |  |  |  | 1
584 |  |  |  |  | 1
585 |  |  |  |  | 1
586 | Gilb |  | Waiting for 509 |  | 1
587 |  |  |  |  | 1
588 |  |  |  |  | 1
589 |  |  |  |  | 1
590 |  |  |  |  | 1
591 |  |  |  |  | 1
592 |  |  |  |  | 1
593 |  |  |  |  | 1
594 |  |  |  |  | 1
595 |  |  |  |  | 1
596 |  |  |  |  | 1
597 |  |  |  |  | 1
598 |  |  |  |  | 1
599 |  |  |  |  | 1
600 |  |  |  |  | 1
601 |  |  |  |  | 1
602 |  |  |  |  | 1
603 |  |  |  |  | 1
604 |  |  |  |  | 1
605 |  |  |  |  | 1
606 |  |  |  |  | 1
607 |  |  |  |  | 1
608 |  |  |  |  | 1
609 |  |  |  |  | 1
610 |  |  |  |  | 1
611 |  |  |  |  | 1
612 |  |  |  |  | 1
613 |  |  |  |  | 1
614 |  |  |  |  | 1
615 |  |  |  |  | 1
616 |  |  |  |  | 1
617 |  |  |  |  | 1
618 |  |  |  |  | 1
619 |  |  |  |  | 1
620 |  |  |  |  | 1
621 |  |  |  |  | 1
622 |  |  |  |  | 1
623 |  |  |  |  | 1
624 |  |  |  |  | 1
625 |  |  |  |  | 1
626 |  |  |  |  | 1
627 |  |  |  |  | 1
628 |  |  |  |  | 1
629 |  |  |  |  | 1
630 |  |  |  |  | 1
631 |  |  |  |  | 1
632 |  |  |  |  | 1
633 |  |  |  |  | 1
634 |  |  |  |  | 1
635 |  |  |  |  | 1
636 |  |  |  |  | 1
637 |  |  |  |  | 1
638 |  |  |  |  | 1
639 |  |  |  |  | 1
640 |  |  |  |  | 1
641 |  |  |  |  | 1
642 |  |  |  |  | 1
643 |  |  |  |  | 1
644 |  |  |  |  | 1
645 |  |  |  |  | 1
646 |  |  |  |  | 1
647 |  |  |  |  | 1
648 |  |  |  |  | 1
649 |  |  |  |  | 1
650 |  |  |  |  | 1
651 |  |  |  |  | 1
652 |  |  |  |  | 1
653 |  |  |  |  | 1
654 |  |  |  |  | 1
655 |  |  |  |  | 1
656 |  |  |  |  | 1
657 |  |  |  |  | 1
658 |  |  |  |  | 1
659 |  |  |  |  | 1
660 |  |  |  |  | 1
661 |  |  |  |  | 1
662 |  |  |  |  | 1
663 |  |  |  |  | 1
664 |  |  |  |  | 1
665 |  |  |  |  | 1
666 |  |  |  |  | 1
667 |  |  |  |  | 1
668 |  |  |  |  | 1
669 |  |  |  |  | 1
670 |  |  |  |  | 1
671 |  |  |  |  | 1
672 |  |  |  |  | 1
673 |  |  |  |  | 1
674 |  |  |  |  | 1
675 |  |  |  |  | 1
676 |  |  |  |  | 1
677 | Shvodian |  | Due 1/24, How do we handle SIFS/MIFS |  | 1
678 |  |  |  |  | 1
679 |  |  |  |  | 1
680 |  |  |  |  | 1
681 |  |  |  |  | 1
682 | Shvodian |  | Resolve with CID 677 |  | 1
683 |  |  |  |  | 1
684 |  |  |  |  | 1
685 |  |  |  |  | 1
686 |  |  |  |  | 1
687 |  |  |  |  | 1
688 |  |  |  |  | 1
689 |  |  |  |  | 1
690 |  |  |  |  | 1
691 |  |  |  |  | 1
692 |  |  |  |  | 1
693 |  |  |  |  | 1
694 |  |  |  |  | 1
695 |  |  |  |  | 1
696 |  |  |  |  | 1
697 |  |  |  |  | 1
698 |  |  |  |  | 1
699 |  |  |  |  | 1
700 |  |  |  |  | 1
701 |  |  |  |  | 1
702 |  |  |  |  | 1
703 |  |  |  |  | 1
704 |  |  |  |  | 1
705 |  |  |  |  | 1
706 |  |  |  |  | 1
707 |  |  |  |  | 1
708 |  |  |  |  | 1
709 |  |  |  |  | 1
710 |  |  |  |  | 1
711 |  |  |  |  | 1
712 |  |  |  |  | 1
713 |  |  |  |  | 1
714 |  |  |  |  | 1
715 |  |  |  |  | 1
716 |  |  |  |  | 1
717 |  |  |  |  | 1
718 |  |  |  |  | 1
719 |  |  |  |  | 1
720 |  |  |  |  | 1
721 |  |  |  |  | 1
722 |  |  |  |  | 1
723 |  |  |  |  | 1
724 |  |  |  |  | 1
725 |  |  |  |  | 1
726 |  |  |  |  | 1
727 |  |  |  |  | 1
728 |  |  |  |  | 1
729 |  |  |  |  | 1
730 |  |  |  |  | 1
731 |  |  |  |  | 1
732 |  |  |  |  | 1
733 |  |  |  |  | 1
734 |  |  |  |  | 1
735 |  |  |  |  | 1
736 |  |  |  |  | 1
737 |  |  |  |  | 1
738 |  |  |  |  | 1
739 |  |  |  |  | 1
740 |  |  |  |  | 1
741 |  |  |  |  | 1
742 |  |  |  |  | 1
743 |  |  |  |  | 1
744 |  |  |  |  | 1
745 |  |  |  |  | 1
746 |  |  |  |  | 1
747 |  |  |  |  | 1
748 |  |  |  |  | 1
749 |  |  |  |  | 1
750 |  |  |  |  | 1
751 |  |  |  |  | 1
752 |  |  |  |  | 1
753 |  |  |  |  | 1
754 |  |  |  |  | 1
755 |  |  |  |  | 1
756 |  |  |  |  | 1
757 |  |  |  |  | 1
758 |  |  |  |  | 1
759 |  |  |  |  | 1
760 |  |  |  |  | 1
761 |  |  |  |  | 1
762 |  |  |  |  | 1
763 |  |  |  |  | 1
764 |  |  |  |  | 1
765 |  |  |  |  | 1
766 |  |  |  |  | 1
767 |  |  |  |  | 1
768 |  |  |  |  | 1
769 | Gilb |  | Waiting for 509 |  | 1
770 |  |  |  |  | 1
771 |  |  |  |  | 1
772 |  |  |  |  | 1
773 |  |  |  |  | 1
774 |  |  |  |  | 1
775 |  |  |  |  | 1
776 |  |  |  |  | 1
777 |  |  |  |  | 1
778 |  |  |  |  | 1
779 |  |  |  |  | 1
780 |  |  |  |  | 1
781 |  |  |  |  | 1
782 |  |  |  |  | 1
783 |  |  |  |  | 1
784 |  |  |  |  | 1
785 |  |  |  |  | 1
786 |  |  |  |  | 1
787 |  |  |  |  | 1
788 |  |  |  |  | 1
789 |  |  |  |  | 1
790 |  |  |  |  | 1
791 |  |  |  |  | 1
792 |  |  |  |  | 1
793 |  |  |  |  | 1
794 |  |  |  |  | 1
795 |  |  |  |  | 1
796 |  |  |  |  | 1
797 |  |  |  |  | 1
798 |  |  |  |  | 1
799 |  |  |  |  | 1
800 |  |  |  |  | 1
801 |  |  |  |  | 1
802 |  |  |  |  | 1
803 |  |  |  |  | 1
804 |  |  |  |  | 1
805 |  |  |  |  | 1
806 |  |  |  |  | 1
807 |  |  |  |  | 1
808 |  |  |  |  | 1
809 |  |  |  |  | 1
810 |  |  |  |  | 1
811 |  |  |  |  | 1
812 |  |  |  |  | 1
813 |  |  |  |  | 1
814 |  |  |  |  | 1
815 |  |  |  |  | 1
816 |  |  |  |  | 1
817 |  |  |  |  | 1
818 |  |  |  |  | 1
819 |  |  |  |  | 1
820 |  |  |  |  | 1
821 |  |  |  |  | 1
822 |  |  |  |  | 1
823 |  |  |  |  | 1
824 |  |  |  |  | 1
825 |  |  |  |  | 1
826 |  |  |  |  | 1