## Sheet1
Deffered comments
|  | 2 | to be resolved toghether with 336
|  | 55 | to be resolved toghether with 336
|  | 65 | to be resolved toghether with 336
|  | 72 | to be resolved toghether with 336
|  | 79 | to be resolved toghether with 336
|  | 80 | to be resolved toghether with 336
|  | 81 | to be resolved toghether with 336
|  | 83 | to be resolved toghether with 336
|  | 84 | Ken fixing the text
|  | 85 | to be resolved toghether with 336
|  | 86 | to be resolved toghether with 336
|  | 87 | to be resolved toghether with 336
|  | 89 | to be resolved toghether with 336
|  | 194 | to be resolved toghether with 343L and 344L
Action Items and Ad-Hoc
Comment |  | Responsible |  | Item
6 |  | Mariana |  | define the CX-Frame in definitions
6 |  | David |  | Ad-Hoc to improve the definition of the Coordinated CX mechamism - David
Note: The existing definition does not include the CXCC and the 4 frame structure, which do not need messages
16, 18 |  | Shulan |  | Ad-Hoc on messages related to the detection of bursty (802.11) systems - Shulan
17, 22 |  | John |  | Change the text wording of BS_CCID_RSP and BS_CCID_REQ message sections
23 |  | John |  | Specifically identify CCID as message ID
30 |  | Ken |  | Refer DCS in 15.3.2
38 |  | Paul |  | Implement Ken's sugestion on orderly transition
39, 48 |  | Paul |  | Provide clarifications related to fig. h1
40 |  | Paul |  | Fix the figure h2 and the text
41 |  | Paul |  | Fix the figure h2 and the text to implement the accepted remedy
50 |  | Paul |  | Replace all instances of "backup channels" with "alternative channels"
53 |  | Ken |  | Find a name more suitable for the "Uncoordinated Protocol"
69 |  | Paul |  | Define energy level measurement (power and measurement duration), duration of the slot, decission conditions and CMA/CCA issue
77 |  | Ken |  | Maybe look at a short Message to avoid the IE usage
78 |  | Shulan |  | Define the DIUC used in the DL-CXZ and the needed text
92, 144, 333 |  | Mariana |  | Ad-Hoc to establish the Mandatory profile
99, 94 |  | Xuyong |  | Either define numbers or delete the different interference thresholds
100 |  | Xuyong |  | Define the conditions for the detection threshold, other conditions for probability 0.9
113, 119, 122, 125, 120 |  | Mariana |  | Re-make 15.1.3
115 |  | David |  | Provide text
129 |  | David |  | Fix the usage of "master sub-frame" and "master frame" and "master frame allocation"
133 |  | Mariana |  | Better explain the Secondary Sync
157 |  | Mariana |  | Study the support of weather radars by CXCC
158, 215 |  | Mariana |  | Add frequency keying for OFDMA
167, 174, 202 |  | Xuyong |  | Increase the spectral efficiency of CSI
170 |  | Mariana |  | Describe the sub-channel 4 operation
192 |  | John |  | Use the comment to improve the text in 15.3.3
196 |  | Shulan |  | Continue the Ad-Hoc on CMI and add the reciprocal interference new clause (15.3.7)
210 |  | Xuyong |  | Check the algorithm in 15.3.4.4 and modify it if needed
213 |  | Xuyong |  | Clarify what is the "known occupier"
218 |  | Mariana |  | Fig. h46 needs consolidation relative to channel boundary
226 |  | Mariana |  | Define Radio Signaling
228, 231 |  | Mariana |  | Ad-Hoc on Radio Signatures to define MAC header to include BSID in down-link and SSID in up-link; in UL shall not be used preambles in the OFDMA mode
234 |  | Mariana |  | Check the GAP interval scheduling in 15.5
237 |  | Xuyong |  | Up-date fig. h47 according to the comment
244 |  | Shulan |  | Clarify the backward compatibility; give an example
251 |  | Mariana |  | Verify if there are legacy zones including preambles
214 |  | Xuyong |  | write the text on backoff window such to understand it - use short sentences.
256 |  | Mariana |  | Fix the text on page 105
264, 266 |  | Mariana |  | Check if the DL CX Zone is needed
275 |  | Mariana |  | Define the MAC message related to 802.11 detection
278 |  | Mariana |  | Ad-Hoc: SS working in the 3.7GHz, new licensed European allocation, should be able to work also in 3.7GHz with no SW changes.
281 |  | Mariana |  | Clarify in CX-DL-MAP or CX-UL_MPA message the indication for Scheduled Listen Before Talk opportunities
282 |  | Mariana |  | Correct the figure h55. Remove the "CXCPB" indication and add an indication for the contention window.
298 |  | Harry |  | Fix the parameters in table h9
300, 302 |  | John |  | Check the TLVs types 67 and 70 in h9 and add GPS location to SSURF
303, 304 |  | John |  | Fix or delete message 15.5.1.21 and 15.5.1.22
317 |  | David |  | Aquire the CXP UDP port number - work with IETF through Motorola and David Johnston - the 802.16 Liaison Officer to IETF
324 |  | Mariana |  | Add 5.9GHz to Table h45
325 |  | John |  | Check the GPS format in Rev 2 and harmonize the text in 16h
327 |  | Xuyong, Shulan, David, John, Mariana |  | Replace "will" in the draft with shall or should
330 |  | John |  | Format 15.5.1.17 SS_CCID_IND message and 15.5.1.18 SS_CCID_RSP message according to the format in 15.5 and change the title to more general sounding
334 |  | Xuyong |  | Reflect with text in standard for resource scheduling using the interf inferce information provided by SS
336 |  | Paul |  | Provide solutions for the open issues in comment 336
Profiles |  |  |  |  | Mandatory
6.4.4.2 CX with SSU when relevant |  |  |  |  | 6 | of 6
6.4.2.3.2 DCS (passive channel selection) |  |  |  |  | 6
6.4.2.3.7 UCP |  |  |  |  | 1
( MAC messages (6.3.xx))
15.2 Provisionning (GPS sync) |  |  |  |  | 4
15.3.1 CXCC (timming) |  |  |  |  | 4
| sub-chann1 (sync and SSU) |  |  |  | 5
| sub-chann 2 (CMI) |  |  |  | 5
| sub-chann 3 (secondary sync) |  |  |  | 2
| sub-chann4 (Radio sig) |  |  |  | 1
| sub-chann 5 (CSI) |  |  |  | 1
15.3.2 (candidate channel and Master fr. Selection) |  |  |  |  | 5
15.4.1 (CX Frame) |  |  |  |  | 5
| CX-CBP |  |  |  | 4
15.4.2 | Channel optimization |  |  |  | 1
15.4.3 | Master frame optimization |  |  |  | 1
15.4.4 | Interference control |  |  |  | 0
15.4.5 | Token Protocol |  |  |  | 1
15.5 | CXP |  |  |  | 2
15.6 | Intersystem communication |  |  |  | 2
15.8 | Network -based identification of SSU |  |  |  | 1