IEEE 802.16 ITU-R Liaison Group Workplan

The following table represents a workplan for the IEEE 802.16 ITU-R Liaison Group based on ITU-R and IEEE events relevant to the IEEE 802.16 Working Group.

Note: The Annexes provide more details on the IMT-Advanced work items, which are highlighted.

| Group/Event | # | Start | # days | End | Location | Actions/Comments |
| --- | --- | --- | --- | --- | --- | --- |
| IEEE 802.18 |  | 8-Sep-08 | 5 | 12-Sep-08 | Kona, HI, USA |  |
| IEEE 802.16 | 57 | 16-Sep-08 | 4 | 19-Sep-08 | Kobe, Japan | - Need for ITU-R Liaison Group meeting in September 2008 is not currently anticipated. - Identify acting chair of ITU-R Liaison Group for November meeting. - Prepare contribution for the IMT-Advanced workshop |
|  |  |  |  |  |  | - No time for IEEE 802 EC correspondence activity to approve contribution(s) to ITU-R. |
| WiMAX Forum |  | 22-Sep-08 | 5 | 26-Sep-08 | Macao, China |  |
| WP 5D contr. Due: |  |  |  | 1-Oct-08 |  |  |
| IMT-Adv Workshop |  | 07-Oct-08 |  | 07-Oct-08 | Seoul, Korea | - Presentation by José Costa |
| ITU-R WP 5D | 3 | 08-Oct-08 | 8 | 15-Oct-08 | Seoul, Korea |  |
| WP 5A contr. Due: |  |  |  | 21-Oct-08 |  |  |
| ITU-R WP 5A | 2 | 28-Oct-08 | 10 | 06-Nov-08 | Geneva, CH |  |
| SG5 contr. Due: |  |  |  | 3-Nov-08 |  |  |
| ITU-R SG5 | 2 | 10-Nov-08 | 2 | 11-Nov-08 | Geneva, CH |  |
| IEEE 802.16 | 58 | 10-Nov-08 | 4 | 13-Nov-08 | Dallas, TX | - Plan for the IMT-Advanced submission package development in 2009 - Prepare contribution #1 towards IMT-Advanced indicating intent to submit candidate RIT proposal - Prepare the third contribution on IMT-2000 Rev. 9 - Consider SG 5 results - Prepare more detailed workplan and Timelines for the ITU-R contribution development - Provide comments to 802.18 on the IEEE 802 IMT-Advanced Process |
| IEEE 802.18 |  | 10-Nov-08 | 5 | 14-Nov-08 | Dallas, TX | - Definition of IMT-Advanced submission process in IEEE 802.18 |
| IEEE 802 |  | 10-Nov-08 | 5 | 14-Nov-08 | Dallas, TX | - Definition of IMT-Advanced submission process in IEEE 802, with minimized lead time - Approval of contribution #1 by the EC |
| IEEE 802.16 | 59 | 12-Jan-09 | 4 | 15-Jan-09 | La Jolla, CA, USA | - Review 802-approved contributions from Session #58; if necessary, update and seek approval as replacements. - Issue a call for contributions for TDT, SCT. SPECT. |
| IEEE 802.18 |  | 19-Jan-09 | 5 | 23-Jan-09 | Los Angeles, CA, USA | If necessary, update 802-approved contributions from Session #58. |
| WP 5D contr. Due: |  |  |  | 4-Feb-09 |  | - Deadline for submission of IEEE contributions for WP 5D - Deadline for letters of conveyance for IMT-2000 Rev. 9 |
| WiMAX Forum |  | 5-Feb-09 | 6 | 10-Feb-09 | Orlando, FL, USA |  |
| ITU-R WP 5D | 4 | 10-Feb-09 | 8 | 17-Feb-09 | Geneva, CH | - Present contribution #1 on IMT-Advanced |
| IEEE 802.16 | 60 | 9-Mar-09 | 4 | 12-Mar-09 | Vancouver, BC, Canada | - Prepare contribution #2 on IMT-Advanced - Review input contributions. Prepare preliminary drafts of TDT, SCT, SPECT. - Call for Contributions on simulation package |
| IEEE 802 |  | 9-Mar-09 | 5 | 13-Mar-09 | Vancouver, BC, Canada | - Approval of IMT-Advanced contribution #2 by the EC |
| IEEE 802.16 | 61 | 4-May-09 | 4 | 7-May-09 | Cairo, Egypt | - Review 802-approved contributions from Session #58; if necessary, update and seek approval as replacements. - Initiate development of final submission package towards IMT-Advanced - Update drafts of TDT, SCT, SPECT for the final submission - Call for Contributions for LBT and PCT including supporting simulations |
| IEEE 802.18 |  | 11-May-09 | 5 | 15-May-09 | Montreal, Canada | If necessary, update 802-approved contributions from Session #58. |
| WP 5A contr. Due: |  |  |  | 11-May-09 |  |  |
| ITU-R WP 5A |  | 18-May-09 | 12 | 27-May-09 | Geneva, CH |  |
| ITU-R SG 5: deadline for M.1457 |  | Date unknown |  |  |  | -certification of references and transposition for M.1457-9 |
| ITU-R SG 5 |  | 29-May-09 | 1 | 29-May-09 | Geneva, CH | -M.1457-9 approved |
| WP 5D contr. Due: |  |  |  | 3-Jun-09 |  | - Deadline for submission of IEEE contributions for WP 5D |
| ITU-R WP 5D | 5 | 10-Jun-09 | 8 | 17-Jun-09 | [TBD] | - Present contribution #2 on IMT-Advanced |
| IEEE 802.16 | 62 | 13-Jul-09 | 5 | 17-Jul-09 | San Francisco, CA, USA | - Review input contributions for the LBT and PCT - Draft submission package for IMT-Advanced |
| IEEE 802.18 |  | 13-Jul-09 | 5 | 17-Jul-09 | San Francisco, CA, USA | - Review draft final submission. |
| IEEE 802 |  | 13-Jul-09 | 5 | 17-Jul-09 | San Francisco, CA, USA |  |
| IEEE 802.16 | 63 | 31-Aug-09 | 5 | 3-Sep-09 | Korea | - Conclude final submission package including final self evaluation for IMT-Advanced |
| IEEE 802.18 contr. Due: |  |  |  | 4-Sep-09 |  | - Deadline for final submission for IMT-Advanced |
| IEEE 802.18 |  | 21-Sep-09 |  | 25-Sep-09 | Kona, HI, USA | - Delegation from 802.16 expected to attend for review and approval of IMT-Advanced proposal. |
| WP 5D contr. Due: |  |  |  | 7-Oct-09 |  |  |
| ITU-R WP 5D | 6 | 14-Oct-09 | 8 | 21-Oct-09 | [Germany] | - Present final submission for IMT-Advanced |

Note: Regarding IMT-Advanced deadlines in IEEE 802, the above timeline assumes the process according to IEEE 802.18 document IEEE 802.18-08-0058r6:

< https://mentor.ieee.org/802.18/file/08/18-08-0058-06-0000-ieee-802-18-imt-advanced-review-process.ppt>.

### Annex 1: IMT-Advanced Candidate RIT Components

The following are the components that have been identified as required as part of the IMT-Advanced Candidate RIT final submission package or Step 3 Contribution per the IMT-Advanced schedule [1] and Rec. [IMT.REST]:

- Technology Description Template (TDT)

- Link Budget Template (LBT)

- Self Evaluation:

  - Services Compliance Template (SCT)

  - Spectrum Compliance Template (SPECT)

  - Performance Compliance Template (PCT)

- Indication of ITU-R Patent Policy Compliance

### Annex 2: IEEE Project 802.16m IMT-Advanced Candidate RIT Timelines

The following figure highlights the development timeline for all the components of the IEEE 802.16m IMT-Advanced Candidate RIT proposal taking into account the TGm schedule [2].

### References:

[1] IMT-Advanced Schedule <http://www.itu.int/ITU-R/study-groups/docs/imt-advanced-schedule.doc>

[2] IEEE 802.16m-07/001 (“Work Plan for Development of IEEE P802.16m Draft Standard”)  <http://ieee802.org/16/tgm/#07_001>.