**IEEE 802.16 ITU-R Liaison Group Workplan**

The following table represents a workplan for the IEEE 802.16 ITU-R Liaison Group for 2011 and beyond based on ITU-R and IEEE events relevant to the IEEE 802.16 Working Group. For historical information related to 2010 and prior, please see L802.16-08/058r5 and L802.16-10/0017r7.

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Group/Event** | **#** | **Start** | **End** | **Location** | **Actions** | **Result of each meeting** |
| IEEE 802.16  | 71 | 10-Jan-2011 | 13-Jan-2011 | Taipei, Taiwan | * Further develop contribution for IMT.RSPEC (Overview in B.1 & titles and synopses of the GCS in B.2)
 | Done(L802.16-10/0113d9) |
| * Send LS to ARIB, TTA and the WiMAX Forum on the status of preparations for submission towards IMT.RSPEC
 | Done(L802.16-10/0129r1) |
| * Develop contribution to WP 5D on M.1224 (to provide Abbreviations)
 | Done(L802.16-10/00132d1) |
| * Develop plan for the March 2011 WATO meeting
 | Done(L802.16-10/0130) |
| * Prepare input material for WP 5D Workshop on IMT for the Next Decade (Apr-Jul 2011)
 | Withdrawn |
| IEEE 802.18 |  | 16-Jan-2011 | 21-Jan-2011 | Los Angeles, CA, USA | * No action
 |  |
| IEEE 802.16 | 72 | 14-Mar-2011 | 17-Mar-2011 | Singapore | * Develop and finalize M.1457-11 Meeting X contribution
 | Done(L802.16-11/0009r1) |
| * Finalize contribution on IMT.RSPEC (Overview in B.1 & titles and synopses of the GCS in B.2)
 | Done(L802.16-11/0010r2) |
| * Finalize contribution to WP 5D on M.1224 (to provide Abbreviations)
 | Done(L802.16-11/0012r3) |
| * Send LS to ARIB, TTA and the WiMAX Forum on the status of preparations for submission towards IMT.RSPEC
 | Done(L802.16-11/0018r1) |
| * Develop contributions to WP 5A on topics such as M2M, CRS, etc.
 | Deferred |
| WATO meeting | 1 | 15-Mar-2011 | 15-Mar-2011 | Singapore | * Agenda: IEEE L802.16-10/0130
 | Done(L802.16-11/0015) |
| IEEE 802.18 |  | 14-Mar-2011 | 17-Mar-2011 | Singapore | * Review M.1457-11 Meeting X contribution
 | Done(L802.16-11/0009r1) |
| * Review contribution on IMT.RSPEC
 | Done(L802.16-11/0010r2) |
| * Review any other ITU-R contributions
 | Done(L802.16-11/0012r3) |
| IEEE 802 |  | 14-Mar-2011 | 17-Mar-2011 | Singapore | * Approve M.1457-11 Meeting X contribution
 | Done(L802.16-11/0009r1) |
| * Approve contribution on IMT.RSPEC
 | Done(L802.16-11/0010r2) |
| * Approve any liaison and/or other contributions
 | Done(L802.16-11/0012r3) |
| IEEE-SA |  | 30-Mar-2011 | 30-Mar-2011 |  | * Submit Certification B and GCS to ITU-R
 | Done(L802.16-10/0090r6) |
| ITU-R WP 5D | 10 | 6-Apr-2011 | 13-Apr-2011 | Sweden | * Present IEEE contributions including on IMT.RSPEC and M.1224
 | Done(L802.16-11/0010r2, L802.16-11/0012r3) |
| IEEE 802.18 |  | 8-May-2011 | 13-May-2011 | Palm Springs, CA, USA | * No action
 |  |
| IEEE 802.16 | 73 | 16-May-2011 | 19-May-2011 | Lake Louise, Alberta, Canada | * Review the outcome of WP 5D #10
 | Done |
| * Prepare draft Certification C
 | Done(L802.16-11/0028d0) |
| * Develop plan for the July 2011 WATO meeting
 | Done(L802.16-11/0027r1) |
| ITU-R WP 5A | 7 | 13-Jun-2011 | 22-Jun-2011 | Geneva, Switzerland | * No action
 |  |
| ITU-R WP 5D | 11 | 7-Jul-2011 | 14-Jul-2011 | USA | * Present M.1457-11 Meeting X contribution
 | Done |
| IEEE 802.16 | 74 | 18-Jul-2011 | 21-Jul-2011 | San Francisco, USA | * Review the outcome of WP 5D #11
 | Done |
| * Finalize Certification C
 | Done(L802.16-11/0028r1) |
| * Develop and finalize M.1457-11 Meeting X+1 contribution (incl. IMT-2000 roadmap update for OFDMA TDD WMAN)
 | Done(L802.16-11/0043r1, L802.16-11/0039r1) |
| * Review the outcome of WP 5A #7 (on M2M etc.)
 | Done |
| * Develop and finalize contribution to WP 5A on M2M
 | Done(L802.16-11/0045r1) |
| * Develop and finalize contribution to WP 5D on M.1224
 | Done(L802.16-11/0042) |
| WATO meeting | 2 | 19-Jul-2011 | 19-Jul-2011 | San Francisco, USA | * Agenda: IEEE L802.16-11/0027r1
 | Done(L802.16-11/0040) |
| IEEE 802.18 |  | 18-Jul-2011 | 21-Jul-2011 | San Francisco, USA | * Review M.1457-11 Meeting X+1 contribution
 | Done(L802.16-11/0043r1) |
| * Review any other ITU-R contributions
 | Done(L802.16-11/0042, L802.16-11/0045r1, L802.16-11/0039r1) |
| IEEE 802 |  | 18-Jul-2011 | 21-Jul-2011 | San Francisco, USA | * Approve M.1457-11 Meeting X+1 contribution
 | Done(L802.16-11/0043r1) |
| * Approve any liaison and/or other contributions
 | Done(L802.16-11/0042, L802.16-11/0045r1, L802.16-11/0039r1) |
| IEEE 802.16 | 75 | 19-Sep-2011 | 22-Sep-2011 | Bangkok, Thailand | * Develop and finalize transposition references
 | Done(L802.16-11/0057r1) |
| * Develop M.1457-11 Meeting X+2 contribution
 | Done(L802.16-11/0059d0)[Note: WG to form an ad-hoc group on this particular topic] |
| * Prepare for/hold/review the CRS tutorial
 |  |
| IEEE 802.18 |  | 18-Sep-2011 | 23-Sep-2011 | Okinawa, Japan |  |  |
| IEEE-SA |  | 21-Sep-2011 | 21-Sep-2011 |  | * Submit Certification C and transposition references to ITU-R
 | Done(L802.16-11/0028r1, L802.16-11/0057r1) |
| ITU-R WP 5D | 12 | 12-Oct-2011 | 19-Oct-2011 | Goa, India | * Present IEEE contributions including M.1457-11 Meeting X+1 contribution
 |  |
| IEEE 802.16 | 76 | 7-Nov-2011 | 10-Nov-2011 | Atlanta, USA | * Further develop M.1457-11 Meeting X+2 contribution
 |  |
| * Follow up CRS discussion

Note: To be addressed jointly with PPC |  |
| IEEE 802.18 |  | 7-Nov-2011 | 10-Nov-2011 | Atlanta, USA | * Review any ITU-R contributions
 |  |
| IEEE 802 |  | 7-Nov-2011 | 11-Nov-2011 | Atlanta, USA | * Approve any liaison and/or other contributions
 |  |
| ITU-R WP 5A | 8 | 8-Nov-2011 | 18-Nov-2011 | Geneva, Switzerland | * Present any IEEE contributions
 |  |
| ITU-R SG 5 |  | 21-Nov-2011 | 22-Nov-2011 | Geneva, Switzerland | * Present any IEEE contributions
 |  |
| IEEE 802.16 | 77 | 16-Jan-2012 | 19-Jan-2012 | Jacksonville, USA | * Further develop M.1457-11 Meeting X+2 contribution
 |  |
| IEEE 802.18 |  | 16-Jan-2012 | 19-Jan-2012 | Jacksonville, USA |  |  |
| ITU-R RA-12 |  | 16-Jan-2012 | 20-Jan-2012 | Geneva, Switzerland | * No action
 |  |
| ITU-R WRC-12 |  | 23-Jan-2012 | 17-Feb-2012 | Geneva, Switzerland | * No action
 |  |
| IEEE 802.16 | 78 | 12-Mar-2012 | 15-Mar-2012 | Waikoloa, USA | * Finalize M.1457-11 Meeting X+2 contribution

Note: Expect to include [Draft] IEEE Std 802.16.1 |  |
| * [Develop and finalize IMT.RSPEC-1 Meeting Y contribution]
 |  |
| IEEE 802.18 |  | 12-Mar-2012 | 15-Mar-2012 | Waikoloa, USA | * Review M.1457-11 Meeting X+2 contribution
 |  |
| * [Review IMT.RSPEC-1 Meeting Y contribution]
 |  |
| * Review any other ITU-R contributions
 |  |
| IEEE 802 |  | 12-Mar-2012 | 16-Mar-2012 | Waikoloa, USA | * Approve M.1457-11 Meeting X+2 contribution
 |  |
| * [Approve IMT.RSPEC-1 Meeting Y contribution]
 |  |
| * Approve any liaison and/or other contributions
 |  |
| ITU-R [WP 5D] | [13] | [23-Apr-2012] | [27-Apr-2012] | TBD | * Present M.1457-11 Meeting X+2 contribution
 |  |