## Slide 1
Project | IEEE 802.20 Working Group on Mobile Broadband Wireless Access <http://grouper.ieee.org/groups/802/20/> | 
Title | Schedule Considerations | 
Date Submitted | 2004-01-12 | 
Source(s) | Robert Love LAN Connect Consultants 7105 Leveret Circle Raleigh, NC 27615 | Voice: (919) 848-6773 Email: rdlove@ieee.org
Re: | 802.20 Schedule and Work Plan | 
Abstract | Discussion of the issues that need addressing and proposed schedule. | 
Purpose | Develop 802.20 schedule that we are all working toward | 
Notice | This document has been prepared to assist the IEEE 802.20 Working Group. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. | 
Release | The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.20. | 
Patent Policy | The contributor is familiar with IEEE patent policy, as outlined in Section 6.3 of the IEEE-SA Standards Board Operations Manual <http://standards.ieee.org/guides/opman/sect6.html#6.3> and in Understanding Patent Issues During IEEE Standards Development <http://standards.ieee.org/board/pat/guide.html>. | 
IEEE C802.20-04/007a

## Slide 2: 802.20 Schedule Considerations
Robert D.Love
rdlove@ieee.org
LAN Connect Consultants
C802.20-04/007a

## Slide 3: Present Status
We’re behind schedule & getting further behind
  802.17 had first plenary meeting in March and cut off new proposals that November
  802.20 had first plenary meeting in March and has not even established a cutoff date for proposed solutions
The market has present needs our standard should be addressing
Proposed solutions are “waiting in the wings”
  “The technical feasibility of such a system has been demonstrated by proprietary systems currently in deployment and trial.” (From our 5 Criteria charts)
We are hotly debating details of the Requirements document
No proposals have been forwarded since the approval of our PAR

## Slide 4: Report Card
N Needs Improvement
How do we improve?… We need a paradigm shift in how we address our work
  Use Requirements Document and Evaluation Criteria as guides, but do not hold up progress, requiring them to be polished
  Respond to the urgency of the marketplace and of the opportunity
  Establish a schedule driven by what can be done if we focus on urgency
  Break up work so segments can proceed in parallel
  Require detailed proposals in earliest possible timeframe

## Slide 5: Proposed Schedule
Finalize Requirements Document March 2004
  Call For Proposals Issued following March meeting (Proposals to be submitted in May and July)
Cutoff for new proposals July 2004
First round evaluation and simulation of proposals through September 2004 interim meeting
Second round evaluation Sept - Nov 2004
Choose proposals to be incorporated November 2004
1st draft out for 30 day comment January 31, 2005 (assumes January 10 - 14 interim meeting with two weeks to prepare the draft).

## Slide 6: First Action Steps
Discuss this schedule now
Limit schedule discussion through creation of first draft
Informal meetings this week to develop consensus
Vote on proposed schedule by end of Vancouver meeting
Carry results of vote to email discussion and for confirmation in March by WG vote