## Slide 1
Project | IEEE 802.20 Working Group on Mobile Broadband Wireless Access <http://grouper.ieee.org/groups/802/20/> | 
Title | Proposed Work Plan and Project Schedule | 
Date Submitted | 2004-03-11 | 
Source(s) | Mark Klerer Joanne Wilson Steve Dennett | Voice: +1 908-997-2069 Fax: +1 908-997-2069 Email: klerer@flarion.com Voice: 202-669-4006 Fax: 408-428-9083 Email: joanne@arraycomm.com Voice: Fax: Email: Steve.Dennett@Nextel.com
Re: | 802.20 Work Plan | 
Abstract | Proposed Work Plan and Project Schedule for 802.20. | 
Purpose | For discussion and adoption. | 
Notice | This document has been prepared to assist the IEEE 802.20 Working Group. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. | 
Release | The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.20. | 
Patent Policy | The contributor is familiar with IEEE patent policy, as outlined in Section 6.3 of the IEEE-SA Standards Board Operations Manual <http://standards.ieee.org/guides/opman/sect6.html#6.3> and in Understanding Patent Issues During IEEE Standards Development <http://standards.ieee.org/board/pat/guide.html>. | 
2004-03-11 IEEE C802.20-03/40R1

## Slide 2: IEEE 802.20 Project Development Timeline
Project Launch Process:
  ECSG Approval of PAR/5C September 2002
  Approval of PAR/5C by LMSC Executive Committee Nov 15, 2002
  Approval of PAR by IEEE-SA Board Dec 12, 2002
Stage Setting:
  Initial Membership Meeting March 10-14, 2003
  Finalize Requirements March 15-18, 2004
  Closure on Channel Models March/May 2004
  Closure on Evaluation Criteria May 2004
  Establishment of 802.20 Organizational Substructure May 2004
Specification development
  Call for Proposals May 2004
  Presentation of proposals and simulation results July/September 2004
  First WG Ballot Jan 2005/March 2005
  Second WG Ballot May 2005/July 2005
  Sponsor Ballot Sept 2005/Nov 2005
  Sponsor Recirc Nov 2005/Jan 2006
IEEE-SA Approval Jan 2006/March 2006
  Optimistic Target Date Less optimistic target date

## Slide 3: 802.20 Proposed Standards Development Timeline
2004 |  |  |  |  | 
JUL
JAN
MAR
MAY
JUL
SEP
NOV
JAN
2005 |  |  |  | 
MAR
Requirements
MAY
SEP
NOV
2006 | 
Channel
Evaluation Criteria
Models
Structuring for Progress
Call for Proposals
Proposal Submittals and Evaluation
Further Evaluations and Draft Preparation
Comment Resolution
JAN
MAR
1st WG Ballot
2nd WG Ballot
Comment Resolution/Slip Margin
Sponsor Ballot
Comment Resolution
IEEE-SA Approval