## Slide 1
Project | IEEE 802.20 Working Group on Mobile Broadband Wireless Access <http://grouper.ieee.org/groups/802/20/> | 
Title | Proposed Work Plan and Project Schedule | 
Date Submitted | 2004-04-30 | 
Source(s) | Mark Klerer Joanne Wilson Steve Dennett | Email: klerer@flarion.com Email: joanne@arraycomm.com Email: Steve.Dennett@Nextel.com
Re: | 802.20 Work Plan | 
Abstract | Proposed Work Plan and Project Schedule for 802.20. | 
Purpose | For discussion and adoption. | 
Notice | This document has been prepared to assist the IEEE 802.20 Working Group. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein. | 
Release | The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.20. | 
Patent Policy | The contributor is familiar with IEEE patent policy, as outlined in Section 6.3 of the IEEE-SA Standards Board Operations Manual <http://standards.ieee.org/guides/opman/sect6.html#6.3> and in Understanding Patent Issues During IEEE Standards Development <http://standards.ieee.org/board/pat/guide.html>. | 
2004-03-11 IEEE C802.20-04/57

## Slide 2: IEEE 802.20 Project Development Timeline
Project Launch Process:
  ECSG Approval of PAR/5C September 2002
  Approval of PAR/5C by LMSC Executive Committee Nov 15, 2002
  Approval of PAR by IEEE-SA Board Dec 12, 2002
Stage Setting:
  Initial Membership Meeting March 10-14, 2003
  Closure on Requirements May/July, 2004
  Closure on Channel Models May/July 2004
  Proposal Selection and/or Merge Procedure July/September 2004
  Closure on Evaluation Criteria July 2004
  Establishment of 802.20 Organizational Substructure July 2004
Specification development
  Call for Proposals July 2004
  Presentation of proposals and simulation results September 2004
  Further Presentation, Revisions, Selections and/or Merge November 2004
  Further Revisions, Selections and/or Merges January 2005
  First WG Ballot July 2005
  Second WG Ballot November 2005
  Sponsor Ballot January 2006
  Sponsor Recirc March 2006
IEEE-SA Approval
  Submission to RevCom April 2006
  SA Approval May 2006
  Optimistic Target Date Less optimistic target date

## Slide 3: 802.20 Proposed Standards Development Timeline
2004 |  |  |  |  | 
JUL
JAN
MAR
MAY
JUL
SEP
NOV
JAN
2005 |  |  |  | 
MAR
MAY
SEP
NOV
2006 |  | 
JAN
MAR
Requirements
Channel Models
Evaluation Criteria
Selection and Merge Process Agreements
Call for Proposals
Proposal Submittals and Evaluation
Further Evaluations, Selections and/or Merges and Draft Preparation
Comment Resolution
1st WG Ballot
2nd WG Ballot
Comment Resolution
Sponsor Ballot
Comment Resolution
IEEE-SA Approval
MAY
Sponsor Recirc
Org. Substructure