## Title
| IEEE P802.21 Media Independent Handover | 802.21
Submission
Designator: | doc.: IEEE 802.21
Venue Date: | January 2006
First Author: | Vivek Gupta, 802.21 Editor
Subject: | To-Do List
Full Date: | January 2006
Author(s): | Vivek Gupta
Intel Corporation
2111 NE 25th Avenue, Hillsboro, OR 97124
Phone: 503 712 1754
email: vivek.g.gupta@intel.com
Abstract:
To-Do List to update 802.21 Draft P802.21/D00.04
This is the Editor's internal To Do list to keep track of work items and also to use as a benchmark as to how close we are towards Letter Ballot.
Project IEEE 802.21 Media Independent Handover Services
<http://www.ieee802.org/21/>
Title MEDIA INDEPENDENT HANDOVER
Date Submitted September, 2005
Source(s) Harmonized Section 5 Contribution
21-05-0330-00-0000-To_Do_List
Notice This document has been prepared to assist the IEEE 802.21 Working Group. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
Release The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.21.
Patent Policy The contributor is familiar with IEEE patent policy, as outlined in Section 6.3 of the IEEE-SA Standards Board Operations Manual <http://standards.ieee.org/guides/opman/sect6.html#6.3> and in Understanding Patent Issues During IEEE Standards Development <http://standards.ieee.org/board/pat/guide.html>.

## To-Do List
Title/Task | Description | Action | People | Status
Consider updating Figure 3 on page 19 | This is a very busy picture and is hard to follow. There are other more elaborate figures presented earlier that we could consider using here | Submit updated diagram | Ulises, Vivek | Done
MIH Reference model for 3GPP/3GPP2, sections 5.5.4 and 5.5.5 | Are these reference models correct? Do we really need the MIH_MGMT_SAP and other SAPs shown in this diagram? Primitives for all the SAPs proposed are not described in current draft? How does this match with our strategy to take these updates to 3GPP/3GPP2? | Submit updated Ref models for 3GPP2 | Ulises
Updated Communication Reference Model |  | Consolidated contribution in Nov meeting | Qiabing et al | Done
Update Figure 9 based on changes to other MIH Reference diagrams |  | Figure to be updated once all Ref. models are updated | Editor
Update section 5.6 and include only those SAPs in discussion for which we intend to define primitives. |  | Section already updated based on contribution in Sept. Further updates required due to Cellular Ref models | Editor
Revisit Sections 5.8.2 and 5.8.3 (Amendments to 3GPP/3GPP2) | have we got the right text in this section? | Contributions submitted | Ulises
Figure 11 | Do we need to show both local and peer stacks in this figure? | Submit comments | Editor
Section 6.1.2: Link Synchronous and Link Transmission events | Update the explanation to clarify these events and show how they are different than other events in the list or delete this category if it is duplicate | Updated sections in Nov | Ajoy, Qiabing | Done
Update Figs 14 and 15 | Editorial. Do better rendering an formatting | Comments submitted | Editor
Table-1 Link layer events | Updtae the table. Remove duplicate events or ones that are not really generic in functionality. Do we need to add an entry for Vendor Specific events? | Updated contribution for Nov meeting | Srini, Vivek | Done
Table-2 MIH Commands (section 6.2.5.1) | Are all these commands both local nad remote? Do we really need them in our draft? Are there more commands that need to be added? | Comments from Srini submitted in Sept meeting | Srini | Done
Link Commands (6.2.5.2) | Are there any link commands we need to support? | Submit comments | Vivek | Done
Table-3: Remote MIH Commands | Merge Table 2 and Table 3. Specify which command is remote, which local nad which both. Delete those commands that are out of scope. | More comments from Srini in Sept. Contribution planned for Jan meeting | Srini
Update Figure 21 | GLI, LLI, HLSI may need to be updated with newer terms. |  | Subir, Yoshi, Vivek | Done
Tables 4, 5 and 6 | These need to be updtaed based on how we decide to categorize and organize the different IEs. We need to remove reference to any dynamically changing properties from Information Service in general. This is the only section in draft where all supported IEs are listed. Also describe in what stage of connectivity are each of the different IEs required | Submit updated contribution on all IEs. | Subir, Yoshi, Vivek | Done
Figure 22 | Do we really need this? | Removed | Yoshi | Done
Table-7 | Update/Replace with tables 4,5 and 6 | Comments already submitted in Sept | Yoshi, Subir | Done
Section 6.3.3 | Describe the reasons for having a schema. But also include a case for just TLV based description | Submit a TLV based contribution in Jan | Vivek, Yoshi, Ajoy, kalyan
Section 7.1 | Update with all the SAPs that need to be described in this section. For each media specific SAP specify the plan….does it lead to modification of media specific Reference model, or is it an already existing media specific SAP? How will these SAPs be used/deployed by specific media? | Updated contribution for Nov meeting | Vivek | Done
Include list of primitives for each SAP |  | Done for MIH_SAP, MIH_LINK_SAP | Vivek | Done
Revisit MIH_SME_SAP | Do we have the right primitives? | To do
Update MIH_SAP | Based on revisions to section 6 | Was updated in November.
Update C-SAP, M_SAP, MLME_SAP |  | Contributions in Jan | Ronnie
Section 8 | Update MIH header. Naming for primitives. Include all primitive names. | Contributions submitted in Jan | Eunah, Kalyan, Wolfgang
Annex D: Media Specific Enhancements | Do we need this section? These details are being evolved in separate documents and need to be submitted to other WGs. Do we really need to keep this section in our draft? How do we keep it in synch with these evelving documents? | Sections deleted and reference to appropriate documents already inserted | Editor | Done
Annex C | Do we really need this? | Comments already submitted in Sept | Yoshi | Done
Annex B: MING | There need to be more updates/contributions on how we could really use MING and how it helps with deployment? Otherwise this section may not be all that useful. | Updates submitted | Xiaoyu
Ensure every primitive has appropriate Request, Confirm and Response primitives |  | Comments submitted | Eunah, Vivek
Resolve whether commands/events are local/remote |  | More Contributons submitted in this meeting | Srini
Are IP level parameters like MacAccessRouter etc. available with link layer indications? Need to evaluate for different link layer technologies. |  | To do | Srini, Qiaobing
Registration: MIH services discovery, registration, binding needs to be addressed |  | Initial update submitted | Srini, Benjamin
Handover Flow diagrams | Flow diagrams for MIP, SIP, FMIPv6, etc. |  | All