## Slide 1
IEEE 802.21 MEDIA INDEPENDENT HANDOVER
DCN:21-04-200-00
Title: IEEE 802.21 Down Selection Process
Date Submitted: December 20, 2004
Presented at IEEE 802.21 Reflector
Authors or Source(s):
  Ad hoc Group on Evaluation Criteria
  Abstract: This document summarizes the down-selection process for developing IEEE 802.21 draft specifications.

## Slide 2
  IEEE 802.21 presentation release statements
This document has been prepared to assist the IEEE 802.21 Working Group. It is offered as a basis for discussion and is not binding on the contributing individual(s) or organization(s). The material in this document is subject to change in form and content after further study. The contributor(s) reserve(s) the right to add, amend or withdraw material contained herein.
This contribution is made by the National Institute of Standards and Technology and thus is not subject to copyright in the US. [The contributor grants a free, irrevocable license to the IEEE to incorporate material contained in this contribution, and any modifications thereof, in the creation of an IEEE Standards publication; to copyright in the IEEE’s name any IEEE Standards publication even though it may include portions of this contribution; and at the IEEE’s sole discretion to permit others to reproduce in whole or in part the resulting IEEE Standards publication. The contributor also acknowledges and accepts that this contribution may be made public by IEEE 802.21. Does not apply]
The contributor is familiar with IEEE patent policy, as outlined in Section 6.3 of the IEEE-SA Standards Board Operations Manual <http://standards.ieee.org/guides/opman/sect6.html#6.3> and in Understanding Patent Issues During IEEE Standards Development http://standards.ieee.org/board/pat/guide.html>

## Slide 3
IEEE 802.21 Down Selection Process
The proposed down-selection process addresses the following issues:
giving enough buffer time between presentations in order to work out details and build consensus
providing material to group ahead of time to allow for more thorough review and allow focused discussion
having a rule to sunset unpopular proposals after two trials.
This document describes the procedures and timeline, for proposal presentation and draft text selection.

## Slide 4
After the November 2004 meeting no new proposals will be accepted for presentation in response to the Call For Proposal document #21-04-0151-02
Proposals submitted in November 2004 are presented again in their improved, standalone or harmonized form in the initial Phase, Phase I and Phase II.
Presentations are made available one week prior to presentation time in order to allow for sufficient review time.
Proposals should be accompanied with 1) checklist, 2) MIH call flow, and 3) MIH scope matrix according to templates provided in document #21-04-199-XX for Phase I and Phase II presentations.
Proposals are required to provide draft text at Phase II and make it available for review two weeks prior to presentation time.
Presentation order is random as determined by the Chair
Time allocated to each presentation is evenly distributed among all contributors
Strawpolls may be conducted at the discretion of the Chair at the end of a presentation in order to provide additional feedback on a proposal.
Presentation Procedures

## Slide 5
Timeline
Initial Phase
All proposals submitted in
response to the Call for Proposal
#21-04-0151-02 are presented
Phase I
Harmonized proposals are presented
with more details/ explanatory text
(available 1 wk prior to meeting)
November 2004
Phase II
Harmonized proposals are presented
with Draft Text
(available 2 weeks prior to meeting)
Draft Standard
Text is contributed to
Draft IEEE 802.21
Standard
Motion to be included in standard passes by 75%
Motion fails to get 75%
Proposal is no longer
considered by the group
Evaluation Guidelines
#21-04-0199
Ad hoc group works on evaluation guidelines document
Evaluation criteria used in Phase II down selection
Harmonization
March 2005
May 2005
Harmonization
January 2005
Harmonization
Harmonized proposals are presented
(available 1 wk prior to meeting)

## Slide 6
The down selection is applied in Phase II
Authors provide text for review two weeks prior to presentation
A motion to approve draft text provided by the proposal and make it part of the IEEE 802.21 draft specifications: should pass by 75%
A failed motion on a proposed item, leads to the removal of the proposed item from any further consideration by the group.
Down Selection Process

## Slide 7
All motions are carried out at the end of all presentations
Time allocated for motions is advertised in the opening meeting of each session.
A technical motion at Phase II selection requires 75% to pass
A proposal containing multiple non-overlapping components can lead to multiple motions:
  Authors must indicate at presentation time how many motions they intend to bring forward to the working group.
  The proposal component granularity is defined by either a single entry, an entire row, or entire column in the proposal scope matrix (ref. Doc#21-04-199-00)
Motions for each proposal are voted on separately
Proposals (or components) addressing similar issues are voted on at the same time
  Allow to choose multiple proposals (or components)
  Proposal (or component) with majority vote is selected and should get 75% approval for text inclusion in the draft.
Motion Procedures

## Slide 8
Following each presentation phase, a harmonization effort among proposals addressing similar issues is encouraged.
The evaluation guidelines document # 21-04-199 contains information such as MIH call flow templates, MIH scope matrix, and proposal checklist that should assist in the understanding and the review of proposals.
Harmonization Efforts and Evaluation Guidelines