## Work Items
Line | Area | Dir | Item | Status | Notes / Comment / References | Who | Needed | Points | Change
0 |  |  | % Complete | 80.4% |  | Total Number of items | 139 | 111.75
1 | PHY Layer | Downstream | Downstream PHY Layer | [7 empty] | Status | Descroption | Points | Needed | X
2 |  |  | Downstream TX Block Diagram | D |  |  | X | 1 |  |  | S | baseline starting point, | 0.25
3 |  |  | Reconciliation | N/A | No changes | [5 empty] | B | baseline proposal, | 0.5 | Row Labels | Count of Needed
4 |  |  | 1.6 Gb/s at MAC / PLS service interface in 192 MHz, in baseline channel conditions | D | TD#40: remein_3bn_07_0313.pdf (needs analysis) |  | x | 1 |  |  | D- | in draft, needs work | 0.75 |  | 2
6 |  |  | PCS (transmitting): |  |  |  | h |  |  |  | D | in draft, | 1 | B | 4
7 |  |  | · 64B/66B Encoder / Decoder | D | TD#20 (65b); TD#46: hajduczenia_3bn_04_0513.pdf TD#50 (continuous vector, no split); |  | X | 1 |  |  | D1.0 | Editors create in D1.0 | 1 | D | 68
10 |  |  | · FEC and Data Detector |  | TD#4 (LDPC); TD#47: prodan_3bn_01_0513.pdf; TD#94: hajduczenia_3bn_01a_0913.pdf |  | h |  |  |  | D1.1 | Editors create in D1.1 | 1 | D- | 9
13 |  |  | o Data Detector | N/A | Was added for TDD, no longer needed | Jin |  |  |  |  | D1.3 |  | 1 | D1.0 | 10
15 |  |  | o LDPC | D | TD#81: prodan_3bn_01a_0713.pdf; TD#95 (FDD codes for Node+N, N≥0) |  | X | 1 |  |  | D1.2 |  | 1 | S | 5
17 |  |  | o MTTFPA | D | TD#82 (objective); TD#93: prodan_3bn_02a_0913.pdf |  | X | 1 |  |  | N/A | not applicable |  | (blank) | 38
18 |  |  | · FCP generation | D | TD#51 (PHY LINK Codeword Pointer) | Mark | X | 1 | [5 empty] | Grand Total | 136
19 |  |  | · Scrambler | D1.2 | TD#128: montreuil_3bn_01a_0514.pdf s/b there (motion NOR #3) | Leo | x | 1 |  |  | Needed | Meaning
20 |  |  | · Gearbox | D1.2 | TD#117 (boyd_3bn_03_0114.pdf) | Jin | X | 1 |  |  | X | required item
21 |  |  | · IDLE Delete | D1.3 | TD#118 (boyd_3bn_03_0114.pdf) | Jin | X | 1 |  |  |  | (blank) not required
22 |  |  | PCS (receiving): |  |  |  | h |  |  |  | d | draft proposal
23 |  |  | · NCP processing | N/A | Leave up to implementers choice | [5 empty] | h | header, not need in draft
24 |  |  | PCS / PMA Service Interface | D1.2 |  | Mark | x | 1
25 |  |  | PMA: |  |  |  | h
|  |  | · Subcarrier configuration and bit loading | D1.1 | 101.4.2.3 Subcarrier configuration and bit loading | Mark,Duane
|  |  | · Framing | D1.2 | 101.4.2.4 Framing | Mark
36 |  |  | · Symbol Mapper | D1.2 | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
37 |  |  | o Constellation Mapping | D | TD#103: prodan_3bn_02_1113.pdf shen_3bn_01_140226_Constellation.pdf (comment resolution) |  | X | 1
39 |  |  | · Interleaving |  |  |  | h
40 |  |  | o Time | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | x | 1
41 |  |  | o Frequency (Rich, Avi) | D | Frequency interleaving text is preliminary. | Rich | x | 1
42 |  |  | · Pilot Insertion (Avi, Christian, Jin) | D | TD#29: pietsch_3bn_01_0313.pdf, kliger_3bn_01_0313.pdf; TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
44 |  |  | o Pilot structure | D | TD#60: kliger_3bn_02_0513.pdf pietsch_3bn_01_0313.pdf; TD#67: kliger_3bn_02_0513.pdf; TD#79: kliger_3bn_02a_0713.pdf TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
48 |  |  | · IFFT / IDFT | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
49 |  |  | · Cyclic Prefix and Windowing | D | TD#23: montreuil_01a_0113.pdf; TD#63: pietsch_3bn_02_0313.pdf; TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
52 |  |  | · Subcarrier Configuration | D | TD#103: prodan_3bn_02_1113.pdf |  | X | 1
53 |  |  | o QAM Mapping | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
54 |  |  | · Bit Loading | D1.1 | TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
55 |  |  | · Pilot Map | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
56 |  |  | · PMA Other |  |  |  | h
57 |  |  | o Exclusion Rules | D | TD#5 (exclusions); TD#14 (placement); TD#55 (m, m+1, …); TD#56 (internal, band edge); TD#57 (2 band-edge); TD#58 (minimum internal 1MHz); TD#59 (fixed number internal in 192 MHz); TD#69 (start, integer number sub-carriers); TD#70 (mapping to sub-carriers); TD#71 (at most 16); TD#110: laubach_3bn_04c_1113.pdf | Duane | x | 1
68 |  |  | o Cycle Structure and Initialization | D1.3 | FCP, scrambler init coupled to PHY LINK cycle Proposed text for NCP | Mark & Duane | x | 1
69 |  |  | o Multiple OFDM Channels (Mark, Avi, …) | D1.1 | TD#8 (higher capacity) | Mark | x | 1
70 |  |  | PMA / PMD Service Interface | D1.3 | TD#127 D0.4 Bulk |  | X | 1
71 |  |  | PMD: |  |  |  | h
72 |  |  | · Electrical Input / Output | D- | TD#104: rahman_saif_3bn_02_1113.pdf | Mark et al | X | 0.75
73 |  |  | · Fidelity | D- | TD#104: rahman_saif_3bn_02_1113.pdf | Mark et al | X | 0.75
74 |  |  | · MDI | D | TD#104: rahman_saif_3bn_02_1113.pdf | Mark et al | X | 1
75 |  |  | Other: |  |  |  | h
76 |  |  | · OFDM Numerology | D | TD#2 (OFDM); TD#6 (multiple modulation orders); TD#7 (192 MHz, 10.24 MHz); TD#9 (Scaling); TD#30 (granularity of Fc); TD#31 (upper bound to 5GHz) TD#35 (minimum contiguous 24 MHz); TD#72 (FDD RF Spectrum); TD#74: rahman_saif_3bn_01_0713.pdf; TD#78: solomon_3bn_02b_0713.pdf; TD#89 (FDD 5 to 234 MHz ); |  | X | 1
77 |  |  | · Channel Model | D | TD#15: howald_01a_0113.pdf |  | X | 1
78 |  |  | · CNU and CLT Receive Direction: |  |  |  | h
79 |  |  | · Rx Idle Deletion | D | TD#42 (Like 10G-EPON) |  | X | 1
81 |  |  | · Rx Idle Insertion | D | TD#43 (Like 10G-EPON with changes); TD#48: hajduczenia_3bn_01_0513.pdf |  | X | 1
82 |  |  | · CNU and CLT Transmit Direction: |  |  |  | h
85 |  |  | · Tx Idle Insertion | D1.3 | TD#44 (Like 10G-EPON with changes); TD#49: garavaglia_3bn_02a_0513.pdf See Clause 103.2.2 | Jin & Duane | X | 1
|  |  | · Tx Idle Deletion | D1.3 | TD#45 (Like 10G-EPON with changes); TD#48: hajduczenia_3bn_01_0513.pdf | Jin & Duane | X | 1
87 |  |  | · Downstream PHY Block Diagram | D | TD#91: kliger_3bn_01a_0913.pdf |  | X | 1
88 |  |  | · Subcarrier Clocking, Accuracy | D | TD#110: laubach_3bn_04c_1113.pdf |  | X | 1
89 |  | Upstream | Upstream PHY |  |  |  | h
91 |  |  | Upstream TX Block Diagram | D- | TD#107: kliger_3bn_01a_1113.pdf TD#125: laubach_3bn_02_0314.pdf | Mark, Avi, Duane | X | 0.75
93 |  |  | Reconciliation | N/A | No changes
94 |  |  | Upstream OFDM (Super) Frame |  |  |  | h
95 |  |  | · OFDM frames, Data vs PHY Link, probes | D1.0 |  |  | x | 1
96 |  |  | PCS: |  |  |  | h
97 |  |  | · Rate Adaptation | B |  | Jin | x | 0.5
98 |  |  | · 64B/66B Encoder / Decoder | D | TD#20 (65b); TD#46: hajduczenia_3bn_04_0513.pdf; TD#50 (continuous vector, no split); |  | X | 1
101 |  |  | · Timestamp for de-jittering |  |  | Mark
102 |  |  | · FEC Encoder and Data Detector: |  | TD#47: prodan_3bn_01_0513.pdf |  | h
105 |  |  | o FEC Codewords | D | TD#81: prodan_3bn_01a_0713.pdf; TD#92: shen_3bn_01_0913.pdf; TD#95 (FDD codes for Node+N, N≥0) |  | X | 1
|  |  | o Codeword Builder | D1.3 | TD#103: prodan_3bn_01_1113.pdf | Rich | X | 1
106 |  |  | o SD and/or psudo code for Codeword Builder |  |  | Mark
108 |  |  | o MTTFPA | D | TD#82 (objective); TD#93: prodan_3bn_02a_0913.pdf |  | X | 1
109 |  |  | · Scrambler | B | TD#128: montreuil_3bn_01a_0514.pdf | Mark | X | 0.5
110 |  |  | · Gearbox | N/A | Is this the similar to DS? |  | x | 0
111 |  |  | PCS / PMA Service Interface | D1.2 |  | Mark | x | 1
112 |  |  | PMA: |  |  |  | h
123 |  |  | · Symbol Mapper |  |  |  | h
|  |  | o Constellation Mapping | D | TD#103: prodan_3bn_02_1113.pdf |  | X | 1
124 |  |  | o Burst Marker Placement | D1.3 |  | Rich , Leo & Mark | X
125 |  |  | o 1D-to-2D subcarrier assignment, etc. | B | TD#121 (boyd_3bn_02_0114.pdf) | Mark | X | 0.5
126 |  |  | · Interleaving |  |  |  | h
127 |  |  | o Pilot Pattern (Avi, others) | B | TD#61: pietsch_3bn_01_0513.pdf kliger_3bn_01_0313.pdf pietsch_3bn_01_0513.pdf | Kill | X | 0.5
128 |  |  | o Interleaver | B |  | Kill | x | 0.5
129 |  |  | · Pilot Insertion | D1.3 | TD#131: montreuil_3bn_05a_0514.pdf |  | x | 1
130 |  |  | · IFFT / IDFT | D | ?same as downstream? |  | X | 1
131 |  |  | · Pre-Equalization | D | TD#64: montreuil_01_0512.pdf kliger_01a_0912.pdf |  | X | 1
132 |  |  | · Cyclic Prefix and Windowing | D | TD#23: montreuil_01a_0113.pdf; |  | X | 1
133 |  |  | · OFDM (Super) Frame Configuration and Bit Loading |  |  |  | h
134 |  |  | o Superframe structure | D1.0 |  |  | x | 1
137 |  |  | o Burst Structure / Resource Blocks | D1.0 | TD#61: pietsch_3bn_01_0513.pdf kliger_3bn_01_0313.pdf pietsch_3bn_01_0513.pdf TD#124 (8, 12, and 16 symbols) TD#80: kliger_3bn_03_0713.pdf |  | X | 1
142 |  |  | o Burst Markers Definition | D1.3 | TD#25 (start / stop markers); TD#28 (marker definition); TD#97: rahman_syed_3bn_01_0913.pdf; TD#109: rahman_syed_3bn_01_1113.pdf TD#126: montreuil_3bn_01b_0314.pdf |  | X | 1
143 |  |  | · Framing Timing | D- |  | Duane & Mark | x | 0.75
144 |  |  | · Probe Generator | D1.2 | TD#129 montreuil_3bn_02a_0514.pdf | Avi | x | 1
145 |  |  | · PMA Other |  |  |  | h
154 |  |  | o Exclusion Rules | D1.1 | TD#5 (exclusions); TD#14 (placement); TD#24 ( 192 MHz and exclusions); TD#55 (m, m+1, …); TD#56 (internal, band edge); TD#57 (2 band-edge); TD#58 (minimum internal 1MHz); TD#59 (fixed number internal in 192 MHz); TD#69 (start, integer number sub-carriers); | Duane | x | 1
157 |  |  | PMA / PMD Service Interface | D | TD#127 D0.4 Bulk | Mark | X | 1
158 |  |  | PMD: |  |  | Mark | h
159 |  |  | · Electrical Input / Output | D1.2 |  | Mark, Tom | x | 1
160 |  |  | · Fidelity | D1.2 |  | Mark, Tom | x | 1
|  |  | · MDI | D1.2 |  | Mark, Tom | x | 1
162 |  |  | Other: |  |  |  | H
163 |  |  | · OFDM Numerology | D | TD#3 (OFDMA); TD#9 (scaling); TD#17 (25 kHz and 50 kHz spacing); TD#24 ( 192 MHz and exclusions); TD#30 (granularity of Fc); TD#31 (upper bound to 5GHz); TD#72 (FDD RF Spectrum); TD#74: rahman_saif_3bn_01_0713.pdf; TD#78: solomon_3bn_02b_0713.pdf; TD#89 (FDD 5 to 234 MHz ); |  | X | 1
164 |  |  | · Channel Model | D | See Annex 100A |  | X | 1
166 | MPCP |  | MPCP |  |  |  | h
167 |  |  | MPCP: |  |  |  | h
168 |  |  | · Rate Adaptation | D- |  | Jin, Duane | X | 0.75
169 |  |  | · FEC Adaptation / Impact (Duane) | D- |  | Jin, Duane | X | 0.75
170 |  |  | · Gate / Report calculation changes | D |  |  | X | 1
171 |  |  | MPCP Interoperation: |  |  |  | h
173 |  |  | · MAC Discovery and registration verification ( ) | N/A | Not sure there is anything to do here
174 |  |  | · tqSize, OctetsRemaining, PHY_DATA_SIZE & PHY_OVERHEAD_SIZE, fecOffset, packet_initiate_delay, CheckGrantSize, PMD_OverheadT | D- | TD#112: remein_3bn_06_1113.pdf | Jin, Duane | X | 0.75
175 | PHY Link | Downstream | Downstream PHY Link |  |  |  | h
176 |  |  | · Performance study | D |  | Duane
177 |  |  | PHY LINK Framing |  | TD#38 (PHY Link framing) |  | h
178 |  |  | · Preamble | D | TD#76: montreuil_3bn_01_0713.pdf |  | X | 1
179 |  |  | · PHY Link Frame | D |  |  | X | 1
180 |  |  | PHY LINK Messages and Protocol |  |  |  | h
181 |  |  | · Content | D | TD#77: kliger_3bn_01b_0713.pdf |  | X | 1
182 |  |  | · Protocol | D |  |  | X | 1
183 |  |  | · PHY Discovery | D- | TD#119 (remein_3bn_05_0114.pdf) | Duane, Avi | X | 0.75
184 |  |  | PHY LINK Insertions: |  |  |  | h
185 |  |  | · FCP | D1.3 | There is just the bearest mention of FCP | Duane & Mark | X | 1
186 |  |  | · Timestamp MB | D1.3 | Now part of EPMH |  | X | 1
187 |  |  | · EE MB | N/A | (no work done – evaluate) |  | x | 0
189 |  |  | · Trigger MB | N/A | (PNM, evaluate PHY impact only (not mgmt.)) Do we need this for EPoC? "Nice to have." |  | x | 0
190 |  |  | PHY LINK Numerology: |  |  |  | h
191 |  |  | · 16 QAM fixed | D | TD#11 (16 QAM) |  | X | 1
193 |  |  | · CP and sub-carrier spacing same as data channel (Duane, acquisition) | D | TD#13 (same CP/sub-carrier spacing) (requirement to be added against D0.5) | Duane | X | 1
194 |  |  | · 400 KHz wide without continuous pilots. | D | TD#39 (as described) |  | X | 1
195 |  |  | · PHY LINK Placement 3MHz either side | D | TD#62 (3 MHz either side) |  | X | 1
196 |  |  | PHY Link Receiver |  |  |  | h
197 |  |  | · CNU auto-detect CP / windowing | D | TD#12 (CP) |  | X | 1
198 |  |  | FEC |  |  |  | h
201 |  |  | · Definitions | D | TD#36 (ECC); TD#75: shen_3bn_01_0713.pdf TD#120 (shen_3bn_01_0114.docx) |  | X | 1
202 |  |  | · Use | D |  |  | X | 1
203 |  |  | Scrambler | D |  |  | X | 1
204 |  |  | Time Interleaving | D- | (needs detail / attention / update) | Mark, Avi | X | 0.75
205 |  |  | Symbol Mapper | D- | review draft | Mark, Avi | X | 0.75
207 |  | Upstream | Upstream PHY Link |  |  |  | h
208 |  |  | Upstream (super) frame |  |  |  | h
209 |  |  | · OFDMA frames, PHY Link signals | D1.0 |  |  | x | 1
210 |  |  | · Frame configuration | D1.0 |  |  | x | 1
211 |  |  | PHY LINK Signals / Messages: |  |  |  | h
212 |  |  | · Messages / Content | D | TD#77: kliger_3bn_01b_0713.pdf |  | X | 1
213 |  |  | o Protocol | D |  |  | X | 1
214 |  |  | · PHY Discovery | D |  |  | X | 1
215 |  |  | o Fixed preamble | D |  |  | X | 1
216 |  |  | · Fine ranging | D | (only FEC) |  | X | 1
217 |  |  | o Fixed preamble | D |  |  | x | 1
218 |  |  | FEC |  |  |  | h
222 |  |  | · Definitions | D | TD#36 (ECC); TD#75: shen_3bn_01_0713.pdf TD#105: shen_3bn_01_1113.pdf TD#120 (shen_3bn_01_0114.docx) |  | X | 1
223 |  |  | · Use | D |  |  | X | 1
224 |  |  | Scrambler | D | (assumption same as downstream) TD#128: montreuil_3bn_01a_0514.pdf |  | X | 1
|  |  | Interleaver |  |  | Mark, Avi
225 |  |  | Symbol Mapper | D- | review draft | Mark | X | 0.75
228 |  |  | Wide Band Probing | D1.0 | TD#66: montreuil_3bn_01a_0513.pdf; TD#98: rahman_syed_3bn_01_0313.pdf; TD#106: rahman_syed_3bn_02_1113.pdf |  | X | 1
229 |  |  | · Probe Period scheduling | D1.1 |  | Duane, Avi | x | 1
230 |  |  | · Probe Period scheduling refinment | D1.2 |  | Duane, Avi | x | 1
231 |  | Other | PHY Link Other |  |  |  | h
234 |  |  | PHY LINK Starting Point | D | TD#53: boyd_3bn_02_0513.pdf |  | X | 1
235 |  |  | PHY LINK Baseline Work | D | TD#99: remein_3bn_03a_0913.pdf; TD#113: remein_3bn_07_1113.pdf remein_3bn_08_1113.pdf |  | X | 1
236 |  |  | PHY LINK Transparency, shall not add jitter or latency to the data | D | TD#21 (transparency); |  | X | 1
237 |  |  | · No additional buffering | D | TD#37 (repeat of TD#21 with buffering) |  | X | 1
238 |  |  | PHY Link and procedures: (Avi, Duane, Jin) |  |  |  | h
239 |  |  | · “Bring up” through auto-negotiation to Linked | D1.1 | (beginnings, needs additional detail) |  | X | 1
240 |  |  | · “Ranging” and symbol synchronization (Bill, Leo, Avi, Hesham) | D1.2 |  |  | X | 1
|  |  | Probe/PHY Discovery block didagram update |  |  | Duane, Avi
241 |  |  | PHY Link acquisition: |  |  |  | h
242 |  |  | · “Lock” and acquisition | D1.2 |  |  | X | 1
243 | System Issues |  | System Issues |  |  |  | h
244 |  |  | Clocking / jitter |  | CL 64.2.2.1 (1G), CL 77.2.2.1 (10G) 103.2.2.1 8 TQ down, 12 TQ up see 103.2.2.1 (guardThreshold CLT & CNU) |  | x | 0
247 |  |  | Time Synchronization (Bill) |  |  | Bill | x | 0
248 |  |  | MDIO registers to report on subcarrier or subcarrier group, signal parameters including quality. | D- | TD#34 (MDIO registers to report…) TD#116 (MIDO register baseline material) (some initial work in draft) | Duane | x | 0.75
251 |  |  | Exclusion Bands Configuration |  |  |  | h
252 |  |  | · By MDIO | D | TD#32 (Exclusion bands configured by MDIO) (clause 45 registers) TD#33 (Exclusion bands configured by PHY LINK) |  | X | 1
253 |  |  | “Lost sync” and recovery / reset procedures | D- | Needs review MULPI T3 & T4 timeouts | Avi | x | 0.75
254 |  |  | Performance Analysis: |  |  |  | h
256 |  |  | · Baseline Channel Conditions | D | TD#18: remein_3bn_07_0313.pdf |  | X | 1
257 |  |  | · Exemplar Channel Conditions | N/A | TD#54: howald_3bn_02_0313.pdf (not needed in draft)
258 |  |  | · EPoC Delay evaluation |  | TD#41: garavaglia_02_0912.pdf |  | x | 0
259 |  |  | · Error analysis |  |  |  | x | 0
263 |  |  | Power Saving, study support for configurable mechanism. (Adopt SIEPON and apply to EPoC as appropriate.) |  | TD#1: hajduczenia_05a_0912.pdf Can we eliminate the EE MB in the PHY Link section above? | Leo, Avi | x | 0
264 | Proactive Network Management |  | Proactive Network Management |  | Below is based on currivan_3bn_01_1113.pdf Need to update/sync with any changes since then. |  | h
265 |  |  | CNU Downstream Performance Metrics |  |  |  | h
266 |  |  | Per Data Channel: |  |  |  | h
267 |  |  | · Uncorrectable codewords (CRC-40 fail) | D | FecCodeWordFail |  | X | 1
268 |  |  | · Total number of data FEC codewords | D | FecCodeWordCount, FecCodeWordSuccess |  | X | 1
270 |  |  | · RxMER: Per subcarrier ratio of average power of the equalized QAM constellation to the average error-vector power. For Continuous Pilots, difference between the equalized receive pilot value and the known correct pilot value. | D1.3 | Need to look at specifically what to put in EPoC PHY draft to support this. | Mark & Hesham | x | 1
272 |  |  | · Codeword error ratio versus time (seconds): Ratio of number of uncorrectable codewords to total number of codewords in each one-second interval for a rolling 10-minute period (600 values) | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY |  | x | 0
274 |  |  | · Codeword error ratio versus. time (minutes): Ratio of number of uncorrectable codewords to total number of codewords in each one-minute interval for a rolling 24-hour period (1440 values). | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY |  | x | 0
275 |  |  | · Ending time of rolling period | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY | Mark & Hesham | x | 0
276 |  |  | PHY Link: |  |  |  | h
277 |  |  | · Uncorrectable codewords (CRC-32 fail) |  |  | Mark & Duane | x | 0
278 |  |  | · Total number of PHY Link codewords |  |  | Mark & Duane | x | 0
279 |  |  | CLT Upstream Performance Metrics |  |  |  | h
281 |  |  | · Uncorrectable codewords (CRC-40 fail) | D- |  | Mark | x | 0.75
283 |  |  | · Total number of data FEC codewords | D- |  | Mark | x | 0.75
284 |  |  | · Provide the following FEC summaries over a period of up to 10 minutes for any single upstream user |  | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY. |  | h
285 |  |  | o Total number of seconds | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. |  | x | 0
286 |  |  | o Number of errored seconds (seconds during which at least one unreliable codeword occurred) | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. |  | x | 0
287 |  |  | o Count of codeword errors (uncorrectable codewords) in each 1-second interval | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. |  | x | 0
288 |  |  | o Start and stop time of summary | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. |  | x | 0
289 |  |  | PHY Link: |  |  |  | h
290 |  |  | · Uncorrectable codewords (CRC-32 fail) |  |  | Mark & Duane | x | 0
291 |  |  | · Total number of PHY Link codewords |  |  | Mark & Duane | x | 0
|  |  | Other |  |  |  | h
|  |  | · Downstream PHY Link support for Trigger administration | N/A | Per Saif - "Nice to have" Need work to partition what is in the PHY versus what is in the D3.1 trigger “system” and then what needs to go into other CableLabs specifications. See MULPI | Duane, Saif | x | 0
[9 empty] | 15 | 1
[9 empty] | 14 | 32768
[9 empty] | 13 | 16384
[9 empty] | 12 | 8192
4096
BQ*65+40+CQ*65+CPL+CP
220
14300
14340
16160
16225