## Work Items
Line | Area | Dir | Item | Status | Notes / Comment / References | Who | Needed | Points
0 |  |  | % Complete | 69.07% |  | Total Number of items | 135 | 93.25
1 | PHY Layer | Downstream | Downstream PHY Layer | [5 empty] | Status | Descroption | Points | Needed | X
2 |  |  | Downstream TX Block Diagram | D |  |  | X | 1 | S | baseline starting point, | 0.25
3 |  |  | Reconciliation | N/A | No changes |  |  |  | B | baseline proposal, | 0.5 | Row Labels | Count of Needed
4 |  |  | 1.6 Gb/s at MAC / PLS service interface in 192 MHz, in baseline channel conditions | D | TD#40: remein_3bn_07_0313.pdf (needs analysis) |  | x | 1 | D- | in draft, needs work | 0.75 |  | 2
6 |  |  | PCS (transmitting): |  |  |  | h |  | D | in draft, | 1 | B | 4
7 |  |  | · 64B/66B Encoder / Decoder | D | TD#20 (65b); TD#46: hajduczenia_3bn_04_0513.pdf TD#50 (continuous vector, no split); |  | X | 1 | D1.0 | Editors create in D1.0 | 1 | D | 68
10 |  |  | · FEC and Data Detector |  | TD#4 (LDPC); TD#47: prodan_3bn_01_0513.pdf; TD#94: hajduczenia_3bn_01a_0913.pdf |  | h |  | D1.1 | Editors create in D1.1 | 0.85 | D- | 9
13 |  |  | o Data Detector |  |  | Jin |  |  | N/A | not applicable |  | D1.0 | 10
15 |  |  | o LDPC | D | TD#81: prodan_3bn_01a_0713.pdf; TD#95 (FDD codes for Node+N, N≥0) |  | X | 1 |  |  |  | S | 5
17 |  |  | o MTTFPA | D | TD#82 (objective); TD#93: prodan_3bn_02a_0913.pdf |  | X | 1 | Needed | Meaning |  | (blank) | 38
18 |  |  | · FCP generation | S | TD#51 (PHY LINK Codeword Pointer) | Mark | X | 0.25 | X | required item |  | Grand Total | 136
19 |  |  | · Scrambler | B | TD#128: montreuil_3bn_01a_0514.pdf s/b there (motion NOR #3) | Leo | x | 0.5 |  | (blank) not required
20 |  |  | · Gearbox | S | TD#117 (boyd_3bn_03_0114.pdf) | Jin | X | 0.25 | d | draft proposal
21 |  |  | · IDLE Delete | S | TD#118 (boyd_3bn_03_0114.pdf) | Jin | X | 0.25 | h | header, not need in draft
22 |  |  | PCS (receiving): |  |  |  | h
23 |  |  | · NCP processing | N/A | Leave up to implementers choice
24 |  |  | PCS / PMA Service Interface |  |  | Mark | x | 0
25 |  |  | PMA: |  |  |  | h
|  |  | · Subcarrier configuration and bit loading |  | 101.4.2.3 Subcarrier configuration and bit loading | Mark,Duane
|  |  | · Framing |  | 101.4.2.4 Framing | Mark
36 |  |  | · Symbol Mapper | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
37 |  |  | o Constellation Mapping | D | TD#103: prodan_3bn_02_1113.pdf shen_3bn_01_140226_Constellation.pdf (comment resolution) |  | X | 1
39 |  |  | · Interleaving |  |  |  | h
40 |  |  | o Time | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | x | 1
41 |  |  | o Frequency (Rich, Avi) | D | Frequency interleaving text is preliminary. | Rich | x | 1
42 |  |  | · Pilot Insertion (Avi, Christian, Jin) | D | TD#29: pietsch_3bn_01_0313.pdf, kliger_3bn_01_0313.pdf; TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
44 |  |  | o Pilot structure | D | TD#60: kliger_3bn_02_0513.pdf pietsch_3bn_01_0313.pdf; TD#67: kliger_3bn_02_0513.pdf; TD#79: kliger_3bn_02a_0713.pdf TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
48 |  |  | · IFFT / IDFT | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
49 |  |  | · Cyclic Prefix and Windowing | D | TD#23: montreuil_01a_0113.pdf; TD#63: pietsch_3bn_02_0313.pdf; TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
52 |  |  | · Subcarrier Configuration | D | TD#103: prodan_3bn_02_1113.pdf |  | X | 1
53 |  |  | o QAM Mapping | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
54 |  |  | · Bit Loading | D- | TD#132: Draft 0.5 Comment Approved Responses |  | X | 0.75
55 |  |  | · Pilot Map | D | TD#110: laubach_3bn_04c_1113.pdf TD#132: Draft 0.5 Comment Approved Responses |  | X | 1
56 |  |  | · PMA Other |  |  |  | h
57 |  |  | o Exclusion Rules | D | TD#5 (exclusions); TD#14 (placement); TD#55 (m, m+1, …); TD#56 (internal, band edge); TD#57 (2 band-edge); TD#58 (minimum internal 1MHz); TD#59 (fixed number internal in 192 MHz); TD#69 (start, integer number sub-carriers); TD#70 (mapping to sub-carriers); TD#71 (at most 16); TD#110: laubach_3bn_04c_1113.pdf | Duane | d
68 |  |  | o Cycle Structure and Initialization | D- | NCP, scrambler init coupled to PHY LINK cycle Proposed text for NCP | Duane | d
69 |  |  | o Multiple OFDM Channels (Mark, Avi, …) | D | TD#8 (higher capacity) | Mark | x | 1
70 |  |  | PMA / PMD Service Interface | D | TD#127 D0.4 Bulk |  | X | 1
71 |  |  | PMD: |  |  |  | h
72 |  |  | · Electrical Input / Output | D | TD#104: rahman_saif_3bn_02_1113.pdf |  | X | 1
73 |  |  | · Fidelity | D | TD#104: rahman_saif_3bn_02_1113.pdf |  | X | 1
74 |  |  | · MDI | D | TD#104: rahman_saif_3bn_02_1113.pdf |  | X | 1
75 |  |  | Other: |  |  |  | h
76 |  |  | · OFDM Numerology | D | TD#2 (OFDM); TD#6 (multiple modulation orders); TD#7 (192 MHz, 10.24 MHz); TD#9 (Scaling); TD#30 (granularity of Fc); TD#31 (upper bound to 5GHz) TD#35 (minimum contiguous 24 MHz); TD#72 (FDD RF Spectrum); TD#74: rahman_saif_3bn_01_0713.pdf; TD#78: solomon_3bn_02b_0713.pdf; TD#89 (FDD 5 to 234 MHz ); |  | X | 1
77 |  |  | · Channel Model | D | TD#15: howald_01a_0113.pdf |  | X | 1
78 |  |  | · CNU and CLT Receive Direction: |  |  |  | h
79 |  |  | · Rx Idle Deletion | D | TD#42 (Like 10G-EPON) |  | X | 1
81 |  |  | · Rx Idle Insertion | D | TD#43 (Like 10G-EPON with changes); TD#48: hajduczenia_3bn_01_0513.pdf |  | X | 1
82 |  |  | · CNU and CLT Transmit Direction: |  |  |  | h
85 |  |  | · Tx Idle Insertion | B | TD#44 (Like 10G-EPON with changes); TD#49: garavaglia_3bn_02a_0513.pdf See Clause 103.2.2 | Jin | X | 0.5
|  |  | · Tx Idle Deletion | D | TD#45 (Like 10G-EPON with changes); TD#48: hajduczenia_3bn_01_0513.pdf | Jin | X | 1
87 |  |  | · Downstream PHY Block Diagram | D | TD#91: kliger_3bn_01a_0913.pdf |  | X | 1
88 |  |  | · Subcarrier Clocking, Accuracy | D | TD#110: laubach_3bn_04c_1113.pdf |  | X | 1
89 |  | Upstream | Upstream PHY |  |  |  | h
91 |  |  | Upstream TX Block Diagram | D | TD#107: kliger_3bn_01a_1113.pdf TD#125: laubach_3bn_02_0314.pdf |  | X | 1
93 |  |  | Reconciliation | N/A | No changes
94 |  |  | Upstream OFDM (Super) Frame |  |  |  | h
95 |  |  | · OFDM frames, Data vs PHY Link, probes | D1.0 |  |  | x | 1
96 |  |  | PCS: |  |  |  | h
97 |  |  | · Rate Adaptation |  |  | Jin | x | 0
98 |  |  | · 64B/66B Encoder / Decoder | D | TD#20 (65b); TD#46: hajduczenia_3bn_04_0513.pdf; TD#50 (continuous vector, no split); |  | X | 1
101 |  |  | · FEC Encoder and Data Detector: |  | TD#47: prodan_3bn_01_0513.pdf |  | h
102 |  |  | o FEC Codewords | D | TD#81: prodan_3bn_01a_0713.pdf; TD#92: shen_3bn_01_0913.pdf; TD#95 (FDD codes for Node+N, N≥0) |  | X | 1
105 |  |  | o Codeword Builder | B | TD#103: prodan_3bn_01_1113.pdf | Rich | X | 0.5
106 |  |  | o MTTFPA | D | TD#82 (objective); TD#93: prodan_3bn_02a_0913.pdf |  | X | 1
108 |  |  | · Scrambler | D1.0 | TD#128: montreuil_3bn_01a_0514.pdf |  | X | 1
109 |  |  | · Gearbox |  | Is this the similar to DS? | Jin | x | 0
110 |  |  | PCS / PMA Service Interface |  |  | Mark | x | 0
111 |  |  | PMA: |  |  |  | h
112 |  |  | · Symbol Mapper |  |  | Mark | x | 0
123 |  |  | o Constellation Mapping | D | TD#103: prodan_3bn_02_1113.pdf |  | X | 1
124 |  |  | · Interleaving |  |  |  | h
125 |  |  | o Pilot Pattern (Avi, others) | D1.0 | TD#61: pietsch_3bn_01_0513.pdf kliger_3bn_01_0313.pdf pietsch_3bn_01_0513.pdf |  | X | 1
126 |  |  | o Interleaver |  |  | Rich, Jin | x | 0
127 |  |  | · Pilot and Marker Insertion | D1.0 | TD#131: montreuil_3bn_05a_0514.pdf |  | x | 1
128 |  |  | · IFFT / IDFT | D | ?same as downstream? |  | X | 1
129 |  |  | · Pre-Equalization | D | TD#64: montreuil_01_0512.pdf kliger_01a_0912.pdf |  | X | 1
130 |  |  | · Cyclic Prefix and Windowing | D | TD#23: montreuil_01a_0113.pdf; |  | X | 1
131 |  |  | · OFDM (Super) Frame Configuration and Bit Loading |  |  |  | h
132 |  |  | o Superframe structure | D1.0 |  |  | x | 1
133 |  |  | o Burst Structure / Resource Blocks | D1.0 | TD#61: pietsch_3bn_01_0513.pdf kliger_3bn_01_0313.pdf pietsch_3bn_01_0513.pdf TD#124 (8, 12, and 16 symbols) TD#80: kliger_3bn_03_0713.pdf |  | X | 1
134 |  |  | o Burst Markers | D1.0 | TD#25 (start / stop markers); TD#28 (marker definition); TD#97: rahman_syed_3bn_01_0913.pdf; TD#109: rahman_syed_3bn_01_1113.pdf TD#126: montreuil_3bn_01b_0314.pdf |  | X | 1
137 |  |  | · Framing Timing | D- |  |  | x | 0.75
142 |  |  | · Probe Generator | B | TD#129 montreuil_3bn_02a_0514.pdf | Avi | x | 0.5
143 |  |  | · PMA Other |  |  |  | h
144 |  |  | o Exclusion Rules | D- | TD#5 (exclusions); TD#14 (placement); TD#24 ( 192 MHz and exclusions); TD#55 (m, m+1, …); TD#56 (internal, band edge); TD#57 (2 band-edge); TD#58 (minimum internal 1MHz); TD#59 (fixed number internal in 192 MHz); TD#69 (start, integer number sub-carriers); | Duane | d
145 |  |  | o Multiple OFDM Channels (Mark, Avi, …) |  | Removed
154 |  |  | o 1D-to-2D subcarrier assignment, etc. | S | TD#121 (boyd_3bn_02_0114.pdf) | Mark | X | 0.25
156 |  |  | PMA / PMD Service Interface | D | TD#127 D0.4 Bulk | Mark | X | 1
157 |  |  | PMD: |  |  | Mark | h
158 |  |  | · Electrical Input / Output |  |  | Mark, Tom | x | 0
159 |  |  | · Fidelity |  |  | Mark, Tom | x | 0
160 |  |  | · MDI |  |  | Mark, Tom | x | 0
|  |  | Other: |  |  |  | H
162 |  |  | · OFDM Numerology | D | TD#3 (OFDMA); TD#9 (scaling); TD#17 (25 kHz and 50 kHz spacing); TD#24 ( 192 MHz and exclusions); TD#30 (granularity of Fc); TD#31 (upper bound to 5GHz); TD#72 (FDD RF Spectrum); TD#74: rahman_saif_3bn_01_0713.pdf; TD#78: solomon_3bn_02b_0713.pdf; TD#89 (FDD 5 to 234 MHz ); |  | X | 1
163 |  |  | · Channel Model | D | See Annex 100A |  | X | 1
164 | MPCP |  | MPCP |  |  |  | h
166 |  |  | MPCP: |  |  |  | h
167 |  |  | · Rate Adaptation | D- |  | Jin, Duane | X | 0.75
168 |  |  | · FEC Adaptation / Impact (Duane) | D- |  | Jin, Duane | X | 0.75
169 |  |  | · Gate / Report calculation changes | D |  |  | X | 1
170 |  |  | MPCP Interoperation: |  |  |  | h
171 |  |  | · MAC Discovery and registration verification ( ) | N/A | Not sure there is anything to do here
173 |  |  | · tqSize, OctetsRemaining, PHY_DATA_SIZE & PHY_OVERHEAD_SIZE, fecOffset, packet_initiate_delay, CheckGrantSize, PMD_OverheadT | D | TD#112: remein_3bn_06_1113.pdf |  | X | 1
174 | PHY Link | Downstream | Downstream PHY Link |  |  |  | h
175 |  |  | · Performance study | D- |  | Duane
176 |  |  | PHY LINK Framing |  | TD#38 (PHY Link framing) |  | h
177 |  |  | · Preamble | D | TD#76: montreuil_3bn_01_0713.pdf |  | X | 1
178 |  |  | · PHY Link Frame | D |  |  | X | 1
179 |  |  | PHY LINK Messages and Protocol |  |  |  | h
180 |  |  | · Content | D | TD#77: kliger_3bn_01b_0713.pdf |  | X | 1
181 |  |  | · Protocol | D |  |  | X | 1
182 |  |  | · PHY Discovery | D | TD#119 (remein_3bn_05_0114.pdf) |  | X | 1
183 |  |  | PHY LINK Insertions: |  |  |  | h
184 |  |  | · FCP | D- | There is just the bearest mention of NPC |  | X | 0.75
185 |  |  | · Timestamp MB | D |  |  | X | 1
186 |  |  | · EE MB |  | (no work done – evaluate) | Leo, Avi | x | 0
187 |  |  | · Trigger MB | N/A | (PNM, evaluate PHY impact only (not mgmt.)) Do we need this for EPoC? "Nice to have." |  | x | 0
189 |  |  | PHY LINK Numerology: |  |  |  | h
190 |  |  | · 16 QAM fixed | D | TD#11 (16 QAM) |  | X | 1
191 |  |  | · CP and sub-carrier spacing same as data channel (Duane, acquisition) | D | TD#13 (same CP/sub-carrier spacing) (requirement to be added against D0.5) | Duane | X | 1
193 |  |  | · 400 KHz wide without continuous pilots. | D | TD#39 (as described) |  | X | 1
194 |  |  | · PHY LINK Placement 3MHz either side | D | TD#62 (3 MHz either side) |  | X | 1
195 |  |  | PHY Link Receiver |  |  |  | h
196 |  |  | · CNU auto-detect CP / windowing | D | TD#12 (CP) |  | X | 1
197 |  |  | FEC |  |  |  | h
198 |  |  | · Definitions | D | TD#36 (ECC); TD#75: shen_3bn_01_0713.pdf TD#120 (shen_3bn_01_0114.docx) |  | X | 1
201 |  |  | · Use | D |  |  | X | 1
202 |  |  | Scrambler | D |  |  | X | 1
203 |  |  | Time Interleaving | D- | (needs detail / attention / update) |  | X | 0.75
204 |  |  | Symbol Mapper | D- | (needs attention / update) |  | X | 0.75
205 |  | Upstream | Upstream PHY Link |  |  |  | h
207 |  |  | Upstream (super) frame |  |  |  | h
208 |  |  | · OFDMA frames, PHY Link signals | D1.0 |  |  | x | 1
209 |  |  | · Frame configuration | D1.0 |  |  | x | 1
210 |  |  | PHY LINK Signals / Messages: |  |  |  | h
211 |  |  | · Messages / Content | D | TD#77: kliger_3bn_01b_0713.pdf |  | X | 1
212 |  |  | o Protocol | D |  |  | X | 1
213 |  |  | · PHY Discovery | D |  |  | X | 1
214 |  |  | o Fixed preamble | D |  |  | X | 1
215 |  |  | · Fine ranging | D- | (only FEC) |  | X | 0.75
216 |  |  | o Fixed preamble | D |  |  | x | 1
217 |  |  | FEC |  |  |  | h
218 |  |  | · Definitions | D | TD#36 (ECC); TD#75: shen_3bn_01_0713.pdf TD#105: shen_3bn_01_1113.pdf TD#120 (shen_3bn_01_0114.docx) |  | X | 1
222 |  |  | · Use | D |  |  | X | 1
223 |  |  | Scrambler | D | (assumption same as downstream) TD#128: montreuil_3bn_01a_0514.pdf |  | X | 1
224 |  |  | Symbol Mapper | D |  |  | X | 1
225 |  |  | Wide Band Probing | D1.0 | TD#66: montreuil_3bn_01a_0513.pdf; TD#98: rahman_syed_3bn_01_0313.pdf; TD#106: rahman_syed_3bn_02_1113.pdf |  | X | 1
228 |  |  | · Probe Period scheduling |  |  | Duane, Avi
229 |  | Other | PHY Link Other |  |  |  | h
230 |  |  | PHY LINK Starting Point | D | TD#53: boyd_3bn_02_0513.pdf |  | X | 1
231 |  |  | PHY LINK Baseline Work | D | TD#99: remein_3bn_03a_0913.pdf; TD#113: remein_3bn_07_1113.pdf remein_3bn_08_1113.pdf |  | X | 1
234 |  |  | PHY LINK Transparency, shall not add jitter or latency to the data | D | TD#21 (transparency); |  | X | 1
235 |  |  | · No additional buffering | D | TD#37 (repeat of TD#21 with buffering) |  | X | 1
236 |  |  | PHY Link and procedures: (Avi, Duane, Jin) |  |  |  | h
237 |  |  | · “Bring up” through auto-negotiation to Linked | D- | (beginnings, needs additional detail) |  | X | 0.75
238 |  |  | · “Ranging” and symbol synchronization (Bill, Leo, Avi, Hesham) | D- | (not complete, high level only) |  | X | 0.75
239 |  |  | PHY Link acquisition: |  |  |  | h
240 |  |  | · “Lock” and acquisition | D- | (needs some work) |  | X | 0.75
241 | System Issues |  | System Issues |  |  |  | h
242 |  |  | Clocking / jitter |  |  |  | x | 0
243 |  |  | Time Synchronization (Bill) |  |  | Bill | x | 0
244 |  |  | MDIO registers to report on subcarrier or subcarrier group, signal parameters including quality. |  | TD#34 (MDIO registers to report…) TD#116 (MIDO register baseline material) (some initial work in draft) | Hesham | x | 0
247 |  |  | Exclusion Bands Configuration |  |  |  | h
248 |  |  | · By MDIO | D | TD#32 (Exclusion bands configured by MDIO) (clause 45 registers) TD#33 (Exclusion bands configured by PHY LINK) |  | X | 1
251 |  |  | “Lost sync” and recovery / reset procedures |  | MULPI T3 & T4 timeouts | Duane | x | 0
252 |  |  | Performance Analysis: |  |  |  | h
253 |  |  | · Baseline Channel Conditions | D | TD#18: remein_3bn_07_0313.pdf |  | X | 1
254 |  |  | · Exemplar Channel Conditions | N/A | TD#54: howald_3bn_02_0313.pdf (not needed in draft)
256 |  |  | · EPoC Delay evaluation |  | TD#41: garavaglia_02_0912.pdf |  | x | 0
257 |  |  | · Error analysis |  |  |  | x | 0
258 |  |  | · Jitter |  | CL 64.2.2.1 (1G), CL 77.2.2.1 (10G) 103.2.2.1 8 TQ down, 12 TQ up see 103.2.2.1 (guardThreshold CLT & CNU) |  | x | 0
259 |  |  | Power Saving, study support for configurable mechanism. (Adopt SIEPON and apply to EPoC as appropriate.) |  | TD#1: hajduczenia_05a_0912.pdf Can we eliminate the EE MB in the PHY Link section above? | Leo, Avi | x | 0
261 | Proactive Network Management |  | Proactive Network Management |  | Below is based on currivan_3bn_01_1113.pdf Need to update/sync with any changes since then. |  | h
263 |  |  | CNU Downstream Performance Metrics |  |  |  | h
264 |  |  | Per Data Channel: |  |  |  | h
265 |  |  | · Uncorrectable codewords (CRC-40 fail) | D | FecCodeWordFail |  | X | 1
266 |  |  | · Total number of data FEC codewords | D | FecCodeWordCount, FecCodeWordSuccess |  | X | 1
267 |  |  | · RxMER: Per subcarrier ratio of average power of the equalized QAM constellation to the average error-vector power. For Continuous Pilots, difference between the equalized receive pilot value and the known correct pilot value. |  | Need to look at specifically what to put in EPoC PHY draft to support this. | Hesham | x | 0
268 |  |  | · Codeword error ratio versus time (seconds): Ratio of number of uncorrectable codewords to total number of codewords in each one-second interval for a rolling 10-minute period (600 values) | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY |  | x | 0
270 |  |  | · Codeword error ratio versus. time (minutes): Ratio of number of uncorrectable codewords to total number of codewords in each one-minute interval for a rolling 24-hour period (1440 values). | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY |  | x | 0
272 |  |  | · Ending time of rolling period | N/A | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY | Hesham | x | 0
274 |  |  | PHY Link: |  |  |  | h
275 |  |  | · Uncorrectable codewords (CRC-32 fail) |  |  | Mark | x | 0
276 |  |  | · Total number of PHY Link codewords |  |  | Mark | x | 0
277 |  |  | CLT Upstream Performance Metrics |  |  |  | h
278 |  |  | Per Data Channel: |  |  |  | h
279 |  |  | · Uncorrectable codewords (CRC-40 fail) |  |  | Mark | x | 0
280 |  |  | · Total number of data FEC codewords |  |  | Mark | x | 0
281 |  |  | · Provide the following FEC summaries over a period of up to 10 minutes for any single upstream user |  | Need to look at specifically what to put in EPoC PHY draft to support this. This should be a higher layer function and not part of the PHY. |  | h
283 |  |  | o Total number of seconds |  | Need to look at specifically what to put in EPoC PHY draft to support this. | Mark | x | 0
284 |  |  | o Number of errored seconds (seconds during which at least one unreliable codeword occurred) |  | Need to look at specifically what to put in EPoC PHY draft to support this. | Mark | x | 0
285 |  |  | o Count of codeword errors (uncorrectable codewords) in each 1-second interval |  | Need to look at specifically what to put in EPoC PHY draft to support this. | Mark | x | 0
286 |  |  | o Start and stop time of summary |  | Need to look at specifically what to put in EPoC PHY draft to support this. | Mark | x | 0
287 |  |  | PHY Link: |  |  |  | h
288 |  |  | · Uncorrectable codewords (CRC-32 fail) |  |  | Mark | x | 0
289 |  |  | · Total number of PHY Link codewords |  |  | Mark | x | 0
290 |  |  | Other |  |  |  | h
291 |  |  | · Downstream PHY Link support for Trigger administration |  | Need work to partition what is in the PHY versus what is in the D3.1 trigger “system” and then what needs to go into other CableLabs specifications. See MULPI | Duane, Saif | x | 0