## tasks for D2.1
Due by 08/22/2019 D2.1 comment deadline |  |  |  | Presented at AdHoc |  |  | Status
D2.0 Comment | Commenter | Description | Volunteer | 2019-08-07 | 2019-08-21 | 2019-09-04
245 | Gerrit den Besten | Wants both PHYs to do Slow Wake if one requests it even if the other doesn't. | Gerrit den Besten |  |  |  | TF rejected in previous cycle. No further action unless a new comment is received on D2.1.
196 | Piers Dawe | Wants accuracy removed from SNR measurement. |  |  |  |  | TF rejected in previous cycle. No further action unless a new comment is received on D2.1.
200 | Piers Dawe | Wants jitter test pattern to be PRBS13Q | Ramin Farjad, George Zimmerman |  |  |  | Ramin and George discussing with Piers Dawe and Mike Dudek.
208 | Piers Dawe | Doesn't want tolerance on resistor values |  |  |  |  | General requirement was moved to specific location.
118 | Mike Dudek | Doesn’t want the test setup to show a differential probe when they can be problematic and 2 single ended probes are usually used. | Marty Gubow |  |  |  | Marty will provide a comment on D2.1 with a drawing to change the test fixture drawing to use 2 single ended scope probes with 50 ohm impedance.
207 | Piers Dawe | PHY must work in a wide range of environments. Concerned that perfoming link segment measurements at controlled temperature and humidity may be taken as the limits not applying outside this. | Natalie Wienckowski |  |  |  | Natalie will provide a comment on D2.1 with wording to clarify operating conditions vs. test conditions.
199 | Piers Dawe | Doesn't want state diagrams in an informative annex. |  |  |  |  | Purpose statement was added to annex. No further action unless a new comment is received on D2.1.
138 | Chris DiMinico | Tx - Rx Annex |  |  |  |  | 149C will be added to D2.1 with IL only. Chris will provide a comment with additional text for RL and other parameters needed.