{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["Action Items","Tasks to D1.0","D 1.0 tasks"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Action Items","index":0,"n_rows":116,"n_cols":60,"rows_kept":116,"cut":false,"hidden":false,"merged":[[3,45,3,48],[3,53,3,57],[3,49,3,52],[3,38,3,39],[3,58,3,59],[2,2,2,15],[2,16,2,59],[3,2,3,3],[3,4,3,6],[3,7,3,9],[3,10,3,11],[3,12,3,15],[3,16,3,19],[3,20,3,23],[3,24,3,28],[3,31,3,32],[3,29,3,30],[3,33,3,37],[3,40,3,44]]}
[null,"Planned to vote"]
[null,"On Track"]
[null,"Started, risk of being late",2020,null,null,null,null,null,null,null,null,null,null,null,null,null,2021]
[null,"late","Aug",null,"Sept",null,null,"Oct",null,null,"Nov",null,"Dec",null,null,null,"Jan",null,null,null,"Feb",null,null,null,"Mar",null,null,null,null,"April",null,"May",null,"Jun",null,null,null,null,"July",null,"Aug",null,null,null,null,"Sept",null,null,null,"Oct",null,null,null,"Nov",null,null,null,null,"Dec"]
[null,"due date","5",19,2,16,30,14,21,28,null,"PL",1,8,15,22,5,12,19,"IN",2,9,16,23,1,15,"16(PL)",23,"30(IN)",20,27,18,"25(IN)",1,8,15,22,29,"13(PL)","20(PL)",3,10,17,24,31,7,14,"21(IN)","28(IN)",5,12,16,26,2,9,"PL",23,30,1,15]
[null,"Draft to-do list"]
[null,"Link segment test plan"]
[null,"Test setup for Link Segment measurements (Haysam Kadry)"]
[null,"25 Gbps PMA and link segment, which is reused as 2x or 4x for the 50Gbps and 100 Gbps"]
[]
[null,"Link Segment Measurements - s4p/s2p"]
[null,"Rich Boyer"]
[null,"Eric DiBiaso",null,null,null,null,null,null,null,"7m"]
[null,"Harsh Patel"]
[null,"Thomas Mueller",null,null,null,null,null,null,null,"T"]
[null," - Reference points on PCB side of MDI (GZ)"]
[null," - link segment distances/inlines - usage expectations"]
[null,"Haysam Kadry"]
[null,"Natalie Wienckowski"]
[]
[null,"Link Segement Measurements targeting improved IL at Nyquist (e.g. zimmerman_3cy_01a_1120.pdf, sedarat_3cy_01_10_14_20.pdf)"]
[null,"Thomas Mueller"]
[null,"Rich Boyer"]
[null,"Harsh Patel"]
[]
[null,"link segment worst case IL simulations for 11 m"]
[null,"Erwin Koeppendoefer"]
[null,"Chris DiMinico?"]
[]
[null,"Complete link segment w/ in-lines"]
[null,"Eric DiBiaso"]
[null,"Thomas Mueller"]
[null,"Christian Neulinger"]
[null,"11m cable IL test data - Eric DiBiaso"]
[null,"11m cable RL test data - Eric DiBiaso"]
[]
[null,"Link Segment IL proposal (multiple cable experts) Chris D."]
[null,"Link Segment RL proposal (multiple cable experts)"]
[null,"Link Segment Screening/Coupling Attenuation (multiple cable experts)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"TM"]
[null,"residual echo (micro-reflection) parameters (Ragnar & Hossein)",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"HS"]
[null,"Surface transfer impedance of link segment"]
[]
[null,"Tx Function to Rx function channel characteristics & definiton of test points and segments - Chris DiMinico"]
[null,"Initial timeline - Steve Carlson"]
[]
[null,"Link segment cross talk measurements - Thomas Mueller"]
[null,"Harsh Patel"]
[]
[null,"Link Segment skew between the lanes"]
[null,"Thomas Mueller"]
[null,"Rich Boyer"]
[]
[null,"Link Segment design for measurements"]
[null,"  Eric DiBiaso"]
[null,"Thomas Mueller (7m & 11m 2 inlines) (0.25m shortest segment)"]
[null,"Link Segment RL proposal (Emilio Cuesta, Thomas Mueller, Rich Boyer, Eric DiBiaso)"]
[null,"Presentation on % of cable at x temp vs. length"]
[null,"Haysam Kadry"]
[null,"Natalie Wienckowski"]
[]
[null,"EMC requirements at higher frequencies"]
[null,"Rich Boyer & Haysam Kadry"]
[null,"EMC ingress immunity through shield - Rich Boyer"]
[]
[null,"PCB options and trade offs - DiMinico & Kadry"]
[null,"PCB IL Limit and test fixture definition (examples of existing definitions) - Kadry & DiMinico"]
[null,"Total IL proposal (link segment & PCB) Kadry/Mueller"]
[]
[null,"PCB connector measurements"]
[null,"Emilio Cuesta / Eric DiBiaso"]
[null,"Thomas Mueller"]
[null,"Harsh Patel"]
[]
[null,"Channel Model - IL & RL"]
[null,"Assymetric Communication"]
[null,"Kamal Dalmia"]
[]
[]
[null,"Channel impact on PHY"]
[null,"Time Domain RL - Hossein Sedarat"]
[null,"IL and PHY Complexity - Hossein Sedarat"]
[]
[null,"Micro Reflection limits"]
[null,"Hossein Sedarat"]
[null,"Ragnar Jonsson & Hossein Sedarat"]
[null,"Ragnar Jonsson"]
[]
[null,"Calculations spreadsheet examples"]
[null,"Ragnar Jonsson"]
[]
[null,"Evaluate Phase Characteristics of suck-outs above Nyquist frequency (freq/dB/width allowed in cable) for both IL and RL (thumb up or thumb down)"]
[null,"Ragnar Jonsson/George Zimmerman"]
[null,"  Hossein Sedarat"]
[]
[null,"Fundamentals of TDD - Kamal Dalmia"]
[]
[null,"Signaling Type and Modulation"]
[null,"  Ragnar Jonsson"]
[null,"  Mike Tu"]
[]
[null,"What power may be needed by sensors/actuators that need these speeds?"]
[null,"  Natalie Wienckowski"]
[null,"  Haysam Kadry"]
[null,"PCS Issues for laning - George Zimmerman"]
[null,"laning and OAM - Zimmerman & Wienckowski"]
[null,"PoDL"]
[null,"EMC testing"]
[null,"PHY Vendor Needs"]
[null,"Test Data"]
[null,"Line Coding and FEC "]
[null,"Register Maps"]
[null,"PHY Control State Diagrams"]
[null,"EEE support"]
[null,"PICs"]
[null,"OAM - Natalie Wienckowski"]
[null,"Times synch - Steve & Marek"]

{"sheet":"Tasks to D1.0","index":1,"n_rows":15,"n_cols":3,"rows_kept":15,"cut":false,"hidden":false,"merged":[]}
["P802.3cy timeline D1.0 timing - November 2021"]
[]
["Item to complete","Volunteer","Date for Motion"]
["Link Segment limits (IL, RL)","Chris DiMinico","2021-07-20"]
["Link Segment Screening/Coupling attenuation","Thomas Mueller","2021-08-31"]
["Signaling Type and Modulation (ch?)","Ragnar Jonsson","2021-08-31"]
["Line Coding and FEC (ch?)","Ragnar Jonsson","2021-09-28"]
["What power may be needed by sensors/actuators that need these speeds?","Natalie Wienckowski\nHysam Kadry","2021-08-31"]
["PoDL?  \nIs this practical for the power needed for the PHY?","George Z\n\n","2021-09-28"]
["EEE ","George Z","2021-09-28"]
["Laning details","George Z","2021-10-12"]
["OAM updates","Natalie Wienckowski","2021-10-26"]
["Register Maps",null,"2021-10-26"]
["PHY Control State diagram proposals",null,"2021-10-26"]
["Finalize all items to enable D1.0 to be released ",null,"2021-11-16"]

{"sheet":"D 1.0 tasks","index":2,"n_rows":31,"n_cols":3,"rows_kept":31,"cut":false,"hidden":false,"merged":[[0,0,0,2]]}
["What's still missing.  Major items only.  Minor stuff and corrections not covered here."]
["Based on ","D0.x"]
["Date updated",{"$f":" LastSaveDate()","v":"2021-06-28T14:50:44"}]
[]
["Clause","Who to contribute text","Comments"]
[30,null,"Management\nMost of this can be completed as information is provided in Clauses TBD."]
[45,null,"Management Data Input/Output (MDIO) Interface\nCollected from information in Clauses TBD.\nDoes Adam assign the register numbers or do we just pick?"]
[78,null,"Energy-Efficient Ethernet (EEE)\nSomeone needs to provide the timing information for the rows to be added."]
["98B.3",null,"Need to add bit definitions for 25GBASE-T1, 50GBASE-T1 and 100GBASE-T1. \n"]
["98.B.4",null,"Add 25GBASE-T1, 50GBASE-T1 and 100GBASE-T1 to Priority Resolution list from fastest to slowest."]
[104,null,"PoDL\nIs anything needed?"]
["TBD, TBD.1, TBD.2",null,"Fill in open spots based on remainder of content in Clause TBD."]
["TBD.1.2.1",null,"Overview - Physical Coding Sublayer (PCS)"]
["TBD.1.2.2",null,"Overview - Physical Medium Attachment (PMA) sublayer"]
["TBD.1.2.3",null,"EEE capability"]
["TBD.1.2.4",null,"Link Synchronization"]
["TBD.1.3",null,"Signaling"]
["TBD.1.4",null,"Interfaces "]
["TBD.1.5",null,"Conventions - similar in all PHY Clauses"]
["TBD.2",null,"25/50/100GBASE-T1 service primitives and interfaces"]
["TBD.3",null,"25/50/100GBASE-T1 Physical Coding Sublayer (PCS) functions"]
["TBD.4",null,"Physical Medium Attachment (PMA) Sublayer"]
["TBD.5",null,"PMA electrical specifications"]
["TBD.6",null,"Management interface"]
["TBD.7.x",null,"Differential characteritic impedance\nNeed to decide if we want to put a tolerance on 100 ohms, e.g. 3%."]
["TBD.7.x",null,"Do we need Differential to common mode conversion?"]
["TBD.7.x",null,"Maximum link delay"]
["TBD.8",null,"MDI specification"]
["TBD.9",null,"Use text from Clause 149"]
["TBD.10",null,"Delay constraints"]
["TBD.11",null,"PICS"]