{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Action Items"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Action Items","index":0,"n_rows":22,"n_cols":42,"rows_kept":22,"cut":false,"hidden":false,"merged":[[5,1,7,1],[5,3,7,3],[5,2,7,2],[6,37,6,39],[6,35,6,36],[6,32,6,34],[10,1,11,1],[6,40,6,41],[6,25,6,27],[5,4,5,13],[5,14,5,41],[6,5,6,7],[6,8,6,9],[6,10,6,11],[6,12,6,13],[6,14,6,15],[6,16,6,17],[6,18,6,20],[6,21,6,22],[6,23,6,24],[6,28,6,29],[6,30,6,31]]}
[null,"Planned to vote"]
[null,"On Track"]
[null,"Started, risk of being late"]
[null,"late"]
[]
[null,"Task","Subtask","Owner",2020,null,null,null,null,null,null,null,null,null,2021]
[null,null,null,null,"Aug","Sept",null,null,"Oct",null,"Nov",null,"Dec",null,"Jan",null,"Feb",null,"Mar",null,null,"Apr",null,"May",null,"Jun",null,null,"Jul",null,"Aug",null,"Sept",null,null,"Oct",null,"Nov",null,null,"Dec"]
[null,null,null,null,18,1,15,"IN",6,20,3,"PL",1,15,5,"IN",2,16,2,"PL",30,13,27,11,"IN",1,15,29,"PL",27,10,24,7,"IN",28,12,26,9,"PL",30,14,28]
[null,"Draft to-do list",null,"Luisma Torres"]
[null,"Timeline approval",null,"Bob Grow"]
[null,"In-vehicle link requirements  that will shape the optical channel specifications ","Mechanical requirements"]
[null,null,"Environmental requirements"]
[null,"Relative cost analysis",null,"Rick Pimpinella"]
[null,"Link budget analysis (≤ 25 Gb/s)","PCS encoding, frame structure, modulation scheme, FEC","Rubén Pérez de Aranda"]
[null,null,"Optical channel, and O/E receiver model"]
[null,"Reliability assessment — “reliability constrained link budget” ","Reliability assesment reports"]
[null,null,"Link budget impact "]
[null,"Optical connector requirements ",null,"Steven Swanson"]
[null,"Transceiver specification (PMD)"]
[null,"Link budget analysis (> 25 Gb/s)","VCSEL characterization"]
[null,null,"PCS encoding, frame structure, modulation scheme, FEC"]
[null,null,"Optical channel, and O/E receiver model"]