{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Action Items"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Action Items","index":0,"n_rows":68,"n_cols":53,"rows_kept":68,"cut":false,"hidden":false,"merged":[[5,1,7,1],[5,3,7,3],[5,2,7,2],[6,48,6,50],[6,46,6,47],[6,43,6,45],[6,8,6,10],[6,11,6,13],[6,51,6,52],[6,33,6,36],[5,4,5,16],[5,17,5,52],[6,5,6,7],[6,14,6,16],[6,17,6,19],[6,20,6,21],[6,22,6,26],[6,27,6,28],[6,29,6,32],[6,37,6,40],[6,41,6,42]]}
[null,"Planned to vote"]
[null,"On Track",null,null,null,null,null,null,null,null,null,null,null,null,null,"Comment Deadline for D1.0: 26th February",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Comment Deadline for D1.1: 2 June"]
[null,"Started, risk of being late",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"Last Updated: 26/5/2021"]
[null,"late"]
[]
[null,"Task","Subtask","Owner",2020,null,null,null,null,null,null,null,null,null,null,null,null,2021]
[null,null,null,null,"Aug","Sept",null,null,"Oct",null,null,"Nov",null,null,"Dec",null,null,"Jan",null,null,"Feb",null,"Mar",null,null,null,null,"Apr",null,"May",null,null,null,"Jun",null,null,null,"Jul",null,null,null,"Aug",null,"Sept",null,null,"Oct",null,"Nov",null,null,"Dec"]
[null,null,null,null,18,1,15,29,6,20,27,10,17,18,1,15,22,12,19,26,9,23,9,10,16,17,30,13,27,11,18,25,26,8,15,22,29,13,"14?",20,"21?",10,24,7,"IN",28,12,26,9,"PL",30,14,28]
[null,"Draft to-do list",null,"Luisma Torres"]
[null,"Timeline approval",null,"Bob Grow"]
[null,"Relative cost analysis",null,"Rick Pimpinella"]
[null,null,"Staw poll about connector type"]
[null,null,"Eye Safety","Rick Pimpinella, Rubén Pérez de Aranda"]
[null,null,"Butt coupling","Fukuoka-san"]
[null,"Link budget analysis (≤ 25 Gb/s)","PCS encoding, frame structure, modulation scheme, FEC","Rubén Pérez de Aranda"]
[null,null,"Optical channel, and O/E receiver model"]
[null,"Reliability assessment — “reliability constrained link budget” ","Reliability assesment reports"]
[null,null,"Link budget impact ","Rubén Pérez de Aranda"]
[null,"Optical channel components requirements (connectors, cables, etc)",null,"Steven Swanson; Markus Dittmann; Rick Pimpinella; Mabud Choudhury;Michael O'Gorman;Takashi Fukuoka"]
[null,null,"Optical requirements"]
[null,null,"Mechanical requirements"]
[null,null,"Environmental requirements"]
[null,null,"MDI proposal","Steven Swanson"]
[null,"Transceiver specification (PMD)"]
[null,"Link budget analysis (> 25 Gb/s)","VCSEL characterization"]
[null,null,"PCS encoding, frame structure, modulation scheme, FEC"]
[null,null,"Optical channel, and O/E receiver model"]
[null,"Connector Technology (PC/EBO)",null,"Steven Swanson"]
[null,"Connector testing requirements ",null,"Steven Swanson"]
[null,"POF contribution",null,"Watanabe-san"]
[null,"Signal integrity test methods",null,"Rubén Pérez de Aranda"]
[null,"Optical connectors",null,"Fukuoka-san"]
[null,"PMD silicon photonics implementation",null,"Ogura-san"]
[null,"Possibility of bi-directional communication",null,"Kagami-san"]
[null,"Baseline proposal for PMD, MDI",null,"Steve Swanson"]
[null,"PHY health remote monitoring (per D1.0 comment #130)",null,"Rubén Pérez de Aranda"]
[null,"BER test mode and C/45 register (per D.10 comment #13 and #221)",null,"Rubén Pérez de Aranda"]
[null,"EEE/LPI Baseline (per D1.0 comment #16)",null,"Rubén Pérez de Aranda"]
[null,"Loopback modes (per D1.0 comment #49)",null,"Rubén Pérez de Aranda"]
[null,"Add informative annexes with examples of input and output bit streams for LFSR formal definition (per D1.0 comment #82)",null,"Rubén Pérez de Aranda"]
[null,"VCSEL + OM3 PMD"]
[null,null,"50Gb/s over 15m + 2IL Link Budget","Rubén Pérez de Aranda"]
[null,null,"VCSEL reliability","Joseph Pankert"]
[null,"VCSEL + GIPOF PMD"]
[null,null,"Bandwidth and attenuation measurements with consensus among independent laboratories at 850 nm and 980 nm","Takayama-san"]
[null,null,"Link budget revision (25Gpbs objective not reached)","Takayama-san"]
[null,null,"50Gb/s over 15m + 2IL Link Budget","Takayama-san"]
[null,null,"VCSEL reliability (same as VCSEL +OM3)"]
[null,null,"Relative cost comparison","Takayama-san"]
[null,"Silicon Photonics + OM2/OM3 PMD"]
[null,null,"Attenuation and bandwidth measurements with consensus among independent laboratories at 1310 nm","Ogura-san /Richard Pitwon"]
[null,null,"2.5, 5, 10, 25Gb/s over 40m + 4 IL Link Budget in the temperature range","Ogura-san /Richard Pitwon"]
[null,null,"50Gb/s over 15m + 2IL Link Budget  in the temperature range","Ogura-san /Richard Pitwon"]
[null,null,"Silicon photonics system reliability for automotive","Ogura-san /Richard Pitwon"]
[null,null,"Relative cost comparison","Ogura-san /Richard Pitwon"]
[null,null,"Ability to produce in automotive volumes","Ogura-san /Richard Pitwon"]
[null,"Silicon Photonics + GIPOF PMD"]
[null,null,"Attenuation and bandwidth measurements with consensus among independent laboratories at 1310 nm","Takayama-san"]
[null,null,"2.5, 5, 10, 25Gb/s over 40m + 4 IL Link Budget in the temperature range","Takayama-san"]
[null,null,"50Gb/s over 15m + 2IL Link Budget in the temperature range","Takayama-san"]
[null,null,"Silicon photonics system reliability for automotive","Ogura-san /Richard Pitwon"]
[null,null,"Relative cost comparison","Ogura-san /Richard Pitwon"]
[null,null,"Ability to produce in automotive volumes","Ogura-san /Richard Pitwon"]
[null,"50 Gbps PCS/PMA baseline",null,"Rubén Pérez de Aranda"]
[null,"Alternative 50 Gbps PCS/PMA baseline"]
[null,"Relationship between fiber effective bandwidth (EBW) and sensitivity in the receiver",null,"Rubén Pérez de Aranda"]
[null,"Estimate of OM3 EBW at 1310 nm",null,"John Abbott"]
[null,"Modal Noise",null,"Rick Pimpinella"]