## 802.3da_draft2p0_Unsatisfied
ID | CommenterName | CommenterCo | Clause | Subclause | Page | Line | CommentType | Comment | SuggestedRemedy | Response | CommentStatus | ResponseStatus | Topic
317 | Schreiner, Stephan | Rosenberger Hochfrequenztechnik GmbH & Co. KG | 188 | 188.8.2 | 89 | 14 | TR | Channel Return Loss Limit and TCI Return Loss Limit crossing each other at 22.2 MHz and 36.9 MHz. Within this range, the Channel Return Loss Limit is higher than the TCI Return Loss Limit. This can lead to a case, where the TCI specification is met but the channel specification is not met caused by the TCI. | Change Return Loss Limit in the frequency range from 2.8 MHz <= f <= 40 MHz from: "-42.5-20*log10(f)-(0.024/f)+47.5*sqrt(f)-6.39*f+0.0259*f^2" to: "-45.8-20*log10(f)-(4.3/f)+53*sqrt(f)-8*f+0.046*f^2" | ACCEPT IN PRINCIPLE. Change Mixing Segment Return Loss to: 19.5 - Max (0, 25*log10(F/12.5) dB for 40 MHz > F > 6.8 MHz 0.65 + Max (0, .65+30*log10(F/1.6)) dB for 0.3 < F < 6.8 MHz Editorial license to reformat equation per other comments and 802.3 style. | A | U | Mixing Segment

## 802.3da_draft2p1_Unsatisfied
ID | CommenterName | CommenterCo | Clause | Subclause | Page | Line | CommentType | Comment | SuggestedRemedy | Response | CommentStatus | ResponseStatus | Topic
67 | Slavick, Jeff | Broadcom | 148 | 148.4.4.6 | 58 | 50 | TR | The exit transitions from NEXT_TX_OPPORTUNITY to B does a greater than or equal to compare to plca_node_count and it looks like the exit to G does a less than or equal to comparison. If so then which branch are you supposed to take if curID is equal to plca_node_count. | Change the transition to G to be just a less than compare to plca_node_count. | REJECT. No change to draft. The Commenter appears to have misread the use of < and underline (to indicate inserted text) as a less than or equal to sign on the exit condition to branch G. | R | W | Editorial
68 | Slavick, Jeff | Broadcom | 148 | 148.4.4.6 | 58 | 35 | TR | In the BURST state there is no "stop append_commit_timer" So if you re-etner BURST state won't the append_commit_timer_done be true? Which means you'd enter ABORT instead of waiting out the burst_timer if you have max_bc > 0. | Add "stop append_commit_timer" before the IF statement in BURST state of Figure 148-4, part b | REJECT. The suggesting re-entry doesn't happen after append_commit_timer is started. Looping occurs if BURST exits to "F", going to TRANSMIT, which then comes back to BURST, which only happens when max_bc > 0. (in this case BURST/TRANSMIT loop until either the burst count (bc) is >= max__bc, in which case it moves on, to the next TO, or the burst_timer is complete and TX_EN has dropped. append_commit_timer isn't started in this loop. append_commit_timer is only started when max_bc is = 0, and in this case, burst_timer is not started, so BURST waits until append_commit_timer is done before exiting to ABORT. Note that max_bc is not changed in the state diagram (it maps to a management attribute - and if these are changed, then it is likely plca needs a reset). | R | W | PLCA
70 | Slavick, Jeff | Broadcom | 188 | 188.4.2.7 | 81 | 9 | TR | "not_done" is not a timer property, just "_done" | Change "xmit_max_timer_not_done" to "!xmit_max_timer_done" in the ESD -> GOOD_ESD and DATA -> DATA transitions in Figure 188-5 part b | ACCEPT IN PRINCIPLE. (Editor's note: No change to Suggested Remedy, but Commenter may wish to submit a Maintenance request to also make this change to Figure 147-5.) Change "xmit_max_timer_not_done" to "!xmit_max_timer_done" in the ESD -> GOOD_ESD and DATA -> DATA transitions in Figure 188-5 part b | A | W | Editorial
73 | Slavick, Jeff | Broadcom | 188 | 188.12.4.1 | 105 | 35 | TR | There should be PICS for the unjab_timer | Add a PICS for the unjab_timer point to 188.4.2.9 with a Status of O and Yes / NA options | ACCEPT. | A | W | PCS

## 802.3da_draft2p2_Unsatisfied
ID | CommenterName | CommenterCo | Clause | Subclause | Page | Line | CommentType | Comment | SuggestedRemedy | Response | CommentStatus | ResponseStatus | Topic
115 | Schreiner, Stephan | Rosenberger Hochfrequenztechnik GmbH & Co. KG | 189 | 189.6.1 | 153 | 10 | TR | Equation 189-1 causes issues with sections 188.8 and 188.9. For high unit loads greater than 11, the channel return loss specified in 188.8 cannot be met because the MPI RL limit is more lenient than the channel RL limit. For lower unit loads, it is assumed that the channel return loss will also not be met and therefore needs to be verified. For unit loads greater than 3, the return loss limit, in conjunction with the TCI insertion loss, is not passive, contradicting the concept of making the return loss dependent on the unit load in order to reduce implementation effort. The limit line at frequencies above 26.5 MHz is stricter than the TCI return loss, impacting technical feasibility. In summary, the introduction of 189.6.1 and its dependency on the Unit Load Concept affects multiple sections in 188.8 and 188.9 and will require significant effort to resolve and align the affected requirements. | Insert a note: Impairments to sections 188.8 and 188.9 have been identified. Adaptations to sections 188.8, 188.9, and 189.6.1 might be necessary to maintain consistency and technical feasibility. | REJECT. Commenter offers insufficient information for a remedy. Note: Chair to charter an ad hoc to review return loss as well as TCI requirements for carrying power. Ad hoc to report by July - in preparation for comments to initial SA ballot. | R | W | TCI