{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Action Items"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Action Items","index":0,"n_rows":27,"n_cols":59,"rows_kept":27,"cut":false,"hidden":false,"merged":[[2,3,2,11],[2,12,2,36],[3,39,3,40],[3,41,3,42],[3,43,3,44],[3,56,3,57],[2,37,2,58],[3,45,3,47],[3,48,3,49],[3,50,3,51],[3,52,3,53],[3,54,3,55]]}
[]
[]
[null,null,null,2020,null,null,null,null,null,null,null,null,2021,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,2022]
[null,null,null,"Jul","Aug","Sep","Oct",null,"Nov",null,"Dec",null,"Jan",null,"Feb",null,"Mar",null,null,"Apr",null,"May",null,"Jun",null,"Jul",null,"Aug",null,"Sept",null,"Oct",null,"Nov",null,"Dec",null,"Jan","Feb","Mar",null,"Apr",null,"May",null,"Jun",null,null,"Jul",null,"Aug",null,"Sep",null,"Oct",null,"Nov",null,"Dec"]
[null,null,null,"'20",26,23,7,21,4,18,2,16,13,27,10,24,10,17,24,7,21,19,26,16,30,14,19,11,25,8,22,6,20,3,17,1,15,18,23,9,23,6,20,4,18,1,15,29,13,27,10,24,7,21,5,19,2,16,14]
[]
["finish first","Consensus Model",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"X",null,"X","X",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Topology, spur/stub length","Bob Voss","x",null,null,null,null,null,null,null,null,null,null,null,"x",null,"x","x","x","x",null,null,null,null,null,null,null,"x"]
[null,"connection (inductance, capacitance, resistance) - MDI loading","Chris Diminico",null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x","x",null,null,null,null,null,null,"X","Chris: done",null,"x",null,null,"x",null,null,null,null,null,"x"]
[null,"specifications (IL, RL, mode conversion, etc.), MDI specs (tighter than CG?) [redundant to line 8,9?]","Chris Diminico","x",null,null,null,"x",null,"x","x",null,null,"x",null,null,null,"x",null,null,null,null,null,null,null,null,null,null,"x"]
["dependent\non 7-10","Power Coupling Network definition","Chris Diminico, Michael Paul",null,null,null,null,null,null,null,null,null,null,null,null,null,"x","x",null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Hot insertion, removal and ramifications","Bob Voss, Peter Jones, Jason Potterf, Heath Stewart"]
[null,"power specifications (max & min voltages / power levels / max currents / loop resistances) and what regulations set these limits","Michael Paul",null,null,null,null,null,null,null,"x","x",null,"x",null,"x"]
[null,"Startup Sequence","Michael Paul","x","x","x",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"X","X"]
[null,"Reach extension / validation, interacts with mixing segment spec (dependent) "]
[null,"LLDP  ","Jason Potterf, Peter Jones","x",null,null,null,null,null,null,null,null,null,null,null,null,"x"]
["Dependent\non PHY ","Backwards compatible noise immunity (e.g., FEC)","Gergely Huszak",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"X",null,"X"]
["decision","Sleep/standby/EEE/EEE signaling","George Zimmerman",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"X"]
[null,"Failure modes and preferred behavior (potential to defer until after 1.0)","Gergely Huszak, George Zimmerman"]
[null,"Definition of backward compatibility  / review of backward compatibility objective","Peter Jones, Jason Potterf",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x",null,"x"]
[]
[null,"Closed "]
[null,"Additional requirements for TSN support? (supporting 1588)","Peter Jones",null,null,null,null,null,null,null,null,null,null,null,null,"x","done"]
[null,"Mixing Segment data membership & PLCA ID ","Peter Jones, Piergiorgio Beruto, Kamal Dalmia",null,null,null,null,"x","x","x",null,null,null,null,null,"x","x","x","done",null,null,null,null,"X",null,null,null,null,null,null,null,null,null,null,null,null,null,null,"x"]
[null,"Definitions section","None Needed"]
[null,"EEE signaling (consolidated into other EEE item)","George Zimmerman",null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,null,"X"]
[null,"Topology, allow Y connections? - NO","Bob Voss","x",null,null,null,null,null,null,null,null,null,null,null,"x",null,"x","x","x","x",null,null,null,null,null,null,null,"x",null,null,null,null,null,null,null,null,null,"done"]