## Action Items
Planned to vote
On Track
Started, risk of being late
late
Task | Subtask ( or details of main task) | Owner | 2023
|  |  | Mar |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2
Plenary | bar: Mar 11; Jul 28; Nov 46
Interim | bar: May 20; Sep 37
Liaison letter to the ISO TC 22/SC 32/WG 10 to check temperature requirement | convener: Masahiro Goto | Martino Kjersti | Jul 28: ▼ Revies of response
Liaison letter to the IEC TC86/SC86A |  | Vince Ferretti | bar: Mar 11
Frequency response measurement at interested parties and determine figure of merit for A4j/A4i |  | Yuji Watanabe
Frequency response measurement at all relevant wavelength (980nm, 850nm, ) | choose methodology | Yuji Watanabe
choose proper figure of merit
connection effect
temperature effect
macrobending effect
humidity effect
Attenuation measurement | connection effect
temperature effect
macrobending effect
humidity effect
In-line connection | suitable connectivity investigate for automotive application
(attenuation and modal noise)
round robin testing |  |  | Dec 49: In 2024
Preparation of measurement metholodogy for POF