## Action Items
Planned to vote
On Track
Started, risk of being late
late
Task | Subtask ( or details of main task) | Owner | 2023 | [41 empty] | 2024
|  |  | Mar |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Plenary | bar: Mar 11; Jul 28; Nov 46
Interim | bar: May 20; Sep 37
Liaison letter to the ISO TC 22/SC 32/WG 10 to check temperature requirement | convener: Masahiro Goto | Martino Kjersti | Jul 28: ▼ Review of response
Liaison letter to the IEC TC86/SC86A |  | Vince Ferretti | bar: Mar 11
Frequency response measurement at interested parties and determine figure of merit for A4j/A4i |  | Takeshi Hirose/Yuji Watanabe | bar: Jul 28 to Sep 36
Effect of launching condition | Check effect of launching condition with three different launching modes | Takashi Hirose | bar: Sep 38 to Oct 44
Frequency response measurement at all relevant wavelength (980nm, 850nm, ) | choose methodology | Takeshi Hirose/Yuji Watanabe
choose proper figure of merit
connection effect
temperature effect
macrobending effect | bar: Aug 32 to Sep 36
humidity effect
Attenuation measurement | connection effect | Takeshi Hirose/Yuji Watanabe
temperature effect
macrobending effect | bar: Aug 32 to Sep 36
humidity effect
In-line connection | suitable connectivity investigate for automotive application | Takeshi Hirose/Yuji Watanabe
(attenuation and modal noise)
round robin testing |  |  | Dec 49: In 2024
Define PMD
Contribution to IEC/SC86A/WG1 |  | Yuji Watanabe | bar: Oct 40 to Oct 44; Nov 46
Preparation of measurement metholodogy for GI-POF
Due to the company's policy, samples are not available for every parties. Measurements at Universituy was conducted.
Because concern on butt joint with POF was proposed, vibration test in accordance with ISO16750-3 was conducted. Butt joint can be applied. Further discusion will be related to Imprementation.
Test conditions considering actual usage willbe applied
Effect of macro bend is not observed
Effect of macro bend is not observed
Send contribution to IEC SC86A WG1
Contribution about history of MOST connector