## Action Items
Planned to vote
On Track
Started, risk of being late
late
Task | Subtask ( or details of main task) | Owner | 2023
|  |  | Mar |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
|  |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2
Plenary | bar: Mar 11; Jul 28; Nov 46
Interim | bar: May 20; Sep 37
Liaison letter to the ISO TC 22/SC 32/WG 10 to check temperature requirement | convener: Masahiro Goto | Martino Kjersti | Jul 28: ▼ Review of response
Liaison letter to the IEC TC86/SC86A |  | Vince Ferretti | bar: Mar 11
Frequency response measurement at interested parties and determine figure of merit for A4j/A4i |  | Takeshi Hirose/Yuji Watanabe | bar: Jul 28 to Sep 36
Frequency response measurement at all relevant wavelength (980nm, 850nm, ) | choose methodology | Yuji Watanabe
choose proper figure of merit
connection effect
temperature effect
macrobending effect
humidity effect
Attenuation measurement | connection effect
temperature effect
macrobending effect
humidity effect
In-line connection | suitable connectivity investigate for automotive application
(attenuation and modal noise)
round robin testing |  |  | Dec 49: In 2024
Preparation of measurement metholodogy for GI-POF
Due to the company's policy, samples are not available for every parties. Measurements at Universituy was conducted.
Because concern on butt joint with POF was proposed, vibration test in accordance with ISO16750-3 was conducted