## Slide 1: IEEE 802.20 Project Development Plan- 802.20-PD-07R1
Project Launch Process: July 04 Dates New Dates
  ECSG Approval of PAR/5C Sept 02
  Approval of PAR/5C by LMSC Executive Committee Nov 15, 02
  Approval of PAR by IEEE-SA Board Dec 12, 02
Stage Setting:
  Initial Membership Meeting Mar. 03
  Closure on Requirements July 04
  Closure on Channel Models Sept 04 Jan/Mar 05
  Closure on Evaluation Criteria Sept 04 Jan/Mar 05
  Procedure for proposal selection and merging (“Down select”) Sept 04 Mar 05
Proposal Selection
  Call for Proposals Sept 04 Mar 05
  Proposal Presentations, Simulation Results, and Mergers Nov 04-May 05 May-Sept 05
  Final Selections July 05 Nov 05
Standard Development
  Drafting the Standard July-Sept 05 Nov 05-Jan 06
  First WG Letter Ballot Oct 05 Jan 06
  Second WG Ballot Feb 06 May 06
  Sponsor Ballot June 06 July 06
  Sponsor Recirculation Sept 06 Sept 06
IEEE-SA Approval
  Submission to Rev. Com Nov 06 Nov 06
  SA Approval Dec 06 Dec 06
Nov. 18, 2004
As approved at the November Plenary