Meeting services requirements meeting minutes	March 13, 2002.

Met Wednesday March 13, 2002 10AM-11AM LT.

Attendees: Dawn, Buzz, Bob G., Bill Quackenbush, Paul N.

The objective of the meeting was to review the status of  the high level set of requirements to be included in the meeting planner RFP.

1) Prepare motion to extend planner contract at Friday SEC meeting

Grow			March 15 2002

2) Schedule:

Complete RFP				Buzz			May 31 2002

Competitive bids due			Buzz			June 28 2002

Exec Sec recommendation to SEC reflector	Buzz		July 01 2002

Authorize selection			SEC			July 08 2002

Sign contract				Buzz			July 22 2002

3) Review Dawn’s statement of work (Dawn please attach a copy of your SFW).

- add next level of outline detail

Dawn/Buzz		April 05 2002

- complete first draft of RFP	Dawn/Buzz		May 01 2002

- review draft RFP, modify, finalize	Buzz		May 31 2002

4) Bookkeeping Services detail		BobG/BillQ	March 29 2002

Meeting adjourned 11:37 AM LT

--Paul

Minutes from Wed Nov 14 2001 meeting:

The top level requirements are listed below.  Detail must be added to each requirement and delivered to Buzz—actions/due dates have been assigned as per the list below.  Buzz will compile the inputs into a top level RFP to be issued for quote by January 31.

Top level requirement			Responsible		Due

1) Equipment management		Dawn			January 8th

2) Networking				Paul N.		December 1st

3) Registration Services		Buzz			January 8th

4) Bookkeeping Services		Bob G.			December 1st

5) Attendance record automation	Stuart K.		December 1st

6) Facilities management		Buzz			January 8th

7) Web management			Bob O’Hara		January 8th

8) Compile above inputs, generate complete meeting services RFP and issue to several meeting planner providers		Buzz			January 31st

9) Competitive bids due		Buzz			February 28th

10)  Finalize decision			SEC			March 2002 plenary